## Slide 1
DUBAI METRO BLUE LINE — PROGRAMME DASHBOARD
Weekly Progress Meeting with RTA #35 | Project No. RAL/PPDD/081
22 JUNE 2026
651,790
Manhours Worked (Week)
11 / 22
Reportable Incidents (YTD/PTD)
228
HSE Inspections (Week)
93%
ITR Closed (20,146 of 21,669)
842 (783)
NCRs Raised (Cumulative)
1,087 m
TBM-1 Excavation to date (90%)
1. HEALTH, SAFETY, ENVIRONMENT & SECURITY
Avg. Manpower (week)
10,864 (M 9,074 / S 1,790)
Manhours Worked (week)
651,790
Hours since last LTI
3,255,610
Reportable Incidents (Wk/YTD/PTD)
0 / 11 / 22
HSE Inductions (week)
19
Toolbox Talks (week)
180
HSE Inspections (week)
228
Near Misses/Unsafe Acts (week)
409
Incidents (16-Jun): Excavator boom struck DEWA overhead cable at Ruwaiyah Depot; concrete slurry overflow at Creek piling. No injuries; both under investigation.
2. QUALITY
NCR Status (Open/Closed/Total)
Open
Closed
Total
411 (393)
431 (390)
842 (783)
ITR Status
Closed
Open
With Engr
20,146 (93%)
1,523
494
MAR Status (SONO/NOWC/R&R/UR)
SONO
NOWC
R/R&R
UR
198
346
111
88
Prequalifications (SONO/NOWC/R&R/UR)
SONO
NOWC
R/R&R
UR
162
75
31
26
ECR: 2 ECRs with RTA for Approval (Ref. PAJV-001668, -001795)
3. DESIGN STATUS — KEY ITEMS
Alignment/Track
DCP1–DCP3 Mainline/Depot approved; DCP4 in progress. Mainline mock-up Mar-27.
Viaduct Substr.
Stretch 03 piers/BB03 station span: Conditional NOWC pending compliance checks.
Viaduct Superstr.
BB03 & Typical Station Global Conditional NOWC 19-Jun; BG33 (BC01-03) R&R.
UG Stations
BB05/BB06 base & concourse slabs mostly NOWC; several R&R awaiting resubmission.
Elevated Stations
BB03/04/32/36 roof & entrance pods under review/R&R; BG31 piers blast assessment pending.
Tunnels & Depot
Tunnel Global Pkg NOWC; several validation notes NOWC; Depot APDPs under review/R&R.
Architecture
Pop-ups/entrances/landscape layouts in progress; BG31 Chiller Yard location confirmed.
4. KEY RISKS & CRITICAL ISSUES
Station BG31: Technical level beams & GL8-11 piers — blast assessment pending, approval expected this week.
TBM 3 (towards BB05): idle since 22-May; conveyor belt tower assembly 75% complete — delaying restart.
TBM 2 (towards Car Mart): 17.1% excavated, 33m behind plan; breakthrough now forecast early Dec-2026.
BG34 Concourse Beams: NOWC for Grid 3 & 23 only; remainder pending ICF/Arch DCP2 (escalator shifting issue).
BB06 Base Slab: R&R for Movement Joint areas; Technical Note under review.
Noise & vibration mitigation on mainline and pre-cast track slab system proposal pending.
5. CONSTRUCTION — KEY ACHIEVEMENTS
TBM1: 1,060/1,216m (+180m ahead); breakthrough at BR07 forecast 29-Jun.
Tunnel segments: ~2,600 rings produced, 940 installed; stockpile ~3km.
Viaduct segments: 496 completed. LG1 erecting 2nd TS; LG2 launched 15-May; LG3 commissioned.
Marine piles to Creek Crossing ahead of programme.
BR07: concourse slab concrete complete; TBM on track for breakthrough 29-Jun.
BB06: stub columns & external wall concreting started ahead of programme.
TUNNEL BORING PROGRESS
TBM
Progress
vs Plan
Status
TBM-1
(→BR07)
1,087/1,216m
(90%)
+207m
ahead
BO 29-Jun-26
(BB06→BR07)
TBM-2
(→Car Mart)
583/3,392m
(17.1%)
+75m
ahead
BO ~Dec-26
TBM-3
(→BB05)
83/2,449m
(3.5%)
-260m
behind
Idle since
22-May-26
Precast Yard: 496 of 3,897 segments cast (Plan 12.7% vs Actual 12.8% — on track). 4 of 5 long-lead moulds assembled; remaining items in transit.
6. PROJECT CONTROLS — STATION PROGRAMME
BB05 (Intl. City 2)
Concourse slab 50%, Excavation-Base 7.4%. On track.
BB06 (Intl. City 1)
Base slab 28% (8/28 complete). Wall pours ahead of plan.
BR07 (Dragon Mart)
Base slab NOWC; concourse slab complete; TBM breakthrough imminent.
BR08 (Al Warqa)
Base slab pour 1 preparation underway.
BR09 (Mirdif City Ctr)
Roof slab zone 1 excavation commenced.
BB03/04/BG32/36/BG34
Spine & wing beam works ongoing; on track per target programme.
7. BIM & 8. AOB
BIM
RFI submissions and reviews ongoing (e.g. MLCC-N0003-PMC-IFM-BIM-RFI-00010/00011 — Picklist Additions, Rev C01).
AOB / Other Focus Items
Reconstituted stone sample colour shades selected for WATER, AIR, FIRE themes (18-Jun review).
Advertising DCP2 presentation awaiting Mada Media date confirmation.
Retail report C02 received 22-May; shared with CID — response being chased.
Interface matrix for Iconic Station MEP/RSY/VT/Façade agreement with Emaar — workshops planned.
Consultancy Services for Dubai Metro Blue Line — A Joint Venture
Source: WPP #35 Draft, 22-Jun-2026