## Register
TRANSMITTAL REGISTER
Generated: 17/06/2026 08:08
Draft | Aconex Reference | Submittal Date | Document Reference No./Package no. | Submittal Item Description | Current Rev | Rev. | Type | Discipline | Sub Discipline | No of Items | Lead | DCP | Due date of Response by the Engineer (+21 days from Submittal date) | Response Ref. | Date Responded by the Engineer | Response Status, days | Days Overdue | Review Status | Actual Status (Latest Rev) | Contractor Response Due (+14 Days from Response Date) | Contractor Date Responded | Contractor Days Overdue | Contractor Response Status Days | Data Date | Remarks
| MLCC-TRANSMIT-018011 | 2026-06-13 | MLCC-S0681-CIV-VBR-PIR-DRW-13000 to 13002 | Shop Drawing Submisison - Stretch-04.2 Viaduct Structure Foundation-Pier Shop Drawing & BBS-PM-100, BBS-PM-101, BBS-PM-102 and Setting Out Pocket Track PM-100 to PM-102: MLCC-S0681-CIV-VBR-PIR-DRW-13000 to 13002 and 13015_Rev C01 | C01 |  | DRW | CIV | VBR | 1
| MLCC-TRANSMIT-018010 | 2026-06-12 | MLCC-S0800-CIV-STN-RFC-DRW-13541 | Re: Shop drawings-BR09 -Roof Slab Pour 3 Top Slab:(MLCC-S0800-CIV-STN-RFC-DRW-13541 - MLCC-S0800-CIV-STN-RFC-DRW-13560)_Rev.C02 | C02 |  | DRW | CIV | STN | 2
| MLCC-TRANSMIT-018009 | 2026-06-12 | MLCC-N0003-ARC-NWW-GAR-MTS-00121 | Material Approval Request for Epoxy Floor Coating "X-Tech AntiStatic SLE": MLCC-N0003-ARC-NWW-GAR-MTS-00121_Rev.00 | 00 |  | MAT | ARC | NWW | 1
| MLCC-TRANSMIT-018008 | 2026-06-12 | MLCC-N0003-ARC-NWW-GAR-MTS-00119 | Material Approval Request for Epoxy Floor Coating "X-Tech EpoxySeal FLR100": MLCC-N0003-ARC-NWW-GAR-MTS-00119_Rev.00 | 00 |  | MAT | ARC | NWW | 1
| MLCC-TRANSMIT-018007 | 2026-06-12 | MLCC-N0003-CIV-NWW-GAR-MTS-00274 | Re: Material Approval Request for X-Tite SBA MT "X-Calibur Emirates": MLCC-N0003-CIV-NWW-GAR-MTS-00274_Rev.01 | 01 |  | MAT | CIV | NWW | 1
| MLCC-TRANSMIT-018006 | 2026-06-12 | MLCC-N0003-BES-ELE-LVD-MTS-00047 | Material Approval Request for Cable Labels "HellarMann Tyton/MNG": MLCC-N0003-BES-ELE-LVD-MTS-00047_Rev.00 | 00 |  | MAT | BES | ELE | 1
| MLCC-TRANSMIT-018005 | 2026-06-12 | MLCC-N0003-PMC-PRC-RER-RPT-00495 | Daily Progress Report of 10-June-2026 : MLCC-N0003-PMC-PRC-RER-RPT-00495_Rev.00 | 00 |  | RPT | PMC | PRC | 1
| MLCC-TRANSMIT-018004 | 2026-06-12 | MLCC-S0727-CIV-VBR-PAP-FCR-00002 | FCR Submission - Field Change and Drawing Modification Request (FCR) for Viaduct Pile Cap PM-198 and PM-199 : MLCC-S0727-CIV-VBR-PAP-FCR-00002_Rev.C01 | C01 |  | FCR | CIV | VBR | 1
| MLCC-TRANSMIT-018003 | 2026-06-12 | MLCC-S0727-CIV-VBR-FND-FCR-00001 | FCR Submission - Field Change and Drawing Modification Request (FCR) for Viaduct Static Pile Load Test for PM172 : MLCC-S0727-CIV-VBR-FND-FCR-00001_Rev.C01 | C01 |  | FCR | CIV | VBR | 1
| MLCC-TRANSMIT-018002 | 2026-06-12 | MLCC-N0003-CIV-VBR-PIR-FCR-00009 | FCR Submission - Field Change and Drawing Modification Request (FCR) for Viaduct Structure – Global-Twin span (2x44) superstructure S5 to S10 segments : MLCC-N0003-CIV-VBR-PIR-FCR-00009_Rev.C01 | C01 |  | FCR | CIV | VBR | 1
| MLCC-TRANSMIT-018001 | 2026-06-12 | MLCC-S0647-CIV-STN-GAR-RPT-26004 | Drawing and Report Submission - Design Report for Birdcage & Bridge Scaffolding for Viaduct Protection Scaffold Calculations at BG31 : MLCC-S0647-CIV-STN-GAR-RPT-26004 & MLCC-S0647-CIV-STN-GAR-DRW-26000-26002_Rev.C01 | C01 |  | RPT | CIV | STN | 2
| MLCC-TRANSMIT-018000 | 2026-06-12 | MLCC-S0701-CIV-CCV-RFC-DRW-13003 to 13010 | Re: Shop Drawings Submission - CC01-Cut & Cover Structure D-Wall Reinforcement Shop Drawings Type-D Primary Panel (P35) and (P25): MLCC-S0701-CIV-CCV-RFC-DRW-13003 to 13010_Rev C02 | C02 |  | DRW | CIV | CCV | 1
| MLCC-TRANSMIT-017999 | 2026-06-12 | DE.UGS.GE09.MEP.M4 | Package Submission - DCP2 - Underground Station BB05 MEP VAC: DE.UGS.GE09.MEP.M4.D3_Rev.C01 | C01 |  |  |  |  | 1 |  | DCP2
| MLCC-TRANSMIT-017998 | 2026-06-12 | MLCC-S0651-CIV-VBR-FND-DRW-13022 | Shop Drawing Submission - Stretch-09.1 Viaduct Structure Foundation Pile Cap Shop Drawing & BBS - PR-2: MLCC-S0651-CIV-VBR-FND-DRW-13022 and MLCC-S0651-CIV-VBR-FND-DRW-13023_Rev.C01 | C01 |  | DRW | CIV | VBR | 2
| MLCC-TRANSMIT-017997 | 2026-06-12 | MLCC-C0196-BES-NWW-CDS-RPT-70000 | Package Submission - DCP3 - DCP2 - Station BB03 - MEP Design Report ( DE.ELS.GE11.MEP.M4.D3) : MLCC-C0196-BES-NWW-CDS-RPT-70000_Rev.C01 | C01 |  | RPT | BES | NWW | 1 |  | DCP3
| MLCC-TRANSMIT-017996 | 2026-06-12 | MLCC-N0003-CIV-NWW-GAR-RPT-21554 | Drawing and Report Submission - Temporary PT for Creek Balanced Cantilever : MLCC-N0003-CIV-NWW-GAR-RPT-21554_Rev.C01 | C01 |  | RPT | CIV | NWW | 1
| MLCC-TRANSMIT-017995 | 2026-06-12 |  | Shop Drawing Submission - Station BG36 - Structure Concourse Level Wing Beam PTB13 PTY Detail, Reinforcement and End Details along Grid 14_Rev.C01 | C01 |  |  |  |  | 1
| MLCC-TRANSMIT-017994 | 2026-06-12 | DE.ANX.AX01.STR.S0 | NOC Drawing Submission - Annex-BL-EES-09 - Structure & Viaduct Tunnel : DE.ANX.AX01.STR.S0.NC_Rev.C03 | C03 |  |  |  |  | 1
| MLCC-TRANSMIT-017993 | 2026-06-12 | MLCC-N0003-PMC-PRC-SCH-SCH-00037 | Schedule Submission - 5 Weeks Lookahead dated 06-June-2026 : MLCC-N0003-PMC-PRC-SCH-SCH-00037_Rev.00 | 00 |  | OTH | PMC | PRC | 1
| MLCC-TRANSMIT-017992 | 2026-06-12 | DE.ZNE.ZN03.UTI.U2 | Package Submission - DCP2 - Z0042 Utility Package : DE.ZNE.ZN03.UTI.U2.D2_Rev.C01 | C01 |  |  |  |  | 1 |  | DCP2
| MLCC-TRANSMIT-017991 | 2026-06-12 |  | Re: Package Submission - DCP2 - Zone 4A Utility Z0043 (Creek Mainline) Package : DE.ZNE.ZN4A.UTI.U2.D2_Rev.C02 | C02 |  |  |  |  | 1 | Yazan Safieh | DCP2
| MLCC-TRANSMIT-017990 | 2026-06-12 | DE.UGS.GE09.MEP.M2 | Package Submission - DCP3 - Underground Station BB05 MEP Drainage and Waste & Water Supply: DE.UGS.GE09.MEP.M2.D3_Rev.C01 | C01 |  |  |  |  | 1 |  | DCP3
| MLCC-TRANSMIT-017989 | 2026-06-12 | MLCC-S0786-CIV-VBR-PAP-DRW-13000 | Shop Drawing Submission - Stretch-09.1 Viaduct Structure Foundation Pile Cap Shop Drawing & BBS - PR-2: MLCC-S0786-CIV-VBR-PAP-DRW-13000 and MLCC-S0786-CIV-VBR-PAP-DRW-13001_Rev.C01 | C01 |  | DRW | CIV | VBR | 2
| MLCC-TRANSMIT-017988 | 2026-06-12 | MLCC-S0742-CIV-STN-GAR-DRW-13233 to 13234 | Shop Drawing Submission - Station BB03 - Structure Concourse Wing Beam PT Detail, Reinforcement Elements and Base Plate Anchor Bolt Detail at Grid 22: MLCC-S0742-CIV-STN-GAR-DRW-13233 to 13234, 13182 to 13188, 13233, 13234 and 13018_Rev.C01 | C01 |  | DRW | CIV | STN | 1
| MLCC-TRANSMIT-017987 | 2026-06-12 | MLCC-C0189-CIV-NWW-GAR-CAL-10001 | Report Submission - BB06-Liftable Scaffold Calculations (2.50m+2.50m) : MLCC-C0189-CIV-NWW-GAR-CAL-10001_Rev.C01 | C01 |  | CAL | CIV | NWW | 1
| MLCC-TRANSMIT-017986 | 2026-06-12 | DE.UGS.RE01.STR.S5 | Re: Package Submission - DCP3 - Station BR09 - Structure Base Slab : DE.UGS.RE01.STR.S5.D3_Rev.C01 (IDV Certificate Submission) | C01 |  |  |  |  | 1 |  | DCP3
| MLCC-TRANSMIT-017985 | 2026-06-12 | MLCC-S0716-CIV-EES-RFC-DRW-11046 | Shop Drawing Submission - Annex Structure - BL-EES07 Structure D-Wall Primary Panel P3 Type II AX : MLCC-S0716-CIV-EES-RFC-DRW-11046-11051_Rev.C01 | C01 |  | DRW | CIV | EES | 1
| MLCC-TRANSMIT-017984 | 2026-06-12 | MLCC-C0003-ARC-NWW-GAR-QUA-00001 | Re: PQ Submission - Prequalification Submittal For Dezign Technic LLC : MLCC-C0003-ARC-NWW-GAR-QUA-00001_Rev.01 | 01 |  | QUA | ARC | NWW | 1
| MLCC-TRANSMIT-017983 | 2026-06-12 |  | Package Submission - DCP3 - Stretch 01 - Viaduct Structure Bearing - 3 & 4SP : DE.VDT.B34S.STR.V2.D3_Rev.C01 | C01 |  |  |  |  | 1 |  | DCP3
| MLCC-TRANSMIT-017982 | 2026-06-12 | MLCC-S0300-BES-ESC-SYW-DRW-16000 | Drawing Submission - G30 Creek Station Enhancement Works - Replacement of Escalators : MLCC-S0300-BES-ESC-SYW-DRW-16000-16008_Rev.C01 | C01 |  | DRW | BES | ESC | 1
| MLCC-TRANSMIT-017981 | 2026-06-12 |  | Package Submission - DCP3 - Power Supply (PDS) - Key Interlocking Schematic - BG34 Station : RLS.1.1.9.8.1.3.5.7_Rev.C01 | C01 |  |  |  |  | 1 |  | DCP3
| MLCC-TRANSMIT-017980 | 2026-06-12 | MLCC-S0716-CIV-EES-RFC-DRW-11040 | Shop Drawing Submission - Annex Structure - BL-EES07 Structure D-Wall Primary Panel P12 Type I-C : MLCC-S0716-CIV-EES-RFC-DRW-11040-11045_Rev.C01 | C01 |  | DRW | CIV | EES | 1
| MLCC-TRANSMIT-017979 | 2026-06-12 | MLCC-S0719-CIV-STN-RFC-DRW-13241 | Shop Drawing Submission - Station BB05-Structure Pour-7 Concourse Slab : MLCC-S0719-CIV-STN-RFC-DRW-13241-13256_Rev.C01 | C01 |  | DRW | CIV | STN | 1
| MLCC-TRANSMIT-017978 | 2026-06-12 | MLCC-N0003-CIF-SIF-GEN-ICD-51222 | Re: ICD Submission - DCP2 - Interface Control Document for PWA-PDS : MLCC-N0003-CIF-SIF-GEN-ICD-51222_Rev.C02 | C02 |  | ICD | CIF | SIF | 1 |  | DCP2
| MLCC-TRANSMIT-017977 | 2026-06-12 | MLCC-N0003-UTL-NWW-GEN-MST-00015 | Re: Method Statement For Protection of Existing DUSUP Line : MLCC-N0003-UTL-NWW-GEN-MST-00015_Rev.01 | 01 |  | MST | UTL | NWW | 1
| MLCC-TRANSMIT-017976 | 2026-06-12 | MLCC-N0003-CIV-RAR-GAR-MST-00001 | Re: Method Statement For Site Clearance : MLCC-N0003-CIV-RAR-GAR-MST-00001_Rev.01 | 01 |  | MST | CIV | RAR | 1
| MLCC-TRANSMIT-017975 | 2026-06-12 | MLCC-N0003-PMC-PRC-RER-RPT-00492 | Weekly Progress Report - 06 June 2026 : MLCC-N0003-PMC-PRC-RER-RPT-00492_Rev.00 | 00 |  | RPT | PMC | PRC | 1
| MLCC-TRANSMIT-017974 | 2026-06-12 | MLCC-N0003-OSM-ROM-GEN-RPT-51000 | Re: Report Submission - DCP2 - Preliminary Operation Plan: MLCC-N0003-OSM-ROM-GEN-RPT-51000_Rev.C02 | C02 |  | RPT | OSM | ROM | 1 |  | DCP2
| MLCC-TRANSMIT-017973 | 2026-06-12 | MLCC-N0003-ENG-SSA-RAM-RPT-00001 | Report Submission - FMECA - Track Permanent Way : MLCC-N0003-ENG-SSA-RAM-RPT-00001_Rev.C04 | C04 |  | RPT | ENG | SSA | 1
| MLCC-TRANSMIT-017972 | 2026-06-12 | DE.TNL.GN00.STR.T1 | Re: Package Submission - DCP3 - Bored Tunnel Special Segment Global Package : DE.TNL.GN00.STR.T1.D3_Rev.C01 | C01 |  |  |  |  | 1 |  | DCP3
| MLCC-TRANSMIT-017971 | 2026-06-12 | MLCC-N0003-PMC-THA-EMC-RPT-00002 | Report Submission - EMC Risk Analysis Report : MLCC-N0003-PMC-THA-EMC-RPT-00002_Rev.C01 | C01 |  | RPT | PMC | THA | 1
| MLCC-TRANSMIT-017970 | 2026-06-12 | DE.DPT.YPPC.STR.S0 | Re: Package Submission - DCP3 - Depot BDR04 - Structure Yellow Plant Building: DE.DPT.YPPC.STR.S0.D3_Rev.C01 | C01 |  |  |  |  | 1 |  | DCP3
| MLCC-TRANSMIT-017969 | 2026-06-12 | DE.DPT.OHBD.STR.S0 | Re: Package Submission - DCP3 - Depot BDR03 Overhaul Workshop Building (APDP) - Structure: DE.DPT.OHBD.STR.S0.D3_Rev.C01 | C01 |  |  |  |  | 1 |  | DCP3
| MLCC-TRANSMIT-017968 | 2026-06-12 | MLCC-C0191-BES-NWW-CDS-RPT-70000 | Package Submission - DCP3 - Station BB05 - MEP Design Report (DE.UGS.GE09.MEP.M4.D3) : MLCC-C0191-BES-NWW-CDS-RPT-70000_Rev.C01 | C01 |  | RPT | BES | NWW | 1 |  | DCP3
| MLCC-TRANSMIT-017967 | 2026-06-12 | DE.UGS.RE01.STR.S6 | Re: Package Submission - DCP3 - Station BR09 - Structure Top Slab Submission : DE.UGS.RE01.STR.S6.D3_Rev.C04 (IDV Certificate Submission) | C04 |  |  |  |  | 1 | Daniel Maddy | DCP3
| MLCC-TRANSMIT-017966 | 2026-06-12 | DE.UGS.GE09.MEP.M4 | Package Submission - DCP3 - Station BB05 MEP TVS : DE.UGS.GE09.MEP.M4.D3_Rev.C01 | C01 |  |  |  |  | 1 | Ismaiel Salama | DCP3
| MLCC-TRANSMIT-017965 | 2026-06-12 | MLCC-S0788-CIV-STN-FND-DRW-11078 | Shop Drawing Submission - STATION BR10 - Structure Foundation Level Pile Layout (L-Block Part-D) and Pile P13 - Shop Drawing & BBS: MLCC-S0788-CIV-STN-FND-DRW-11078 and MLCC-S0788-CIV-STN-FND-DRW-11079_Rev.C01 | C01 |  | DRW | CIV | STN | 2 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017964 | 2026-06-12 | MLCC-C0206-CIF-CDS-GEN-IRE-95006 | ICF Submission - DCP3 - Interface Control Form (ICF) for BR08 Base Slab Analysis STR/MEP/ARC/RSY - BR08 Station - Interface Level 2 & Level 3: MLCC-C0206-CIF-CDS-GEN-IRE-95006_Rev.C01 | C01 |  | OTH | CIF | CDS | 1 | Rohit Tharakan | DCP3
| MLCC-TRANSMIT-017963 | 2026-06-12 | MLCC-N0003-ENG-SSA-HUF-RPT-00002 | Re: Report Submission - BOCC Preliminary Ergonomics Study : MLCC-N0003-ENG-SSA-HUF-RPT-00002_Rev.C02 | C02 |  | RPT | ENG | SSA | 1 | Stephen Beadle
| MLCC-TRANSMIT-017962 | 2026-06-12 | MLCC-N0003-ENG-SSA-HUF-RPT-00002 | Re: Report Submission - BOCC Preliminary Ergonomics Study : MLCC-N0003-ENG-SSA-HUF-RPT-00002_Rev.C02 | C02 |  | RPT | ENG | SSA | 1 | Stephen Beadle
| MLCC-TRANSMIT-017961 | 2026-06-12 | MLCC-N0003-ENG-SSA-HUF-RPT-00001 | Re: Report Submission - OCC Preliminary Ergonomic Study : MLCC-N0003-ENG-SSA-HUF-RPT-00001_Rev.C02 | C02 |  | RPT | ENG | SSA | 1 | Stephen Beadle
| MLCC-TRANSMIT-017960 | 2026-06-12 | MLCC-N0003-ENG-SSA-HUF-RCD-00002 | Record Submission - DCP2 - Human Factors Assurance Form DCP2 : MLCC-N0003-ENG-SSA-HUF-RCD-00002_Rev.C01 | C01 |  | RCD | ENG | SSA | 1 | Stephen Beadle | DCP2
| MLCC-TRANSMIT-017959 | 2026-06-12 | MLCC-S0749-CIF-CDS-GEN-IRE-95001 | Re: ICF Submission - Interface Control Form for Viaduct Openings and Inserts for Stretch 8.1 / 8.2 : MLCC-S0749-CIF-CDS-GEN-IRE-95001_Rev.C01 | C01 |  | OTH | CIF | CDS | 1 | Rohit Tharakan
| MLCC-TRANSMIT-017958 | 2026-06-12 | MLCC-S0749-CIF-CDS-GEN-IRE-95001 | Re: ICF Submission - Interface Control Form for Viaduct Openings and Inserts for Stretch 8.1 / 8.2 : MLCC-S0749-CIF-CDS-GEN-IRE-95001_Rev.00 (RCS Resubmission) | 00 |  | OTH | CIF | CDS | 1 | Rohit Tharakan
| MLCC-TRANSMIT-017957 | 2026-06-12 | MLCC-N0003-PMC-SSA-HUF-REG-00001 | Re: Register Submission - Human Factors Issues Log : MLCC-N0003-PMC-SSA-HUF-REG-00001_Rev.C02 | C02 |  | REG | PMC | SSA | 1 | Stephen Beadle
| MLCC-TRANSMIT-017956 | 2026-06-11 | MLCC-Z0045-CIV-NWW-GAR-MST-00001 | Method Statement For Re-enforced Concrete Coring For MEP Services Requirements : MLCC-Z0045-CIV-NWW-GAR-MST-00001_Rev.00 | 00 |  | MST | CIV | NWW | 1 | Ismaiel Salama
| MLCC-TRANSMIT-017955 | 2026-06-11 | MLCC-S0727-CIV-VBR-PIR-DRW-13050 | Re: Shop Drawing Submission - Stretch-06.2 Viaduct Structure ISO & 2SP Pier Setting Out Shop Drawing PM162 to PM196 - MLCC-S0727-CIV-VBR-PIR-DRW-13050 & 13051 - Rev.C02 |  |  | DRW | CIV | VBR | 1 | Amit Kumar
| MLCC-TRANSMIT-017954 | 2026-06-11 | DE.VDT.ST06.STR.V1 | Re: Shop Drawing Submission - Stretch-06.2 - Viaduct Structure Foundation - Pilecap Shop Drawing BC-3SP-72-09_PM197 AND PM200 : DE.VDT.ST06.STR.V1.D5_Rev.C01 (RCS Resubmission) | C01 |  |  |  |  | 1 | Amit Kumar
| MLCC-TRANSMIT-017953 | 2026-06-11 | MLCC-S0663-CIV-VBR-PAP-DRW-84070 | Shop Drawing Submisison - Stretch-02.2 - Viaduct Structure Foundation Pile Cap - BC-3SP-72-03 - PM55: MLCC-S0663-CIV-VBR-PAP-DRW-84070, MLCC-S0663-CIV-VBR-PAP-DRW-84071, MLCC-S0663-CIV-VBR-PAP-DRW-84072 & MLCC-S0663-CIV-VBR-PAP-DRW-84073_Rev C01 | C01 |  | DRW | CIV | VBR | 4 | Ashok Kumar
| MLCC-TRANSMIT-017952 | 2026-06-11 | MLCC-S0663-CIV-VBR-PAP-DRW-84040 | Shop Drawing Submission - Stretch-02.2 - Viaduct Structure Foundation Pile Cap - BC-3SP-72-03 - PM51: MLCC-S0663-CIV-VBR-PAP-DRW-84040 to MLCC-S0663-CIV-VBR-PAP-DRW-84043_Rev C01 | C01 |  | DRW | CIV | VBR | 2 | Ashok Kumar
| MLCC-TRANSMIT-017951 | 2026-06-11 |  | Shop Drawing Submission - Station BB04 - Structure Concourse Wing Beam PT Detail, Reinforcement Elements and Base Plate Anchor Bolt Detail at Grid 5: Rev C01 | [5 empty] | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017950 | 2026-06-11 |  | Shop Drawing Submission - Station BB04 - Structure Concourse Wing Beam PT Detail, Reinforcement Elements and Base Plate Anchor Bolt Detail at Grid 6: Rev C01 | [5 empty] | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017949 | 2026-06-11 | MLCC-S0727-CIV-VBR-PIR-DRW-13020 | Re: Shop Drawing Submission - Stretch-6.2- Viaduct Structure - Pier Shop Drawing & BBS- PM171 to PM186 : MLCC-S0727-CIV-VBR-PIR-DRW-13020-13034_Rev.C02 | C02 |  | DRW | CIV | VBR | 1 | Ashok Kumar
| MLCC-TRANSMIT-017948 | 2026-06-11 | MLCC-S0716-CIV-EES-GAR-RPT-60001 | Re: Package Submission - DCP3 - Annex Structure - BL-EES07 Structure D-Wall (DE.ANX.AX16.STR.S1.D3) : MLCC-S0716-CIV-EES-GAR-RPT-60001-DCP3_Rev.C02 | C02 |  | RPT | CIV | EES | 1 |  | DCP3
| MLCC-TRANSMIT-017947 | 2026-06-11 | MLCC-Z0043-UTL-COM-GEN-DRW-50001 | Re: Shop Drawing Submission - Proposed Relocation of Ex. 1W Fiber Communication Cable Duct With Additional 100Ø Spare Duct (Stretch 07) : MLCC-Z0043-UTL-COM-GEN-DRW-50001-50003_Rev.C02 | C02 |  | DRW | UTL | COM | 1 | Ahmad Chikh bakri
| MLCC-TRANSMIT-017946 | 2026-06-11 | MLCC-N0003-CIV-VBR-GAR-MST-00036 | Re: Method Statement For Concrete Prop / Temporary Tower Installation and Dismantling : MLCC-N0003-CIV-VBR-GAR-MST-00036_Rev.01 | 01 |  | MST | CIV | VBR | 1 | Ashok Kumar
| MLCC-TRANSMIT-017945 | 2026-06-11 | MLCC-C0174-CIV-NWW-GAR-ITP-00005 | Re: ITP Submission - Inspection and Test Plan (ITP) For Precast cast Beams (On site casting ) and Erection : MLCC-C0174-CIV-NWW-GAR-ITP-00005_Rev.01 | 01 |  | ITP | CIV | NWW | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017944 | 2026-06-11 | MLCC-S0651-CIV-VBR-FND-FCR-00003 | FCR Submission - Field Change and Drawing Modification Request (FCR) for Viaduct Stretch 01 - Piles PM-04, PM-10-01, PM-12-02 and PM-15-03 : MLCC-S0651-CIV-VBR-FND-FCR-00003_Rev.C01 | C01 |  | FCR | CIV | VBR | 1 | Ashok Kumar
| MLCC-TRANSMIT-017943 | 2026-06-11 | MLCC-N0003-CIV-TNL-GAR-ITP-01007 | Re: ITP Submission - Inspection and Test Plan (ITP) For Tunnel Segments Repairs : MLCC-N0003-CIV-TNL-GAR-ITP-01007_Rev.01 | 01 |  | ITP | CIV | TNL | 1 | Mohamed Yahia
| MLCC-TRANSMIT-017942 | 2026-06-11 | MLCC-S0709-CIV-STN-FND-DRW-13093 | Shop Drawing Submission - Station BB06 Base Slab Pour 11 : MLCC-S0709-CIV-STN-FND-DRW-13093-13097_Rev.C01 | C01 |  | DRW | CIV | STN | 1 | Suresh Shetty
| MLCC-TRANSMIT-017941 | 2026-06-11 | MLCC-Z0681-UTL-ESP-GEN-DRW-01000 | Re: Shop Drawing Submission - Proposed Temporary Diversion Of 11kV, 6.6kV & LV Cables Near PM-101 at Ras Al Khor : MLCC-Z0681-UTL-ESP-GEN-DRW-01000_Rev.C02 | C02 |  | DRW | UTL | ESP | 1 | Ahmad Chikh bakri
| MLCC-TRANSMIT-017940 | 2026-06-11 | MLCC-S0690-UTL-ESP-GEN-DRW-00004 | Re: Shop Drawing Submission - Proposed Temporary Diversion of 01 No LV Cable Near PM-113 at Ras Al Khor : MLCC-S0690-UTL-ESP-GEN-DRW-00004_Rev.C03 | C03 |  | DRW | UTL | ESP | 1 | Ahmad Chikh bakri
| MLCC-TRANSMIT-017939 | 2026-06-11 | MLCC-N0003-CIV-VBR-PIR-DRW-84060 | Shop Drawing Submission - Global - Viaduct Structure Pierhead - PHR-4C : DE.VDT.GN00.STR.05.D5 (MLCC-N0003-CIV-VBR-PIR-DRW-84060 - MLCC-N0003-CIV-VBR-PIR-DRW-84093)_Rev.C01 | C01 |  | DRW | CIV | VBR | 2 | Mahmoud Saad
| MLCC-TRANSMIT-017938 | 2026-06-11 | DE.ANX.AX17.STR.S0 | Re: Package Submission - DCP2 - Annex Structure - BL-EES08 Structure : DE.ANX.AX17.STR.S0.D2_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad | DCP2
| MLCC-TRANSMIT-017937 | 2026-06-11 | MLCC-N0003-PMC-SEE-ENV-RPT-00013 | Environmental Performance Report - 2026 : MLCC-N0003-PMC-SEE-ENV-RPT-00013_Rev.00 | 00 |  | RPT | PMC | SEE | 1 | Loren Leiski
| MLCC-TRANSMIT-017936 | 2026-06-11 | MLCC-N0003-BES-ELE-LVD-ITP-00003 | ITP Submission - Inspection and Test Plan (ITP) for Installation of Wiring Devices & Isolators (Viaduct) : MLCC-N0003-BES-ELE-LVD-ITP-00003_Rev.00 | 00 |  | ITP | BES | ELE | 1 | Ismaiel Salama
| MLCC-TRANSMIT-017935 | 2026-06-11 | MLCC-S0731-CIV-STN-GAR-DRW-13075 | Shop Drawing Submission - Station BB04-Structure Concourse Level Wing Beam (Grid 11) : MLCC-S0731-CIV-STN-GAR-DRW-13075 -13076, MLCC-S0731-CIV-STN-RFC-DRW-13123 - 13129 , MLCC-S0731-CIV-STN-SSR-DRW-13110_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017934 | 2026-06-11 | DE.DPT.TBG1.STR.S0 | Package Submission - DCP3 - Depot BDR14 -Structure TPS : DE.DPT.TBG1.STR.S0.D3_Rev.C01 | C01 |  |  |  |  | 1 | Daniel Maddy | DCP3
| MLCC-TRANSMIT-017933 | 2026-06-11 | DE.ELS.GE00.GEO.G1 | Package Submission - DCP3 - Technical Note-Working Pile Load test at BG31 (SOP-23) : DE.ELS.GE00.GEO.G1.D3_Rev.C01 | C01 |  |  |  |  | 1 | Mazar Syed | DCP3
| MLCC-TRANSMIT-017932 | 2026-06-11 | MLCC-S0731-CIV-STN-GAR-DRW-13064 | Shop Drawing Submission - Station BB04 - Structure Concourse Level Wing Beam (Grid 4) : MLCC-S0731-CIV-STN-GAR-DRW-13064 , MLCC-S0731-CIV-STN-RFC-DRW-13179 - 13184, MLCC-S0731-CIV-STN-SSR-DRW-13104_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017931 | 2026-06-11 | MLCC-N0003-CIV-STN-GAR-RPT-26000 | Report Submission - Design Report for Spine Beams, Wing Beams Shoring and Shutter Arrangement at BG32 & BB04 Station : MLCC-N0003-CIV-STN-GAR-RPT-26000_Rev.C01 | C01 |  | RPT | CIV | STN | 1 | Daniel Maddy
| MLCC-TRANSMIT-017930 | 2026-06-11 | MLCC-S0731-CIV-STN-GAR-DRW-13063 | Shop Drawing Submission - Station BB04 - Structure Concourse Level Wing Beam (Grid 3) : MLCC-S0731-CIV-STN-GAR-DRW-13063,MLCC-S0731-CIV-STN-RFC-DRW-13174 - 13178, MLCC-S0731-CIV-STN-SSR-DRW-13103_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017929 | 2026-06-11 | MLCC-S0731-CIV-STN-GAR-DRW-13062 | Shop Drawing Submission - Station BB04-Structure Concourse Level Wing Beam (Grid 2) : MLCC-S0731-CIV-STN-GAR-DRW-13062 , MLCC-S0731-CIV-STN-RFC-DRW-13170 - 13173,MLCC-S0731-CIV-STN-SSR-DRW-13102_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017928 | 2026-06-11 | MLCC-S0731-CIV-STN-GAR-DRW-13061 | Shop Drawing Submission - Station BB04 Structure Concourse Level Wing Beam (Grid 1) : MLCC-S0731-CIV-STN-GAR-DRW-13061,MLCC-S0731-CIV-STN-RFC-DRW-13166 - 13169,MLCC-S0731-CIV-STN-SSR-DRW-13101_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017927 | 2026-06-11 | MLCC-S0651-CIV-VBR-FND-MST-00004 | Re: Method Statement For Installation of Precast Shell for Foundation Pile Cap – Dubai Creek Crossing : MLCC-S0651-CIV-VBR-FND-MST-00004_Rev.01 | 01 |  | MST | CIV | VBR | 1 | Ashok Kumar
| MLCC-TRANSMIT-017926 | 2026-06-11 | MLCC-S0731-CIV-STN-GAR-DRW-13099 | Shop Drawing Submission - Station BB04-Structure Concourse Level Wing Beam (Grid 27) : MLCC-S0731-CIV-STN-GAR-DRW-13099,MLCC-S0731-CIV-STN-RFC-DRW-13162 - 13165,MLCC-S0731-CIV-STN-SSR-DRW-13123_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017925 | 2026-06-11 | MLCC-N0003-BES-VAC-ACN-MTS-00001 | Re: Material Approval Request for Duct Insulation - Acoustic Insulation & Accessories "Afico/MNG": MLCC-N0003-BES-VAC-ACN-MTS-00001_Rev.03 | 03 |  | MAT | BES | VAC | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017924 | 2026-06-11 | MLCC-N0003-BES-WTS-SYW-MTS-00003 | Re: Material Approval Request for Pipe Insulation & Accessories "Armacell/Focus/MNG": MLCC-N0003-BES-WTS-SYW-MTS-00003_Rev.03 | 03 |  | MAT | BES | WTS | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017923 | 2026-06-11 | MLCC-N0003-PMC-PRC-RER-RPT-00494 | Daily Progress Report of 09-June-2026 : MLCC-N0003-PMC-PRC-RER-RPT-00494_Rev.00 | 00 |  | RPT | PMC | PRC | 1 | Ahmed Ibrahim
| MLCC-TRANSMIT-017922 | 2026-06-11 | DE.ELS.GE11.MEP.M2 | Package Submission - DCP3 - Elevated Station BB03 MEP-DAW-WTS : DE.ELS.GE11.MEP.M2.D3_Rev.C01 | C01 |  |  |  |  | 1 | Ismaiel Salama | DCP3
| MLCC-TRANSMIT-017921 | 2026-06-11 | DE.ELS.GE11.MEP.M1 | Package Submission - DCP3 - Elevated Station BB03 MEP-Electrical : DE.ELS.GE11.MEP.M1.D3_Rev.C01 | C01 |  |  |  |  | 1 | Ismaiel Salama | DCP3
| MLCC-TRANSMIT-017920 | 2026-06-11 | DE.ELS.GE11.MEP.M3 | Package Submission - DCP3 - Elevated Station BB03 MEP-FPS : DE.ELS.GE11.MEP.M3.D3_Rev.C01 | C01 |  |  |  |  | 1 | Ismaiel Salama | DCP3
| MLCC-TRANSMIT-017919 | 2026-06-11 | DE.TNL.GN00.TWK.P1 | Re: Package Submission - DCP2 -Al Ruwayyah Depot Contact Rail System Design : DE.TNL.GN00.TWK.P1.D2_Rev.C01 | C01 |  |  |  |  | 1 | John Prabhu | DCP2
| MLCC-TRANSMIT-017918 | 2026-06-11 | MLCC-S0770-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP1 - BDR08 and BDR12 Depot - DTS Requirements (AR) Security Drawings (DE.DPT.OCCA.ARC.A0.D1) : MLCC-S0770-ARC-NWW-GAR-DRW-23000-23007_Rev.C02 | C02 |  | DRW | ARC | NWW | 1 |  | DCP1
| MLCC-TRANSMIT-017917 | 2026-06-11 | MLCC-S0719-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - Word City 2 Subway Station BB05 - DTS Requirements (AR) Security Drawings (DE.UGS.GE09.ARC.A0.D2) : MLCC-S0719-ARC-NWW-GAR-DRW-23000-23006_Rev.C02 | C02 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017916 | 2026-06-11 | MLCC-S0709-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - Underground Transfer Station BB06 - Global City 1 - DTS Requirements (AR) Security Drawings (DE.UGS.GE08.ARC.A2.D2) : MLCC-S0709-ARC-NWW-GAR-DRW-23000-23004_Rev.C03 | C03 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017915 | 2026-06-11 | DE.TNL.GN00.TWK.P1 | Re: Package Submission - DCP2 - Contact Rail System Layout Cross Section (Main Line) And Report: DE.TNL.GN00.TWK.P1.D2_Rev.C01 | C01 |  |  |  |  | 1 | John Prabhu | DCP2
| MLCC-TRANSMIT-017914 | 2026-06-11 | MLCC-S0675-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - Iconic Station BG34 - DTS Requirements (AR) Security Drawings (DE.ELS.GE03.ARC.A2.D2) : MLCC-S0675-ARC-NWW-GAR-DRW-23000-23006_Rev.C03 | C03 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017913 | 2026-06-11 | MLCC-S0788-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - Transit Station BR10 - Centerpoint / Al Rashidiya - DTS Requirements (AR) Security Drawings (DE.ELS.RE00.ARC.A2.D2) : MLCC-S0788-ARC-NWW-GAR-DRW-23000-23003_Rev.C02 | C02 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017912 | 2026-06-11 | MLCC-S0647-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - Al Khor Transit Station BG31 - DTS Requirements (AR) Security Drawings (DE.ELS.GE00.ARC.A2.D2) : MLCC-S0647-ARC-NWW-GAR-DRW-23000-23006_Rev.C02 | C02 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017911 | 2026-06-11 | MLCC-S0742-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - Station BB03 - DTS Requirements (AR) Security Drawings (DE.ELS.GE11.ARC.A2.D2) : MLCC-S0742-ARC-NWW-GAR-DRW-23000-23005_Rev.C02 | C02 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017910 | 2026-06-11 | MLCC-N0003-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - General Requirements and office Allocation Schedules for the Blue Line Metro Transit Security Management (AR) (DE.GEN.GN00.ARC.03.GN) : MLCC-N0003-ARC-NWW-GAR-DRW-23000_Rev.C02 | C02 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017909 | 2026-06-11 | MLCC-S0709-CIV-STN-RFC-DRW-13201 | Shop Drawing Submission - Station BB06 - Structure Main Column In Grid (C-C To 8) Base Slab To Concourse Level Reinforcement : MLCC-S0709-CIV-STN-RFC-DRW-13201 - 13204_Rev.C01 | C01 |  | DRW | CIV | STN | 1 | Suresh Shetty
| MLCC-TRANSMIT-017908 | 2026-06-11 | DE.VDT.ST02.STR.V3 | Re: Package Submission - DCP3 - Stretch-02.1 & 02.2 - Viaduct Structure Superstructure ISO Spans : DE.VDT.ST02.STR.V3.D3_Rev.C03 | C03 |  |  |  |  | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017907 | 2026-06-11 | MLCC-C0204-CIF-CDS-GEN-IRE-95004 | Re: ICF Submission - Interface Control Form (ICF) for Concourse Slab Cutout Analysis ARTC/STR/MEP/RSY - BR09 Station : MLCC-C0204-CIF-CDS-GEN-IRE-95004_Rev.C01 | C01 |  | OTH | CIF | CDS | 1 | Rohit Tharakan
| MLCC-TRANSMIT-017906 | 2026-06-11 | MLCC-C0204-CIF-CDS-GEN-IRE-95003 | ICF Submission - Interface Control Form (ICF) for Top Slab STR/RSY – BR09 station : MLCC-C0204-CIF-CDS-GEN-IRE-95003_Rev.C01 | C01 |  | OTH | CIF | CDS | 1
| MLCC-TRANSMIT-017905 | 2026-06-11 | MLCC-S0692-CIV-STN-GAR-DRW-13017 | Shop Drawing Submission - Station BG36 - Structure Concourse Level Wing Beam (Ptb12) Along Grid 13 : MLCC-S0692-CIV-STN-GAR-DRW-13017 - 13018,MLCC-S0692-CIV-STN-RFC-DRW-13110 - 13116,MLCC-S0692-CIV-STN-SSR-DRW-13010_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017904 | 2026-06-11 | DE.UGS.RE03.STR.S3 | Re: Package Submission - DCP3 - Station BR07 - Structure - Concourse Slab Submission -: DE.UGS.RE03.STR.S3.D3_Rev.C04 (Partial Submission) (IDV Certificate Submission) | C04 |  |  |  |  | 1 | Daniel Maddy | DCP3
| MLCC-TRANSMIT-017903 | 2026-06-11 | DE.ELS.GE00.STR.S1 | Re: Package Submission - DCP3 - Station BG31 – Structural – Link Bridge-Pile Caps : DE.ELS.GE00.STR.S1.D3_Rev.C02 | C02 |  |  |  |  | 1 | Daniel Maddy | DCP3
| MLCC-TRANSMIT-017902 | 2026-06-11 |  | Package Submission - DCP1 - Landscape Alignment BG32 to BG34: DE.ZNE.ZN2B.LDS.L1.D1_Rev.C01 | C01 |  |  |  |  | 1 | Mike Lewey | DCP1
| MLCC-TRANSMIT-017901 | 2026-06-11 | MLCC-S0742-CIV-STN-RFC-DRW-13311 | Shop Drawing Submission - Station BB03 - Concourse level secondary beam GL 06-22 : MLCC-S0742-CIV-STN-RFC-DRW-13311 - 13322 , MLCC-S0742-CIV-STN-SSR-DRW-13025 -13027_Rev.C01 | C01 |  | DRW | CIV | STN | 2 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017900 | 2026-06-11 | MLCC-S0731-CIV-STN-GAR-DRW-13095 | Shop Drawing Submission - Station BB04-Structure Concourse Level Wing Beam (Grid 23) : MLCC-S0731-CIV-STN-GAR-DRW-13095,MLCC-S0731-CIV-STN-RFC-DRW-13140 - 13146 , MLCC-S0731-CIV-STN-SSR-DRW-13119_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017899 | 2026-06-11 | MLCC-S0731-CIV-STN-GAR-DRW-13096 | Shop Drawing Submission - Station BB04-Structure Concourse Level Wing Beam (Grid 24) : MLCC-S0731-CIV-STN-GAR-DRW-13096,MLCC-S0731-CIV-STN-RFC-DRW-13147 - 13152,MLCC-S0731-CIV-STN-SSR-DRW-13120_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017898 | 2026-06-11 | MLCC-S0731-CIV-STN-GAR-DRW-13097 | Shop Drawing Submission - Station BB04-Structure Concourse Level Wing Beam (Grid 25) :MLCC-S0731-CIV-STN-GAR-DRW-13097, MLCC-S0731-CIV-STN-RFC-DRW-13153 - 13157,MLCC-S0731-CIV-STN-SSR-DRW-13121_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017897 | 2026-06-11 | MLCC-S0731-CIV-STN-GAR-DRW-13098 | Shop Drawing Submission - Station BB04-Structure Concourse Level Wing Beam (Grid 26) : MLCC-S0731-CIV-STN-GAR-DRW-13098, MLCC-S0731-CIV-STN-RFC-DRW-13158 -MLCC-S0731-CIV-STN-RFC-DRW-13161,MLCC-S0731-CIV-STN-SSR-DRW-13122_Rev.C01 | C01 |  | DRW | CIV | STN | 4 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017896 | 2026-06-11 | MLCC-S0673-CIV-VBR-PIR-DRW-84277 | Shop Drawing Submission - Stretch 03 Viaduct Structure - Pier Head - PM75, Inserts, Coordinates & Bearing BBS (DE.VDT.ST08.STR.V2.D5) : MLCC-S0673-CIV-VBR-PIR-DRW-84277 - MLCC-S0673-CIV-VBR-PIR-DRW-84280_Rev.C01 | C01 |  | DRW | CIV | VBR | 2 | Ashok Kumar
| MLCC-TRANSMIT-017895 | 2026-06-10 |  | Package Submission - DCP3 - Power Supply (PDS) - Key Interlocking Schematic - BG31 Station : RLS.1.1.9.8.1.1.5.7_Rev.C01 | C01 |  |  |  |  | 1 | Sherif Zayed | DCP3
| MLCC-TRANSMIT-017894 | 2026-06-10 |  | Package Submission - DCP3 - Power Supply (PDS) - Key Interlocking Schematic - BG32 (ITPS) Station : RLS.1.1.9.8.1.2.5.7_Rev.C01 | C01 |  |  |  |  | 1 | Sherif Zayed | DCP3
| MLCC-TRANSMIT-017893 | 2026-06-10 |  | Package Submission - DCP3 - Power Supply (PDS) - Key Interlocking Schematic - BG35(ITPS) Station : RLS.1.1.9.8.17.13.3_Rev.C01 | C01 |  |  |  |  | 1 | Sherif Zayed | DCP3
| MLCC-TRANSMIT-017892 | 2026-06-10 |  | Package Submission - DCP3 - Power Supply (PDS) - Key Interlocking Schematic - BG33 (ITPS) Station : RLS.1.1.9.8.17.13.3_Rev.C01 | C01 |  |  |  |  | 1 | Sherif Zayed | DCP3
| MLCC-TRANSMIT-017891 | 2026-06-10 | MLCC-S0731-CIV-STN-SSR-DRW-13111 | Shop Drawing Submission - Station BB04 - Concourse Level Wing Beam (Grid 13) : MLCC-S0731-CIV-STN-SSR-DRW-13111, MLCC-S0731-CIV-STN-GAR-DRW-13078-13079, MLCC-S0731-CIV-STN-RFC-DRW-13130-13136_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017890 | 2026-06-10 | MLCC-S0731-CIV-STN-GAR-DRW-13080 | Shop Drawing Submission - Station BB04 - Concourse Level Wing Beam (Grid 14) : MLCC-S0731-CIV-STN-GAR-DRW-13080, MLCC-S0731-CIV-STN-RFC-DRW-13137-13139_Rev.C01 | C01 |  | DRW | CIV | STN | 2 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017889 | 2026-06-10 | MLCC-S0654-CIV-STN-GAR-DRW-13202 to 13203 | Re: Shop Drawing Submission - Station BG32-Structure Concourse Level Wing Beam (Grid 11) : MLCC-S0654-CIV-STN-GAR-DRW-13202 to 13203, MLCC-S0654-CIV-STN-RFC-DRW-13143 to 13149 & MLCC-S0654-CIV-STN-SSR-DRW-13010_Rev.C01 (RCS Resubmission) | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017888 | 2026-06-10 | MLCC-S0654-CIV-STN-GAR-DRW-13205 | Re: Shop Drawing Submission - Station BG32 - Concourse Level Wing Beam Reinf. At Grid 13 : MLCC-S0654-CIV-STN-GAR-DRW-13205-13206,MLCC-S0654-CIV-STN-RFC-DRW-13150-13156_Rev.C01 (RCS Resubmission) | C01 |  | DRW | CIV | STN | 2 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017887 | 2026-06-10 | MLCC-S0654-CIV-STN-GAR-DRW-13211 to 13212 | Re: Shop Drawing Submission - Station BG32-Structure Concourse Level Wing Beam (Grid 17) : MLCC-S0654-CIV-STN-GAR-DRW-13211 to 13212, MLCC-S0654-CIV-STN-RFC-DRW-13133 to 13139 & MLCC-S0654-CIV-STN-SSR-DRW-13013_Rev.C01 (RCS Resubmission) | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017886 | 2026-06-10 | MLCC-S0654-CIV-STN-GAR-DRW-13214 | Re: Shop Drawing Submission - Station BG32-Structure Concourse Level Wing Beam (Grid 19) Shop Drawings : MLCC-S0654-CIV-STN-GAR-DRW-13214-13215 & MLCC-S0654-CIV-STN-RFC-DRW-13113-13119_Rev.C01 (RCS Resubmission) | C01 |  | DRW | CIV | STN | 2 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017885 | 2026-06-10 | MLCC-S0654-CIV-STN-GAR-DRW-13210 | Re: Shop Drawing submission - Station BG32-Structure Concourse Level Wing Beam (Grid 16) : MLCC-S0654-CIV-STN-GAR-DRW-13210, MLCC-S0654-CIV-STN-RFC-DRW-13130-13132_Rev.C01 (RCS Resubmission) | C01 |  | DRW | CIV | STN | 2 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017884 | 2026-06-10 | MLCC-S0820-CIV-STN-RFC-DRW-25500 | Shop Drawing Submission - BR07 station Base slab water proofing : MLCC-S0820-CIV-STN-RFC-DRW-25500-25507_Rev.C01 | C01 |  | DRW | CIV | STN | 1 | Suresh Shetty
| MLCC-TRANSMIT-017883 | 2026-06-10 | MLCC-N0003-BES-FPS-FFS-MST-00004 | Method Statement for Installation of Tunnel and Cut & Cover Water Based Fire Fighting System : MLCC-N0003-BES-FPS-FFS-MST-00004_Rev.00 | 00 |  | MST | BES | FPS | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017882 | 2026-06-10 | DE.VDT.GN00.STR.03.D5 | Shop Drawing Submission - Global - Viaduct Structure Balanced Cantilever (BC-3SP-72) Reinf. Shop Dwg : (DE.VDT.GN00.STR.03.D5) :MLCC-N0003-CIV-VBR-3SP-DRW-84201 - 84211_Rev.C01 | C01 |  |  |  |  | 1 | Ashok Kumar
| MLCC-TRANSMIT-017881 | 2026-06-10 | MLCC-S0794-QHS-INI-GEN-RPT-00001 | Environmental Incident reporting Form - Incident that occurred on BR10 - Cut & Cover dated 03-June-2026 : MLCC-S0794-QHS-INI-GEN-RPT-00001_Rev.00 | 00 |  | RPT | QHS | INI | 1 | Loren Leiski
| MLCC-TRANSMIT-017880 | 2026-06-10 | MLCC-N0003-CIF-SIF-GEN-ICD-51168 | ICD Submission - DCP2 -Interface Control Document - BG35 Ras Al Khor Provisional Station – Civil Works / Stakeholders : MLCC-N0003-CIF-SIF-GEN-ICD-51168_Rev.C01 | C01 |  | ICD | CIF | SIF | 1 | Rohit Tharakan | DCP2
| MLCC-TRANSMIT-017879 | 2026-06-10 | MLCC-N0003-CIV-TNL-GAR-RPT-00023 | Cutterhead Intervention Report 6 for TBM 1 : MLCC-N0003-CIV-TNL-GAR-RPT-00023_Rev.00 | 00 |  | RPT | CIV | TNL | 1 | Evripidis Zampiras
| MLCC-TRANSMIT-017878 | 2026-06-10 | DE.UGS.RE03.STR.S4 | Package Submission - DCP3 - Station BR07 - Structure - Platform Slab : DE.UGS.RE03.STR.S4.D3_Rev.C01 | C01 |  |  |  |  | 1 | Daniel Maddy | DCP3
| MLCC-TRANSMIT-017877 | 2026-06-10 | MLCC-N0003-CIV-STN-GAR-MST-00008 | Re: Method Statement For Installation of Duct, Strands & Anchorages & Stressing Works for BB03, BB04, BG32 and BG36 : MLCC-N0003-CIV-STN-GAR-MST-00008_Rev.02 | 02 |  | MST | CIV | STN | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017876 | 2026-06-10 | MLCC-C0003-BES-NWW-CDS-PRC-00001 | Re: Procedure Submission - SOP – Standard Operating Procedure for Passage Operation Including FAS, CCTV & Operations (BR10 – Temporary Passenger Passage) : MLCC-C0003-BES-NWW-CDS-PRC-00001_Rev.C01 | C01 |  | PRC | BES | NWW | 1 | Mohsin Patel
| MLCC-TRANSMIT-017875 | 2026-06-10 | MLCC-N0003-CIV-TNL-SYW-MTS-00045 | Re: Material Approval Request Technical Submittal for C25/30 – Infil Concrete under Tunnel Invert (Mix Code : M3013)- 50% OPC + 50% GGBS "Emirates Beton": MLCC-N0003-CIV-TNL-SYW-MTS-00045_Rev.00 (RCS Resubmission) | 00 |  | MAT | CIV | TNL | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017874 | 2026-06-10 | MLCC-N0003-BES-ECS-GAL-MTS-00001 | Material Approval Request for Sand Trap & Weather Louvers "Betec Cad/MNG": MLCC-N0003-BES-ECS-GAL-MTS-00001_Rev.00 | 00 |  | MAT | BES | ECS | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017873 | 2026-06-10 | MLCC-N0003-BES-FPS-FFS-MTS-00013 | Material Approval Request for Threaded & Grooved Fittings for Fire Fighting Systems "HEBEI JIANZHI & SDSX / MNG": MLCC-N0003-BES-FPS-FFS-MTS-00013_Rev.00 | 00 |  | MAT | BES | FPS | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017872 | 2026-06-10 | MLCC-N0003-BES-WTS-WRD-MTS-00007 | Material Approval Request for PPR (Composite) Pipes and Fittings "AQUATHERM/MNG": MLCC-N0003-BES-WTS-WRD-MTS-00007_Rev.00 | 00 |  | MAT | BES | WTS | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017871 | 2026-06-10 | MLCC-C0003-PDS-MPD-MVN-MTS-10008 | Material Approval Request for Pilot Control Cable for 33 kV Protection & Control System "Jiangsu Yuanyang Cable/GIGA Power And Piping Solutions" (Temporary - Enhancement Works): MLCC-C0003-PDS-MPD-MVN-MTS-10008_Rev.00 | 00 |  | MAT | PDS | MPD | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017870 | 2026-06-10 | MLCC-S0709-CIV-STN-RFC-DRW-13001 to 13004 | Re: Shop Drawing Submission - Station BB06 - Structure External Wall (EW1) Reinforcement along Grid H Shop Drawing & BBS : MLCC-S0709-CIV-STN-RFC-DRW-13001 to 13004_Rev.C03 | C03 |  | DRW | CIV | STN | 1 | Suresh Shetty
| MLCC-TRANSMIT-017869 | 2026-06-10 | MLCC-C0003-CIV-PTW-GAR-RPT-00001 | Re: Report Submission - Safety Report for Temporary Pedestrian Passageway at Centrepoint Station (Enhancement Works) : MLCC-C0003-CIV-PTW-GAR-RPT-00001_Rev.C06 | C06 |  | RPT | CIV | PTW | 1 | Stephen Beadle
| MLCC-TRANSMIT-017868 | 2026-06-10 | MLCC-N0003-PMC-PRC-RER-RPT-00493 | Daily Progress Report of 08-June-2026 : MLCC-N0003-PMC-PRC-RER-RPT-00493_Rev.00 | 00 |  | RPT | PMC | PRC | 1 | Ahmed Ibrahim
| MLCC-TRANSMIT-017867 | 2026-06-10 | MLCC-C0003-BES-NWW-CDS-MAN-00001 | Operation and Maintenance Manual for (Rashidiya Stations – Temporary Pedestrian Passage) Mechanical and Electrical Systems : MLCC-C0003-BES-NWW-CDS-MAN-00001_Rev.00 | 00 |  | MAN | BES | NWW | 1 | Mohsin Patel |  |  | PAJV-TRANSMIT-013802 | 2026-06-11
| MLCC-TRANSMIT-017866 | 2026-06-10 | MLCC-C0003-CIV-PTW-GAR-RPT-00003 | Report Submission - Test Case Reports for the Temporary Passageway at Centerpoint Station : MLCC-C0003-CIV-PTW-GAR-RPT-00003_Rev.C01 | C01 |  | RPT | CIV | PTW | 1 | Mohsin Patel
| MLCC-TRANSMIT-017865 | 2026-06-10 | MLCC-C0181-CIV-STN-GAR-RPT-60005 | Re: Package Submission - DCP3 - Station BG34 - Structure Structural Design Report (Concourse Level) DE.ELS.GE03.STR.S3.D3 : MLCC-C0181-CIV-STN-GAR-RPT-60005-DCP3_Rev.C02 | C02 |  | RPT | CIV | STN | 1 | Daniel Maddy | DCP3
| MLCC-TRANSMIT-017864 | 2026-06-10 | MLCC-N0003-BES-TRV-SYW-MTS-00002 | Material Sample Approval for Moving Walks & Accessories "TK Elevator/MNG": MLCC-N0003-BES-TRV-SYW-MTS-00002_Rev.00 | 00 |  | MAT | BES | TRV | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017863 | 2026-06-10 | MLCC-N0003-BES-ESC-SYW-MTS-00002 | Material Sample Approval for Escalators & Accessories "TK Elevator/MNG": MLCC-N0003-BES-ESC-SYW-MTS-00002_Rev.00 | 00 |  | MAT | BES | ESC | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017862 | 2026-06-10 | MLCC-N0003-ARC-NWW-GAR-MTS-00044 | Re: Material Approval Request for Raised Access Floor "MBM": MLCC-N0003-ARC-NWW-GAR-MTS-00044_Rev.01 | 01 |  | MAT | ARC | NWW | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017861 | 2026-06-10 | MLCC-C0181-CIV-STN-GAR-RPT-60005 | Package Submission - DCP3 - Station BG34 - Structure Structural Design Report (Concourse Level) DE.ELS.GE03.STR.S3.D3 : MLCC-C0181-CIV-STN-GAR-RPT-60005-DCP3_Rev.C02 | C02 |  | RPT | CIV | STN | 1 | Daniel Maddy | DCP3
| MLCC-TRANSMIT-017860 | 2026-06-10 | MLCC-S0810-CIV-STN-GAR-DRW-13008 | Shop Drawing Submission - BR08 Station Base slab water proofing : MLCC-S0810-CIV-STN-GAR-DRW-13008-13016_Rev.C01 | C01 |  | DRW | CIV | STN | 1 | Vinod Kalwaghe
| MLCC-TRANSMIT-017859 | 2026-06-10 | MLCC-N0003-PMC-SOH-GEN-PLN-00007 | Re: Plan Submission - Tunnel HSE & Emergency Plan : MLCC-N0003-PMC-SOH-GEN-PLN-00007_Rev.C04 | C04 |  | PLN | PMC | SOH | 1 | Loren Leiski
| MLCC-TRANSMIT-017858 | 2026-06-10 | DE.ELS.GE06.STR.S9 | Package Submission - DCP3 - Elevated Station BG36 - Structure- Chiller Yard: DE.ELS.GE06.STR.S9.D3_Rev.C01 | C01 |  |  |  |  | 1 | Daniel Maddy | DCP3
| MLCC-TRANSMIT-017857 | 2026-06-10 | MLCC-S0709-CIV-STN-RFC-DRW-13238 | Shop Drawing Submission - Station BB06 - Structure Platform Pour PS-1 Slab : MLCC-S0709-CIV-STN-RFC-DRW-13238-13242_Rev.C01 | C01 |  | DRW | CIV | STN | 1 | Suresh Shetty
| MLCC-TRANSMIT-017856 | 2026-06-10 | MLCC-N0003-OCC-SYW-GEN-PLN-51111 | Plan Submission - DCP2 - OCC Software Configuration Management Plan (RLS.1.1.10.5.2.5) : MLCC-N0003-OCC-SYW-GEN-PLN-51111_Rev.C03 | C03 |  | PLN | OCC | SYW | 1 | Siddarth Jayaraman | DCP2
| MLCC-TRANSMIT-017855 | 2026-06-10 | MLCC-N0003-PSD-NWW-SSA-RPT-51607 | Report Submission : DCP2 - Platform Screen Doors (PSD) - RAMS - Preliminary Design Safety Case : MLCC-N0003-PSD-NWW-SSA-RPT-51607_Rev.C02 | C02 |  | RPT | PSD | NWW | 1 | Stephen Beadle | DCP2
| MLCC-TRANSMIT-017854 | 2026-06-10 | MLCC-S0654-CIV-STN-RFC-DRW-13057 | Re: Shop Drawing Submission - Station BG32 - Concourse Level RC Elements Spine Beam Grid-01 to 06 : MLCC-S0654-CIV-STN-RFC-DRW-13057-13065_Rev.C02 | C02 |  | DRW | CIV | STN | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017853 | 2026-06-10 | DE.ANX.AX08.ARC.A0 | Package Submission - DCP1 - Annex BL-EES16 - Architectural: DE.ANX.AX08.ARC.A0.D1_Rev.C01 | C01 |  |  |  |  | 1 |  | DCP1
| MLCC-TRANSMIT-017852 | 2026-06-10 |  | Package Submission - DCP3 - Foundation & Substructure - Viaduct Structure Stretch 06.2 - BC-3SP-72-09 : DE.VDT.B009.STR.V1.D3_Rev.C04 (Partial Submission) | C04 |  |  |  |  | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017851 | 2026-06-10 | MLCC-N0003-BES-VAC-CHW-MST-00004 | Method Statement for Installation of Air-Cooled Chillers with Adiabatic Cooling Unit Complete with Ancillaries : MLCC-N0003-BES-VAC-CHW-MST-00004_Rev.00 | 00 |  | MST | BES | VAC | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017850 | 2026-06-10 | MLCC-S0719-CIV-STN-RFC-DRW-13223 | Shop Drawing Submission - BB05 Station - Concourse Slab - Pour-6 Reinforcement : MLCC-S0719-CIV-STN-RFC-DRW-13223-13240_Rev.C01 | C01 |  | DRW | CIV | STN | 1 | Suresh Shetty
| MLCC-TRANSMIT-017849 | 2026-06-10 | MLCC-N0003-CIF-SIF-GEN-ICD-51301 | Re: ICD Submission - DCP2 - Interface Control Document Signalling - Rolling Stock (RLS.1.1.13.2.2) : MLCC-N0003-CIF-SIF-GEN-ICD-51301_Rev.C02 | C02 |  | ICD | CIF | SIF | 1 | Rohit Tharakan | DCP2
| MLCC-TRANSMIT-017848 | 2026-06-10 | MLCC-N0003-CIF-SIF-GEN-ICD-51302 | Re: ICD Submission - DCP2 - Interface Control Document ATC-DEP-002 ATC Signalling SIG – DEP Depot Equipment : MLCC-N0003-CIF-SIF-GEN-ICD-51302_Rev.C02 | C02 |  | ICD | CIF | SIF | 1 |  | DCP2 |  | PAJV-TRANSMIT-013794 | 2026-06-11
| MLCC-TRANSMIT-017847 | 2026-06-10 | MLCC-C0003-BES-VAC-SYW-MST-00003 | Re: Method Statement For T&C of HVAC Services at Rashidiya Temporary Pedestrian Passage : MLCC-C0003-BES-VAC-SYW-MST-00003_Rev.02 | 02 |  | MST | BES | VAC | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017846 | 2026-06-10 | MLCC-S0749-CIV-VBR-PIR-DRW-84141 | Shop Drawing Submission - Stretch-08.1 - Viaduct Structure Pierhead - PM246 (DE.VDT.ST08.STR.V2.D5) : MLCC-S0749-CIV-VBR-PIR-DRW-84141 - 84144_Rev.C01 | C01 |  | DRW | CIV | VBR | 1 | Mahmoud Saad
| MLCC-TRANSMIT-017845 | 2026-06-10 | MLCC-C0003-BES-NWW-CDS-PRC-00001 | Re: Procedure Submission - SOP – Standard Operating Procedure for Passage Operation Including FAS, CCTV & Operations (BR10 – Temporary Passenger Passage) : MLCC-C0003-BES-NWW-CDS-PRC-00001_Rev.C01 | C01 |  | PRC | BES | NWW | 1 | Mohsin Patel
| MLCC-TRANSMIT-017844 | 2026-06-10 | DE.ANX.AX10.STR.S0 | Package Submission - DCP2 - Annex Structure - BL-EES01 Structure - S0703 : DE.ANX.AX10.STR.S0.D2_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad | DCP2
| MLCC-TRANSMIT-017843 | 2026-06-10 | MLCC-N0003-ENG-SEE-AMN-PLN-00001 | Re: Plan Submission - Acoustic and Vibration Management Plan (Project Wide) : MLCC-N0003-ENG-SEE-AMN-PLN-00001_Rev.C03 | C03 |  | PLN | ENG | SEE | 1 | Oladele Kupolati | [13 empty] | [Already in master log]
| MLCC-TRANSMIT-017842 | 2026-06-10 | MLCC-S0692-CIV-STN-GAR-DRW-13034 | Shop Drawing Submission - Station BG36 Structure Concourse Level Wing Beams shop drawing along Grid-23 : MLCC-S0692-CIV-STN-GAR-DRW-13034,MLCC-S0692-CIV-STN-RFC-DRW-13120 - 13126,MLCC-S0692-CIV-STN-SSR-DRW-13018_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017841 | 2026-06-10 | MLCC-S0738-CIV-VBR-FND-FCR-00001 | Re: FCR Submission - Filed Change and Modification Request (FCR) for Viaduct PM213 Pile 213-01 : MLCC-S0738-CIV-VBR-FND-FCR-00001_Rev.C01 (RCS Resubmission) | C01 |  | FCR | CIV | VBR | 1 | Mahmoud Saad
| MLCC-TRANSMIT-017840 | 2026-06-09 | MLCC-C0201-CIF-CDS-GEN-IRE-95001 | Re: ICF Submission - DCP1 - Interface Control Form (ICF) for RSY Room Space Proofing Analysis - BR10 Station - Level 2: MLCC-C0201-CIF-CDS-GEN-IRE-95001_Rev.C01 (RCS Resubmission) | C01 |  | OTH | CIF | CDS | 1 | Rohit Tharakan | DCP1
| MLCC-TRANSMIT-017839 | 2026-06-09 | MLCC-N0003-CIF-SIF-GEN-ICD-51316 | Re: ICD Submission - Interface Control Document COM-DEP-016 Depot Equipment /Communications (RLS.1.1.6.6.2.5) : MLCC-N0003-CIF-SIF-GEN-ICD-51316_Rev.C02 | C02 |  | ICD | CIF | SIF | 1 | Rohit Tharakan
| MLCC-TRANSMIT-017838 | 2026-06-09 | MLCC-N0003-CIF-SIF-GEN-ICD-51322 | Re: ICD Submission - DCP2 - Interface Control Document - Power Distribution Systems / Communication (RLS.1.1.2.2.8) : MLCC-N0003-CIF-SIF-GEN-ICD-51322_Rev.C02 | C02 |  | ICD | CIF | SIF | 1 | Rohit Tharakan | DCP2
| MLCC-TRANSMIT-017837 | 2026-06-09 | MLCC-N0003-CIF-SIF-GEN-ICD-51303 | Re: ICD Submission - Interface Control Document – ATC-OCC-003 Signalling System / OCC Systems (RLS.1.1.13.2.2) : MLCC-N0003-CIF-SIF-GEN-ICD-51303_rev.C02 | C02 |  | ICD | CIF | SIF | 1 | Rohit Tharakan
| MLCC-TRANSMIT-017836 | 2026-06-09 | MLCC-N0003-CIF-SIF-GEN-ICD-51349 | Re: ICD Submission - Interface Control Document Signalling (ATC)-Yellow Plant Equipment (YPE)-049 (RLS.1.1.13.2.2) : MLCC-N0003-CIF-SIF-GEN-ICD-51349_Rev.C02 | C02 |  | ICD | CIF | SIF | 1 | Rohit Tharakan |  |  | PAJV-TRANSMIT-013795 | 2026-06-11
| MLCC-TRANSMIT-017835 | 2026-06-09 | MLCC-S0692-CIV-STN-GAR-DRW-13043 | Shop Drawing Submission - BG36 - Cross head at Grid-16 : MLCC-S0692-CIV-STN-GAR-DRW-13043, MLCC-S0692-CIV-STN-PIR-DRW-13025 - 13026_Rev.C01 | C01 |  | DRW | CIV | STN | 2 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017834 | 2026-06-09 | DE.ELS.GE03.STR.S1 | Re: Package Submission - DCP3 - Station BG34 - Structure – (Concourse above pier and Transverse Beam) : DE.ELS.GE03.STR.S1.D3_Rev.C03 (RCS Resubmission) | C03 |  |  |  |  | 1 | Daniel Maddy | DCP3 |  | PAJV-TRANSMIT-013810 | 2026-06-12
| MLCC-TRANSMIT-017833 | 2026-06-09 | MLCC-S0762-UTL-DRN-GEN-QUA-00001 | PQ Submission - Prequalification Submittal For Al Noor Fibreglass Co. LLC : MLCC-S0762-UTL-DRN-GEN-QUA-00001_Rev.00 | 00 |  | QUA | UTL | DRN | 1 | Lynneth Santos
| MLCC-TRANSMIT-017832 | 2026-06-09 | MLCC-N0003-BES-NWW-ANO-RPT-70000 | Re: Report Submission - Technical Note - MEP - LV Cable Colour Coding Project Wide (DE.GEN.GN00.MEP.M0.GN): MLCC-N0003-BES-NWW-ANO-RPT-70000_Rev C02 | C02 |  | RPT | BES | NWW | 1 | Ismaiel Salama |  |  | PAJV-TRANSMIT-013829 | 2026-06-12
| MLCC-TRANSMIT-017831 | 2026-06-09 | MLCC-N0003-BES-FPS-FFS-MST-00005 | Method Statement for Installation of Electric-Driven, Centrifugal and Other Fire Pumps with Ancillaries : MLCC-N0003-BES-FPS-FFS-MST-00005_Rev.00 | 00 |  | MST | BES | FPS | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017830 | 2026-06-09 | MLCC-Z0041-UTL-NWW-GEN-MST-00001 | Re: Method Statement For Pocket Track Construction (PM100 – PM114) Ras Al Khor : MLCC-Z0041-UTL-NWW-GEN-MST-00001_Rev.01 | 01 |  | MST | UTL | NWW | 1 | Ashok Kumar
| MLCC-TRANSMIT-017829 | 2026-06-09 | DE.EEP.EEP2.STR.S0 | Package Submission - DCP2 - Emergency Egress Point-EEP2-STR: DE.EEP.EEP2.STR.S0.D2_Rev.C01 | C01 |  |  |  |  | 1 | Daniel Maddy | DCP2
| MLCC-TRANSMIT-017828 | 2026-06-09 | MLCC-N0003-ENG-SSA-FNL-RPT-65008 | Re: Report Submission - DCP1 - Fire Life Safety (FLS) Strategy Report (DE.GEN.GN00.MEP.M8.D1) : MLCC-N0003-ENG-SSA-FNL-RPT-65008_Rev.C01 | C01 |  | RPT | ENG | SSA | 1 | Ismaiel Salama | DCP1
| MLCC-TRANSMIT-017827 | 2026-06-09 | DE.UGS.SB01.STR.S7 | Re: Package Submission - DCP3 - Switchbox Base Slab (Remaining Area) : DE.UGS.SB01.STR.S7.D3_Rev.C04 | C04 |  |  |  |  | 1 | Daniel Maddy | DCP3
| MLCC-TRANSMIT-017826 | 2026-06-09 | MLCC-N0003-CIV-NWW-GEO-RPT-82263 | Re: Report Submission - DCP3 - Geotechnical Design Report for Viaduct - Stretch 4 (PM-99) (DE.VDT.ST04.GEO.G1.D3) ( MLCC-N0003-CIV-NWW-GEO-RPT-82263-DCP3_Rev.C02 | C02 |  | RPT | CIV | NWW | 1 | Mazar Syed | DCP3
| MLCC-TRANSMIT-017825 | 2026-06-09 | MLCC-N0003-NSP-NPR-GEN-DRW-00152 | NOC Drawing Submission - Tunnel NOC-02 Instrumentation And Monitoring Boreholes BB06 To BB05 (Ch:111+593.445 To 112+200) : MLCC-N0003-NSP-NPR-GEN-DRW-00152 & MLCC-N0003-NSP-NPR-GEN-DRW-00166 - 00167_Rev.C02 | C02 |  | DRW | NSP | NPR | 2 | Evripidis Zampiras
| MLCC-TRANSMIT-017824 | 2026-06-09 | MLCC-S0654-CIV-STN-RFC-DRW-13066 | Re: Shop Drawing Submission - Station BG32 - Concourse Level RC Elements Spine and Wing Beam At Grid 23 To 27 : MLCC-S0654-CIV-STN-RFC-DRW-13066-13073_Rev.C02 | C02 |  | DRW | CIV | STN | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017823 | 2026-06-09 | DE.VDT.ST51.STR.V3 | Package Submission - DCP3 - Stretch-05.1 - Viaduct Structure Superstructure 2SP Spans : DE.VDT.ST51.STR.V3.D3_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017822 | 2026-06-09 | DE.UGS.RE03.STR.S3 | Re: Package Submission - DCP3 - Station BR07 - Structure - Concourse Slab Submission -: DE.UGS.RE03.STR.S3.D3_Rev.C04 (Partial Submission) | C04 |  |  |  |  | 1 | Daniel Maddy | DCP3
| MLCC-TRANSMIT-017821 | 2026-06-09 | MLCC-N0003-BES-FPS-FFS-QUA-00003 | Re: PQ Submission - Prequalification Submittal For Butler Engineering LLC : MLCC-N0003-BES-FPS-FFS-QUA-00003_Rev.01 | 01 |  | QUA | BES | FPS | 1 | Lynneth Santos
| MLCC-TRANSMIT-017820 | 2026-06-09 |  | Package Submission - DCP3 - Utility Drawings Z0044 : DE.ZNE.ZN4B.UTI.U1.D3_Rev.C01 | C01 |  |  |  |  | 1 | Yazan Safieh | DCP3
| MLCC-TRANSMIT-017819 | 2026-06-09 | MLCC-N0003-CIV-VBR-FND-FCR-00003 | FCR Submission - Field Change and Drawing Modification Request - Viaduct Superstructure TWIN Global: MLCC-N0003-CIV-VBR-FND-FCR-00003_Rev.C01 | C01 |  | FCR | CIV | VBR | 1 | Mahmoud Saad
| MLCC-TRANSMIT-017818 | 2026-06-09 | MLCC-N0003-BES-LFT-SYW-MTS-00003 | Re: Material Approval Request for Elevators Type 3: Fire Lift "TK Elevator/MNG": MLCC-N0003-BES-LFT-SYW-MTS-00003_Rev.01 | 01 |  | MAT | BES | LFT | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017817 | 2026-06-09 | MLCC-N0003-BES-LFT-SYW-MTS-00002 | Re: Material Approval Request for Elevators Type 2: Passenger - Panoramic "TK Elevator/MNG": MLCC-N0003-BES-LFT-SYW-MTS-00002_Rev.01 | 01 |  | MAT | BES | LFT | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017816 | 2026-06-09 | MLCC-S0757-CIV-CCV-GAR-COD-00002 | T105 - Work Notification for CC-03 Emirates Road Crossing Cut&Cover Structure North Site, Site Grading and Levelling Works for TTM Road Works: MLCC-S0757-CIV-CCV-GAR-COD-00002_Rev.00 | 00 |  | COD | CIV | CCV | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017815 | 2026-06-09 | MLCC-N0003-PMC-PRC-RER-RPT-00491 | Daily Progress Report of 07-June-2026 : MLCC-N0003-PMC-PRC-RER-RPT-00491_Rev.00 | 00 |  | RPT | PMC | PRC | 1 | Ahmed Ibrahim
| MLCC-TRANSMIT-017814 | 2026-06-09 | MLCC-N0003-PMC-PRC-RER-RPT-00490 | Daily Progress Report of 06-June-2026 : MLCC-N0003-PMC-PRC-RER-RPT-00490_Rev.00 | 00 |  | RPT | PMC | PRC | 1 | Ahmed Ibrahim
| MLCC-TRANSMIT-017813 | 2026-06-09 | MLCC-S0724-CIV-EPD-RFC-DRW-13048 | Re: Shop Drawing Submission - BB05 Station - Ancillary-02 – D-wall - Type-AS1 - Primary Panel D14 & D16 Reinforcement : MLCC-S0724-CIV-EPD-RFC-DRW-13048-13049, 13105-13110_Rev.C01 (RCS Resubmission) | C01 |  | DRW | CIV | EPD | 1 | Suresh Shetty |  |  | PAJV-TRANSMIT-013842 | 2026-06-12
| MLCC-TRANSMIT-017812 | 2026-06-09 | MLCC-S0820-CIV-STN-RFC-DRW-14001 | Re: Shop Drawing Submission - Station BR07-Structure Pour-C8 Concourse Slab : MLCC-S0820-CIV-STN-RFC-DRW-14001-14018_Rev.C02 | C02 |  | DRW | CIV | STN | 1 | Suresh Shetty |  |  | PAJV-TRANSMIT-013840 | 2026-06-12
| MLCC-TRANSMIT-017811 | 2026-06-09 | MLCC-S0800-CIV-STN-RFC-DRW-13500 to 13522 | Re: Shop Drawing Submission - Station BR09 - Structure Pour-R1 Top Slab Drawings : MLCC-S0800-CIV-STN-RFC-DRW-13500 to 13522_Rev.C03 | C03 |  | DRW | CIV | STN | 1 | Vinod Kalwaghe
| MLCC-TRANSMIT-017810 | 2026-06-09 | MLCC-N0003-BES-FPS-FFS-QUA-00002 | Re: PQ Submission - Pre-qualification Submittal for Al Futtaim Engineering LLC : MLCC-N0003-BES-FPS-FFS-QUA-00002_Rev.01 | 01 |  | QUA | BES | FPS | 1 | Lynneth Santos
| MLCC-TRANSMIT-017809 | 2026-06-09 | MLCC-S0810-CIV-STN-RFC-DRW-13810 | Re: Shop Drawing Submission - Station BR08-Structure Pour-C6 Concourse Slab : MLCC-S0810-CIV-STN-RFC-DRW-13810-13836_Rev.C02 | C02 |  | DRW | CIV | STN | 1 | Vinod Kalwaghe |  |  | PAJV-TRANSMIT-013841 | 2026-06-12
| MLCC-TRANSMIT-017808 | 2026-06-09 | MLCC-N0003-TRW-FIX-PLT-RPT-81001 | Re: Report Submission - DCP1 - Technical Note for Track Derailment Containment (DE.GEN.TS00.TWK.P0.D1) : MLCC-N0003-TRW-FIX-PLT-RPT-81001_Rev.C02 | C02 |  | RPT | TRW | FIX | 1 | Stephen Beadle | DCP1 |  | PAJV-TRANSMIT-013849 | 2026-06-12
| MLCC-TRANSMIT-017807 | 2026-06-09 | MLCC-N0003-CIV-NWW-GEO-RPT-82448 | Re: Report Submission - DCP3 - Technical Note-Dynamic Pile load Test Viaduct Stretch 4.1 (PM-91-01) (DE.VDT.ST04.GEO.G1.D3) : MLCC-N0003-CIV-NWW-GEO-RPT-82448-DCP3_Rev.C02 (RCS Submission) | C02 |  | RPT | CIV | NWW | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017806 | 2026-06-09 | MLCC-N0003-SIG-ATC-NWW-RFI-10005 | Re: RFI Submission - Request for Information - Required Information for G30/G29/G28 As-built Drawing : MLCC-N0003-SIG-ATC-NWW-RFI-10005_Rev.C01 (OBSOLETE) | C01 |  | RFI | SIG | ATC | 1 | Kaddour Lardjani
| MLCC-TRANSMIT-017805 | 2026-06-09 | DE.UGS.RE01.STR.S7 | Re: Package Submission - DCP3 - Station BR09 - Structure Ancillary 01 Dwall Reinforcements Details : DE.UGS.RE01.STR.S7.D3_Rev.C02 | C02 |  |  |  |  | 1 | Daniel Maddy | DCP3
| MLCC-TRANSMIT-017804 | 2026-06-09 | DE.ZNE.ZN05.ARD.R0 | Re: Package Submission - DCP2 - Z0045 Road Package : DE.ZNE.ZN05.ARD.R0.D2_Rev.C01(RCS Submission) | C01 |  |  |  |  | 1 | Sandeep Jha | DCP2
| MLCC-TRANSMIT-017803 | 2026-06-09 |  | Re: Package Submission - DCP2 - Zone 4A Roads Z0043 Package : DE.ZNE.ZN4A.ARD.R0.D2_Rev.C01 (RCS Resubmission) | C01 |  |  |  |  | 1 | Sandeep Jha | DCP2
| MLCC-TRANSMIT-017802 | 2026-06-09 | MLCC-N0003-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - General Requirements and office Allocation Schedules for the Blue Line Metro Transit Security Management (AR) (DE.GEN.GN00.ARC.03.GN) : MLCC-N0003-ARC-NWW-GAR-DRW-23000_Rev.C02 | C02 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017801 | 2026-06-09 | MLCC-S0675-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - Iconic Station BG34 - DTS Requirements (AR) Security Drawings (DE.ELS.GE03.ARC.A2.D2) : MLCC-S0675-ARC-NWW-GAR-DRW-23000-23006_Rev.C03 | C03 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017800 | 2026-06-09 | MLCC-S0647-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - Al Khor Transit Station BG31 - DTS Requirements (AR) Security Drawings (DE.ELS.GE00.ARC.A2.D2) : MLCC-S0647-ARC-NWW-GAR-DRW-23000-23006_Rev.C02 | C02 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017799 | 2026-06-09 | MLCC-S0709-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - Underground Transfer Station BB06 - Global City 1 - DTS Requirements (AR) Security Drawings (DE.UGS.GE08.ARC.A2.D2) : MLCC-S0709-ARC-NWW-GAR-DRW-23000-23004_Rev.C02 | C02 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017798 | 2026-06-09 | MLCC-S0719-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - Word City 2 Subway Station BB05 - DTS Requirements (AR) Security Drawings (DE.UGS.GE09.ARC.A0.D2) : MLCC-S0719-ARC-NWW-GAR-DRW-23000-23006_Rev.C01 | C01 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017797 | 2026-06-09 | MLCC-S0742-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - Station BB03 - DTS Requirements (AR) Security Drawings (DE.ELS.GE11.ARC.A2.D2) : MLCC-S0742-ARC-NWW-GAR-DRW-23000-23005_Rev.C01 | C01 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017796 | 2026-06-09 | MLCC-S0770-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP1 - BDR08 and BDR12 Depot - DTS Requirements (AR) Security Drawings (DE.DPT.OCCA.ARC.A0.D1) : MLCC-S0770-ARC-NWW-GAR-DRW-23000-23007_Rev.C01 | C01 |  | DRW | ARC | NWW | 1 |  | DCP1
| MLCC-TRANSMIT-017795 | 2026-06-09 | MLCC-S0788-ARC-NWW-GAR-DRW-23000 | Re: Drawing Submission - DCP2 - Transit Station BR10 - Centerpoint / Al Rashidiya - DTS Requirements (AR) Security Drawings (DE.ELS.RE00.ARC.A2.D2) : MLCC-S0788-ARC-NWW-GAR-DRW-23000-23003_Rev.C02 | C02 |  | DRW | ARC | NWW | 1 |  | DCP2
| MLCC-TRANSMIT-017794 | 2026-06-09 |  | Re: Calculation Submission - Extension Calculation for Stretch 08.2 Viaducts Structure Twin Span 284 & 285 : MLCC-C0198-CIV-VBR-2SP-CAL-00001_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad
| MLCC-TRANSMIT-017793 | 2026-06-09 | MLCC-C0003-ARC-PTW-GAR-DRW-10016 to 10023 | Re: Shop Drawing Submission - Rashidya Temporary Corridor Shop Drawings Doors & Tactile : MLCC-C0003-ARC-PTW-GAR-DRW-10016 to 10023_Rev.C03 | C03 |  | DRW | ARC | PTW | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017792 | 2026-06-09 | MLCC-N0003-CIV-NWW-GAR-QUA-00120 | Re: PQ Submission - Prequalification Submittal For ECAM Building Maintenance and Demolition LLC : MLCC-N0003-CIV-NWW-GAR-QUA-00120_Rev.01 | 01 |  | QUA | CIV | NWW | 1 | Lynneth Santos
| MLCC-TRANSMIT-017791 | 2026-06-09 | MLCC-C0204-TAL-TRH-ROD-DRW-00005 | Drawing Submission - Temporary Traffic Diversion At Mirdif BR09 Station : MLCC-C0204-TAL-TRH-ROD-DRW-00005 - 00006_Rev.C01 | C01 |  | DRW | TAL | TRH | 1 | Ahmad Chikh bakri
| MLCC-TRANSMIT-017790 | 2026-06-09 | MLCC-N0003-COM-NWW-GEN-SPC-51040 | Specification Submission - Dubai Metro Blue Line- Enhancement Technical Solution (COMS) (ENH.2.1.3) : MLCC-N0003-COM-NWW-GEN-SPC-51040_Rev.C01 | C01 |  | SPC | COM | NWW | 1 | Allan Halferty
| MLCC-TRANSMIT-017789 | 2026-06-09 | MLCC-N0003-MSM-MDP-GEN-PLN-00001 | Re: Plan Submission - Preliminary Maintenance Management Plan : MLCC-N0003-MSM-MDP-GEN-PLN-00001_Rev.C03 | C03 |  | PLN | MSM | MDP | 1 | Nageswara Ampolu
| MLCC-TRANSMIT-017788 | 2026-06-09 | MLCC-N0003-TRW-NWW-GEN-PLN-00005 | Plan Submission - FAT Plan for Flash Butt Welding Machine : MLCC-N0003-TRW-NWW-GEN-PLN-00005_Rev.00 | 00 |  | PLN | TRW | NWW | 1 | John Prabhu
| MLCC-TRANSMIT-017787 | 2026-06-09 | MLCC-N0003-PMC-PRC-RER-RPT-00489 | Daily Progress Report of 05-June-2026 : MLCC-N0003-PMC-PRC-RER-RPT-00489_Rev.00 | 00 |  | RPT | PMC | PRC | 1 | Ahmed Ibrahim
| MLCC-TRANSMIT-017786 | 2026-06-08 | DE.VDT.GN00.STR.04 | Re: Package Submission - DCP3 Station Superstructure-Global 3SPAN PKG-1 : DE.VDT.GN00.STR.04.D3_Rev.C03 | C03 |  |  |  |  | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017785 | 2026-06-08 | DE.VDT.GE11.STR.V3 | Re: Package Submission - DCP3_Station BB03 - Viaduct Structure Three Span Setting Out Superstructure: DE.VDT.GE11.STR.V3.D3_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad
| MLCC-TRANSMIT-017784 | 2026-06-08 | MLCC-Z0015-CIV-NWW-GAR-MTS-00025 | Material Approval Request for Galvanized Binding Wire (1.2mm) "Admiral Hardware L.L.C, Ashkal (FZE)/BVA": MLCC-Z0015-CIV-NWW-GAR-MTS-00025_Rev.00 | 00 |  | MAT | CIV | NWW | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017783 | 2026-06-08 | MLCC-N0003-BES-ECS-SYW-MTS-00001 | Material Approval Request for Control & Monitoring Cables "CAVICEL/MNG": MLCC-N0003-BES-ECS-SYW-MTS-00001_Rev.00 | 00 |  | MAT | BES | ECS | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017782 | 2026-06-08 | MLCC-N0003-CIV-NWW-GAR-MTS-00284 | Material Approval Request for HDG-MS Pipe OD 168.3mm ID 150mm- S355 J2H "HBIS / EMBOSAL / Royal Steel Fabrication": MLCC-N0003-CIV-NWW-GAR-MTS-00284_Rev.00 | 00 |  | MAT | CIV | NWW | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017781 | 2026-06-08 | MLCC-N0003-CIV-NWW-GAR-MTS-00283 | Material Approval Request for Neoprene Sheet (5MM) "Supreme Rubber": MLCC-N0003-CIV-NWW-GAR-MTS-00283_Rev.00 | 00 |  | MAT | CIV | NWW | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017780 | 2026-06-08 | MLCC-N0003-CIV-NWW-GAR-MTS-00282 | Material Approval Request for Granular Bedding for Pipe Bedding (Above 600mm) "AL Amara Crusher/ Marjan Aman": MLCC-N0003-CIV-NWW-GAR-MTS-00282_Rev.00 | 00 |  | MAT | CIV | NWW | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017779 | 2026-06-08 | MLCC-N0003-CIV-TNL-SYW-MTS-00051 | Material Approval Request - Technical Submittal for C30/40 FRC Class 2C – Annex Galleries (Sprayed Concrete – Primary Lining) (Mix Code : M4002) 69.4% OPC + 27% GGBS + 3.6% MS + Steel Fiber "Emirate Beton": MLCC-N0003-CIV-TNL-SYW-MTS-00051_Rev.00 | 00 |  | MAT | CIV | TNL | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017778 | 2026-06-08 | MLCC-N0003-CIV-TNL-SYW-MTS-00050 | Material Approval Request - Technical Submittal for C25/30 – Tunnel Back fill Concrete Under Invert (Lean concrete) (Mix Code : M3014)- 64% OPC + 36% GGBS "Emirate Beton": MLCC-N0003-CIV-TNL-SYW-MTS-00050_Rev.00 | 00 |  | MAT | CIV | TNL | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017777 | 2026-06-08 | MLCC-N0003-CIV-TNL-SYW-MTS-00049 | Material Approval Request for Pin Socket System "FORTA": MLCC-N0003-CIV-TNL-SYW-MTS-00049_Rev.00 | 00 |  | MAT | CIV | TNL | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017776 | 2026-06-08 | MLCC-N0003-ARC-NWW-GAR-MTS-00112 | Material Approval Request for Reconstituted Stone "Global Surfaces FZE-UAE": MLCC-N0003-ARC-NWW-GAR-MTS-00112_Rev.00 | 00 |  | MAT | ARC | NWW | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017775 | 2026-06-08 | MLCC-N0003-ARC-NWW-GAR-MTS-00044 | Re: Material Approval Request for Raised Access Floor System "MBM": MLCC-N0003-ARC-NWW-GAR-MTS-00044_Rev.01 | 01 |  | MAT | ARC | NWW | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017774 | 2026-06-08 | MLCC-S0715-CIV-EES-RFC-DRW-13038 to 13049 | Re: Shop Drawing Submission - Annex Structure - BL-EES06 Structure D-Wall Shop Drawing - Primary Panel P7 & P9 Type IV-C* (P) : MLCC-S0715-CIV-EES-RFC-DRW-13038 to 13049_Rev.C03 | C03 |  | DRW | CIV | EES | 1 | Suresh Shetty
| MLCC-TRANSMIT-017772 | 2026-06-08 | DE.VDT.ST00.STR.V2 | Package Submission - DCP3 - Stretch 00 - Viaduct Structure Pier Head ISO & 2SP: DE.VDT.ST00.STR.V2.D3_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017771 | 2026-06-08 | MLCC-S0719-CIV-STN-RFC-DRW-13205 | Re: Shop Drawing Submission - BB05 Station – Concourse Slab – Pour-5 Reinforcement Shop Drawings:MLCC-S0719-CIV-STN-RFC-DRW-13205 to MLCC-S0719-CIV-STN-RFC-DRW-13222, MLCC-S0719-CIV-STN-RFC-DRW-13294 and MLCC-S0719-CIV-STN-RFC-DRW-13295_Rev.C02 | C02 |  | DRW | CIV | STN | 4 | Suresh Shetty |  |  | PAJV-TRANSMIT-013847 | 2026-06-12
| MLCC-TRANSMIT-017770 | 2026-06-08 | MLCC-S0810-CIV-STN-RFC-DRW-13885 | Shop Drawing Submission - Station BR08-Structure Pour-C9 Concourse Slab : MLCC-S0810-CIV-STN-RFC-DRW-13885-13912_Rev.C01 | C01 |  | DRW | CIV | STN | 1 | Vinod Kalwaghe
| MLCC-TRANSMIT-017769 | 2026-06-08 | MLCC-C0003-ARC-PTW-GAR-RPT-00001 | Re: Report Submission - Rashidiya Temporary Passageway Signages Strategy Report : MLCC-C0003-ARC-PTW-GAR-RPT-00001_Rev.C02 (RCS Resubmission) | C02 |  | RPT | ARC | PTW | 1 |  |  |  | PAJV-TRANSMIT-013675 | 2026-06-09
| MLCC-TRANSMIT-017768 | 2026-06-08 | MLCC-S0651-CIV-VBR-FND-MST-00002 | Re: Method Statement For Excavation and Scour Protection Works for Creek Crossing Bridge : MLCC-S0651-CIV-VBR-FND-MST-00002_Rev.01 | 01 |  | MST | CIV | VBR | 1 | Ashok Kumar
| MLCC-TRANSMIT-017767 | 2026-06-08 | MLCC-N0003-CIV-NWW-GAR-QUA-00101 | Re: PQ Submission - Prequalification Submittal for FF Group & Alufar : MLCC-N0003-CIV-NWW-GAR-QUA-00101_Rev.02 | 02 |  | QUA | CIV | NWW | 1 | Lynneth Santos
| MLCC-TRANSMIT-017766 | 2026-06-08 | MLCC-C0174-CIV-NWW-GAR-MST-00005 | Method Statement for Precast Works at BG-31 Creek Interchange Station : MLCC-C0174-CIV-NWW-GAR-MST-00005_Rev.00 | 00 |  | MST | CIV | NWW | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017765 | 2026-06-08 | MLCC-N0003-DEP-NWW-GEN-RFI-10001 | RFI Submission - Request for Information - Lightning Protection System and DEWA requirements for Solar Panels : MLCC-N0003-DEP-NWW-GEN-RFI-10001_Rev.C01 | C01 |  | RFI | DEP | NWW | 1 | Ismaiel Salama
| MLCC-TRANSMIT-017764 | 2026-06-08 | DE.ZNE.ZN06.UTI.U2 | Re: Package Submission - DCP2 - Utility Station Tie-in, SL and SWD - Z0046 Package: DE.ZNE.ZN06.UTI.U2.D2_Rev.C02 | C02 |  |  |  |  | 1 | Yazan Safieh | DCP2
| MLCC-TRANSMIT-017763 | 2026-06-08 |  | Re: Package Submission - DCP2 - Zone 4A Utility Z0043 (Creek Mainline) Package : DE.ZNE.ZN4A.UTI.U2.D2_Rev.C02 | C02 |  |  |  |  | 1 | Yazan Safieh | DCP2
| MLCC-TRANSMIT-017762 | 2026-06-08 | DE.VDT.ST08.STR.V2 | Package Submission - DCP3 - Stretch 08.1 - Viaduct Structure Pierhead - 2SP Part 2 (PM246) : DE.VDT.ST08.STR.V2.D3_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017761 | 2026-06-08 | MLCC-N0003-CIV-NWW-GAR-RPT-21541 | Re: Drawing and Report Submission - Segment Erection on Falsework for ISO/Twin/Station Span & Drop-In Span : MLCC-N0003-CIV-NWW-GAR-RPT-21541_Rev.C02 | C02 |  | RPT | CIV | NWW | 1 | Mahmoud Saad
| MLCC-TRANSMIT-017759 | 2026-06-08 | DE.VDT.ST09.STR.V1 | Package Submission - DCP3 - Stretch 09.2 - Viaduct Structure Substructure - Transition Ramps-4 Concrete Out Line : DE.VDT.ST09.STR.V1.D3_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017758 | 2026-06-08 | MLCC-N0003-CIV-NWW-GAR-PLN-00066 | Lifting Plan for Lifting and Installation of Launching Gantry (LG50) Winch Trolley for LG – 03 : MLCC-N0003-CIV-NWW-GAR-PLN-00066_Rev.00 | 00 |  | PLN | CIV | NWW | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017757 | 2026-06-08 | MLCC-N0003-PMC-RKM-GEN-RPT-00002 | Re: Report Submission - Risk Management Monthly Report with Quantitative Schedule Risk Analysis (QSRA) (May 2026) : MLCC-N0003-PMC-RKM-GEN-RPT-00002_Rev.C07 | C07 |  | RPT | PMC | RKM | 1 | Ahmed Ibrahim
| MLCC-TRANSMIT-017756 | 2026-06-08 | DE.VDT.ST03.STR.V2 | Shop Drawing Submission - Stretch-03 - Viaduct Structure Pierhead -PM74, Inserts, Coordinates & Bearing BBS : DE.VDT.ST03.STR.V2.D5_Rev.C01 | C01 |  |  |  |  | 1 | Ashok Kumar |  |  | PAJV-TRANSMIT-013772 | 2026-06-11
| MLCC-TRANSMIT-017755 | 2026-06-08 | DE.VDT.GN00.STR.01 | Package Submission - DCP3 -Global - Viaduct Structure ISO Span Superstructure-Global ISO Pkg : DE.VDT.GN00.STR.01.D3_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017754 | 2026-06-08 | MLCC-S0719-CIV-STN-RFC-DRW-13144 | Re: Shop Drawing Submission - Station BB05-Structure Concourse Slab Soffit Level Lifting Hook Arrangement : MLCC-S0719-CIV-STN-RFC-DRW-13144_Rev.C01 (RCS Resubmission) | C01 |  | DRW | CIV | STN | 1 | Suresh Shetty |  |  | PAJV-TRANSMIT-013835 | 2026-06-12
| MLCC-TRANSMIT-017753 | 2026-06-08 | MLCC-S0794-CIV-CCV-RFC-DRW-13141 | Re: Shop Drawing Submission - CC04 Cut & Cover – D-wall - Type-D Secondary Panel S48, S49, S50, S51 & S52 Reinforcement : MLCC-S0794-CIV-CCV-RFC-DRW-13141-13150_Rev.C01 (RCS Resubmission) | C01 |  | DRW | CIV | CCV | 1 | Shahab Ahmad Khan |  |  | PAJV-TRANSMIT-013771 | 2026-06-11
| MLCC-TRANSMIT-017752 | 2026-06-08 | MLCC-S0794-CIV-CCV-RFC-DRW-13201 | Re: Shop Drawing Submission - CC04 Cut & Cover – D-wall - Type-D Secondary Panel S6, S7, S8, S9 & S10 Reinforcement : MLCC-S0794-CIV-CCV-RFC-DRW-13201-13210_Rev.C01 (RCS Resubmission) | C01 |  | DRW | CIV | CCV | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017751 | 2026-06-08 | MLCC-S0794-CIV-CCV-RFC-DRW-13111 | Re: Shop Drawing Submission - CC04 Cut & Cover – D-wall - Type-D Primary Panel P49, P50, P51, P52 & P53 Reinforcement : MLCC-S0794-CIV-CCV-RFC-DRW-13111-13125_Rev.C01 (RCS Resubmission) | C01 |  | DRW | CIV | CCV | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017750 | 2026-06-08 | MLCC-S0794-CIV-CCV-RFC-DRW-13176 | Re: Shop Drawing Submission - CC04 Cut & Cover – D-wall - Type-D Primary Panel P6, P7, P8, P9 & P10 Reinforcement shop drawing : MLCC-S0794-CIV-CCV-RFC-DRW-13176-13190_Rev.C01 (RCS Resubmission) | C01 |  | DRW | CIV | CCV | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017749 | 2026-06-08 | MLCC-N0003-CIV-NWW-GEO-RPT-82442 | Re: Report Submission - DCP3 - Dynamic Pile load Test Viaduct Stretch 6 (PM-162-01, PM-185-01, PM-190-03) (DE.VDT.ST06.GEO.G1.D3) : MLCC-N0003-CIV-NWW-GEO-RPT-82442_Rev.C02 (RCS Resubmission) | C02 |  | RPT | CIV | NWW | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017748 | 2026-06-08 | MLCC-N0003-CIV-NWW-GEO-RPT-82424 | Re: Report Submission - DCP3 - Technical Note - Dynamic Pile load Test Viaduct Stretch 2 (PM43-02, PM45-04, PM47 A-01) (DE.VDT.ST02.GEO.G1.D3) : MLCC-N0003-CIV-NWW-GEO-RPT-82424_Rev.C02 (RCS Resubmission) | C02 |  | RPT | CIV | NWW | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017747 | 2026-06-08 | MLCC-N0003-PSD-NWW-SSA-PLN-51610 | Plan Submission - DCP2 - Platform Screen Doors (PSD) - RAMS - Software Development Management Plan (RLS.1.1.1.5.5 ) : MLCC-N0003-PSD-NWW-SSA-PLN-51610_Rev.C03 | C03 |  | PLN | PSD | NWW | 1 | Stephen Beadle | DCP2
| MLCC-TRANSMIT-017746 | 2026-06-08 | MLCC-N0003-PSD-NWW-SSA-PLN-51608 | Plan Submission - DCP2 - Platform Screen Doors (PSD) - RAMS - Software Quality Assurance Plan (RLS.1.8.1) : MLCC-N0003-PSD-NWW-SSA-PLN-51608_Rev.C03 | C03 |  | PLN | PSD | NWW | 1 | Stephen Beadle | DCP2
| MLCC-TRANSMIT-017745 | 2026-06-08 | MLCC-N0003-PSD-NWW-SSA-PLN-51611 | Plan Submission - DCP2 - Platform Screen Doors (PSD) - RAMS - Software Verification Plan (RLS.1.1.1.5.5) : MLCC-N0003-PSD-NWW-SSA-PLN-51611_Rev.C03 | C03 |  | PLN | PSD | NWW | 1 | Stephen Beadle | DCP2
| MLCC-TRANSMIT-017744 | 2026-06-08 | MLCC-N0003-CIV-NWW-GAR-RPT-26009 | Report Submission - Shoring Frame Design Reports : MLCC-N0003-CIV-NWW-GAR-RPT-26009_Rev.C01 | C01 |  | RPT | CIV | NWW | 1 | Mahmoud Saad
| MLCC-TRANSMIT-017743 | 2026-06-08 | DE.ELS.GE10.ARC.A2 | Package Submission - DCP2 - Elevated Station – BB04 Architecture: DE.ELS.GE10.ARC.A2.D2_Rev.C01 | C01 |  |  |  |  | 1 | Mike Lewey | DCP2
| MLCC-TRANSMIT-017742 | 2026-06-08 | MLCC-S0725-CIV-CCV-RTS-RPT-26000 | Re: Drawing & Report Submission - Design Report for Guide Wall - CC02 : MLCC-S0725-CIV-CCV-RTS-RPT-26000 & MLCC-S0725-CIV-CCV-RTS-DRW-26000-26002_Rev.C02 | C02 |  | RPT | CIV | CCV | 2 | Mahmoud Saad
| MLCC-TRANSMIT-017741 | 2026-06-08 | DE.VDT.ST09.STR.V2 | Package Submission - DCP3 - Stretch-09.1 - Viaduct Structure Pierhead ISO & 2SP Span : DE.VDT.ST09.STR.V2.D3_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017740 | 2026-06-08 | MLCC-N0003-BES-NWW-EQG-MST-00002 | Method Statement for Installation of Expansion Joints, Fittings and Loops for Mechanical Services : MLCC-N0003-BES-NWW-EQG-MST-00002_Rev.00 | 00 |  | MST | BES | NWW | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017739 | 2026-06-08 | MLCC-C0189-FCL-SSF-GEN-ITP-00001 | Re: ITP Submission - Inspection and Test Plan (ITP) For Prestressed Anchors (Include Waler Beam) : MLCC-C0189-FCL-SSF-GEN-ITP-00001_Rev.01 | 01 |  | ITP | FCL | SSF | 1 | Mohamed Yahia
| MLCC-TRANSMIT-017738 | 2026-06-08 | MLCC-C0003-CIV-PTW-GAR-RPT-00001 | Re: Report Submission - Safety Report for Temporary Pedestrian Passageway at Centrepoint Station (Enhancement Works) : MLCC-C0003-CIV-PTW-GAR-RPT-00001_Rev.C06 | C06 |  | RPT | CIV | PTW | 1 | Stephen Beadle
| MLCC-TRANSMIT-017737 | 2026-06-08 | MLCC-N0003-ENG-ASM-GEN-SPC-00003 | Re: Specification Submission - Maintenance Management System (MMS) Maintenance Job Plan Specification : MLCC-N0003-ENG-ASM-GEN-SPC-00003_Rev.C02 | C02 |  | SPC | ENG | ASM | 1 | Nageswara Ampolu
| MLCC-TRANSMIT-017736 | 2026-06-08 | MLCC-S0048-BES-ELE-LVD-DRW-26000 | Design Drawing Submission - Rashidiya Station Enhancement Works Concept Design Drawing - Temporary MEP Works : MLCC-S0048-BES-ELE-LVD-DRW-26000-26005, MLCC-S0048-BES-FPS-FFS-DRW-26000-26005_Rev.C01 | C01 |  | DRW | BES | ELE | 2 | Ismaiel Salama
| MLCC-TRANSMIT-017735 | 2026-06-08 | MLCC-N0003-CIF-CDS-GEN-QUA-00001 | PQ Submission - Prequalification Submittal For Commissioning Services International Global (CSI) : MLCC-N0003-CIF-CDS-GEN-QUA-00001_Rev.00 | 00 |  | QUA | CIF | CDS | 1 | Lynneth Santos
| MLCC-TRANSMIT-017734 | 2026-06-08 | MLCC-N0003-CIV-NWW-GAR-DRW-24246 | Shop Drawing Submission - Global - Viaduct Structure PT Stressing Sequence for Load Transfer Twin Span - (44m+44m) : MLCC-N0003-CIV-NWW-GAR-DRW-24246_Rev.C01 | C01 |  | DRW | CIV | NWW | 1 | Amit Kumar |  |  | PAJV-TRANSMIT-013657 | 2026-06-08
| MLCC-TRANSMIT-017733 | 2026-06-08 | DE.VDT.GN00.STR.05 | Re: Shop Drawing Submission - Global - Viaduct Structure Pierhead - Balanced Cantilever PHR-BC-11: DE.VDT.GN00.STR.05.D5_Rev.C01 | C01 |  |  |  |  | 1 | Amit Kumar
| MLCC-TRANSMIT-017732 | 2026-06-08 | MLCC-N0003-QHS-QUM-GEN-SCH-00002 | Re: Schedule Submission - Factory Acceptance Test (FAT) Plan and Schedule : MLCC-N0003-QHS-QUM-GEN-SCH-00002_Rev.C02 | C02 |  | OTH | QHS | QUM | 1 | Alister White
| MLCC-TRANSMIT-017731 | 2026-06-08 | MLCC-S0692-CIV-STN-GAR-DRW-13026 to 13027 | Shop Drawing Submission - Structure Concourse Level Wing Beam PTB8 Details for PT, Reinforcement and Anchor Bolt At Grid 19_MLCC-S0692-CIV-STN-GAR-DRW-13026 to 13027, MLCC-S0692-CIV-STN-RFC-DRW-13073 to 13079, MLCC-S0692-CIV-STN-SSR-DRW-13014_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017730 | 2026-06-08 | MLCC-N0003-QHS-NWW-GEN-PLN-00002 | Re: Plan Submission : Project Health and Safety Management Plan : MLCC-N0003-QHS-NWW-GEN-PLN-00002_Rev.C01 | C01 |  | PLN | QHS | NWW | 1 | Loren Leiski
| MLCC-TRANSMIT-017729 | 2026-06-06 | MLCC-N0003-BES-DAW-SYW-RPT-00014 | Construction Waste Management and Consumption Monthly Report - May 2026 : MLCC-N0003-BES-DAW-SYW-RPT-00014_Rev.00 | 00 |  | RPT | BES | DAW | 1 | Loren Leiski
| MLCC-TRANSMIT-017728 | 2026-06-06 |  | Calculation Submission - Extension Calculation for Stretch 08.2 Viaducts Structure Twin Span 284 & 285 : MLCC-C0198-CIV-VBR-2SP-CAL-00001_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad
| MLCC-TRANSMIT-017727 | 2026-06-06 | MLCC-S0709-CIV-STN-RFC-DRW-13188 | Shop Drawing Submission - Station BB06-Structure Pour PW 1-1, 1-2, 2-1, 3-1 & 4-1 Base Slab To Platform Wall Reinf : MLCC-S0709-CIV-STN-RFC-DRW-13188 -13189_Rev.C01 | C01 |  | DRW | CIV | STN | 1 | Suresh Shetty
| MLCC-TRANSMIT-017726 | 2026-06-06 | MLCC-N0003-CIV-NWW-GEO-RPT-00281 | Report Submission - Pre-Construction Condition Survey Report for Centrepoint Metro Station - Car Parking Building : MLCC-N0003-CIV-NWW-GEO-RPT-00281_Rev.00 | 00 |  | RPT | CIV | NWW | 1 | Ahmad Chikh bakri
| MLCC-TRANSMIT-017725 | 2026-06-06 | MLCC-N0003-CIV-NWW-GEO-RPT-00278 | Re: Report Submission - Pre-Construction Condition Survey Report for Centrepoint Metro Station : MLCC-N0003-CIV-NWW-GEO-RPT-00278_Rev.00 | 00 |  | RPT | CIV | NWW | 1 | Mazar Syed
| MLCC-TRANSMIT-017724 | 2026-06-06 | MLCC-S0709-CIV-STN-FND-DRW-13137 to 13141 | Re: Shop Drawing Submission - Station BB06 Base Slab Pour 16 - Reinforcement Details - Shop Drawings - MLCC-S0709-CIV-STN-FND-DRW-13137 to 13141 - Rev.C02 |  |  | DRW | CIV | STN | 1 | Suresh Shetty
| MLCC-TRANSMIT-017723 | 2026-06-06 | MLCC-S0820-CIV-STN-RFC-DRW-13873 | Shop Drawing Submission - Station BR07-Structure Pour-C7 Concourse Slab : MLCC-S0820-CIV-STN-RFC-DRW-13873 - MLCC-S0820-CIV-STN-RFC-DRW-13891_Rev.C01 | C01 |  | DRW | CIV | STN | 2 | Suresh Shetty |  |  | PAJV-TRANSMIT-013691 | 2026-06-09
| MLCC-TRANSMIT-017722 | 2026-06-06 | MLCC-S0709-CIV-STN-FND-DRW-13088 | Shop Drawing Submission - Station BB06 Base Slab Pour 10 : MLCC-S0709-CIV-STN-FND-DRW-13088 - 13092_Rev.C01 | C01 |  | DRW | CIV | STN | 1 | Suresh Shetty
| MLCC-TRANSMIT-017721 | 2026-06-06 | MLCC-N0003-TRW-PWA-RAL-QUA-00001 | PQ Submission - Prequalification Submittal For SGS : MLCC-N0003-TRW-PWA-RAL-QUA-00001_Rev.00 | 00 |  | QUA | TRW | PWA | 1 | Lynneth Santos
| MLCC-TRANSMIT-017720 | 2026-06-06 | MLCC-N0003-PMC-PRC-RER-RPT-00488 | Daily Progress Report of 04-June-2026 : MLCC-N0003-PMC-PRC-RER-RPT-00488_Rev.00 | 00 |  | RPT | PMC | PRC | 1 | Ahmed Ibrahim
| MLCC-TRANSMIT-017719 | 2026-06-06 | MLCC-N0003-ARC-NWW-GAR-MTS-00020 | Material Approval Request for Standing Seam "KINGSPAN": MLCC-N0003-ARC-NWW-GAR-MTS-00020_Rev.00 | 00 |  | MAT | ARC | NWW | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017718 | 2026-06-06 | MLCC-N0003-PDS-MPD-NWW-NTS-51205 | Note Submission - DCP2 - Traction Cable Sizing Calculation Note (RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-NWW-NTS-51205_Rev.C03 | C03 |  | NTS | PDS | MPD | 1 | Sherif Zayed | DCP2 |  | PAJV-TRANSMIT-013660 | 2026-06-08
| MLCC-TRANSMIT-017717 | 2026-06-06 | MLCC-S0692-CIV-STN-GAR-DRW-13044 | Shop Drawing Submission - Station BG36 - Structure Cross Head PT Detail and Reinforcement Detail At Gri 22_MLCC-S0692-CIV-STN-GAR-DRW-13044, MLCC-S0692-CIV-STN-PIR-DRW-13027, MLCC-S0692-CIV-STN-PIR-DRW-13028_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan |  |  | PAJV-TRANSMIT-013704 | 2026-06-09
| MLCC-TRANSMIT-017716 | 2026-06-06 | MLCC-N0003-BES-LFT-SYW-MTS-00001 | Re: Material Approval Request for Elevators Type 1: Passenger - Non Panoramic "TK Elevator/MNG": MLCC-N0003-BES-LFT-SYW-MTS-00001_Rev.01 | 01 |  | MAT | BES | LFT | 1 | Arunkumar Ramakrishnan
| MLCC-TRANSMIT-017715 | 2026-06-06 | MLCC-C0066-ARC-STN-GAR-DRW-10000 | Re: Shop Drawing Submission - Creek G30 Temporary Scaffolding at Concourse and Platform Level : MLCC-C0066-ARC-STN-GAR-DRW-10000-10001_Rev.C01 | C01 |  | DRW | ARC | STN | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017714 | 2026-06-06 | DE.ANX.AX06.STR.S0 | Package Submission - DCP2 - Annex Structure - BL-EES14 Structure : DE.ANX.AX06.STR.S0.D2_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad | DCP2
| MLCC-TRANSMIT-017713 | 2026-06-06 | MLCC-S0675-CIV-STN-RFC-DRW-13011 | Re: Shop Drawing Submission - Station BG34 - Structure Longitudinal Beam At Grid 09-17 & C.8-D & E-E.2 Shop Drawing : MLCC-S0675-CIV-STN-RFC-DRW-13011-13020,MLCC-S0675-CIV-STN-SSR-DRW-13060 - 13067_Rev.C02 | C02 |  | DRW | CIV | STN | 2 | Shahab Ahmad Khan |  |  | PAJV-TRANSMIT-013706 | 2026-06-09
| MLCC-TRANSMIT-017712 | 2026-06-06 | MLCC-N0003-CIF-SIF-GEN-ICD-51211 | ICD Submission - DCP2 - Interface Control Document (ICD) for STN UG (SWB) / Rail System : MLCC-N0003-CIF-SIF-GEN-ICD-51211_Rev.C01 | C01 |  | ICD | CIF | SIF | 1 | Rohit Tharakan | DCP2
| MLCC-TRANSMIT-017711 | 2026-06-06 | MLCC-N0003-CIV-NWW-GAR-PLN-00067 | Lifting Plan for Rebar Cage Lifting and installation in 1500mm Dia Piling Work (BR09) : MLCC-N0003-CIV-NWW-GAR-PLN-00067_Rev.00 | 00 |  | PLN | CIV | NWW | 1 | Vinod Kalwaghe
| MLCC-TRANSMIT-017710 | 2026-06-06 | DE.ANX.AX09.STR.S1 | Package Submission - DCP3 - Annex Structure - BL-EES17 Structure D-Wall -: DE.ANX.AX09.STR.S1.D3_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017709 | 2026-06-06 | DE.ELS.GE03.ARC.A2 | Re: Package Submission - DCP2 - BG34 Station - Architecture Package : DE.ELS.GE03.ARC.A2.D2_Rev.C03 (Part 2 Submission) | C03 |  |  |  |  | 1 |  | DCP2
| MLCC-TRANSMIT-017708 | 2026-06-06 | MLCC-N0003-PDS-MPD-NWW-SPC-51007 | Specification Submission - DCP2 - Cable Trays Technical Specification (RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-NWW-SPC-51007_Rev.C03 | C03 |  | SPC | PDS | MPD | 1 |  | DCP2 |  | PAJV-TRANSMIT-013635 | 2026-06-08
| MLCC-TRANSMIT-017707 | 2026-06-06 | MLCC-S0810-CIV-STN-RFC-DRW-13860 | Shop Drawing Submission - Station BR08-Structure Pour-C8 Concourse Slab Shop Drawing : MLCC-S0810-CIV-STN-RFC-DRW-13860 - 13882_Rev.C01 | C01 |  | DRW | CIV | STN | 1 | Vinod Kalwaghe
| MLCC-TRANSMIT-017706 | 2026-06-06 | MLCC-C0191-CIF-CDS-GEN-IRE-95001 | Re: ICF Submission - Interface Control Form (ICF) for Concourse Slab Cutout Analysis ARC/STR/MEP/RSY - BB05 Station : MLCC-C0191-CIF-CDS-GEN-IRE-95001_Rev.C02 | C02 |  | OTH | CIF | CDS | 1 |  |  |  | PAJV-TRANSMIT-013813 | 2026-06-12
| MLCC-TRANSMIT-017705 | 2026-06-06 | MLCC-C0181-CIF-CDS-GEN-IRE-95002 | ICF Submission - DCP3 - Interface Control Form (ICF) for Concourse Slab - Grids 3 to 5 and Grids 21 to 23 Cutouts and Loadings Analysis ARC/STR/MEP/RSY – Iconic Station BG34 : MLCC-C0181-CIF-CDS-GEN-IRE-95002_Rev.C01 | C01 |  | OTH | CIF | CDS | 1 |  | DCP3 |  | PAJV-TRANSMIT-013685 | 2026-06-09
| MLCC-TRANSMIT-017704 | 2026-06-06 | MLCC-C0003-BES-NWW-CDS-PRC-00001 | Re: Procedure Submission - SOP – Standard Operating Procedure for Passage Operation Including FAS, CCTV & Operations (BR10 – Temporary Passenger Passage) : MLCC-C0003-BES-NWW-CDS-PRC-00001_Rev.C01 | C01 |  | PRC | BES | NWW | 1 | Mohsin Patel |  |  | PAJV-TRANSMIT-013804 | 2026-06-11
| MLCC-TRANSMIT-017703 | 2026-06-06 | DE.DPT.GN00.LDS.L0 | Package Submission - DCP2 - Al Ruwayyah Depot Landscape Design: DE.DPT.GN00.LDS.L0.D2_Rev C01 | C01 |  |  |  |  | 1 | Mike Lewey | DCP2
| MLCC-TRANSMIT-017702 | 2026-06-06 | MLCC-N0003-CIV-NWW-GEO-RPT-00278 | Report Submission - Pre-Construction Condition Survey Report for Centrepoint Metro Station : MLCC-N0003-CIV-NWW-GEO-RPT-00278_Rev.00 | 00 |  | RPT | CIV | NWW | 1 | Mazar Syed
| MLCC-TRANSMIT-017701 | 2026-06-06 | MLCC-N0003-CIV-NWW-GEO-RPT-00280 | Report Submission - Pre-Construction Condition Survey Report for Creek Metro Station : MLCC-N0003-CIV-NWW-GEO-RPT-00280_Rev.00 | 00 |  | RPT | CIV | NWW | 1 | Mazar Syed
| MLCC-TRANSMIT-017700 | 2026-06-06 | MLCC-N0003-CIV-NWW-GEO-RPT-00279 | Report Submission - Pre-Construction Condition Survey Report for Al Qusais Depot Building No.11 : MLCC-N0003-CIV-NWW-GEO-RPT-00279_Rev.00 | 00 |  | RPT | CIV | NWW | 1 | Mazar Syed
| MLCC-TRANSMIT-017699 | 2026-06-06 | DE.ZNE.ZN03.UTI.U2 | Package Submission - DCP2 - Z0042 (Creek Mainline) Utility Package : DE.ZNE.ZN03.UTI.U2.D2_Rev.C01 | C01 |  |  |  |  | 1 | Yazan Safieh | DCP2
| MLCC-TRANSMIT-017698 | 2026-06-06 | MLCC-C0206-BES-TVS-SYW-RPT-70000 | Re: Report Submission - DCP2 - BR08 Station - Tunnel Ventilation System CFD Report (DE.GEN.GN00.MEP.MF.D2) : MLCC-C0206-BES-TVS-SYW-RPT-70000-DCP2_Rev.C02 | C02 |  | RPT | BES | TVS | 1 | Ismaiel Salama | DCP2
| MLCC-TRANSMIT-017697 | 2026-06-06 |  | Re: Package Submission - DCP3 - Viaduct Foundation & Substructure-Stretch 07-BC-3SP-72-10B : DE.VDT.B10B.STR.V1.D3_Rev. C02 (Partial Submission) | [5 empty] | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017696 | 2026-06-06 |  | Package Submission - DCP2 - Power Supply (PDS) - Layout Plan And Section - BG34 Station : RLS.1.1.2.2.5_Rev.C01 (OBSOLETE)) | C01 |  |  |  |  | 1 | Sherif Zayed | DCP2
| MLCC-TRANSMIT-017695 | 2026-06-06 |  | Package Submission - DCP2 - Power Supply (PDS) - BIM Model - BR09 station : RLS.1.1.2.2.5_Rev.C01 (OBSOLETE)) | C01 |  |  |  |  | 1 | Sherif Zayed | DCP2
| MLCC-TRANSMIT-017694 | 2026-06-06 | MLCC-N0003-PDS-MPD-TRP-SPC-51000 | Specification Submission - DCP2 - Traction System Design Specification and System Architecture (RLS.1.1.2.2.2): MLCC-N0003-PDS-MPD-TRP-SPC-51000_Rev C04 | C04 |  | SPC | PDS | MPD | 1 |  | DCP2 |  | PAJV-TRANSMIT-013636 | 2026-06-08
| MLCC-TRANSMIT-017693 | 2026-06-06 | MLCC-C0003-ARC-PTW-GAR-DRW-10016 to 10023 | Re: Shop Drawing Submission - Rashidya Temporary Corridor Shop Drawings Doors & Tactile : MLCC-C0003-ARC-PTW-GAR-DRW-10016 to 10023_Rev.C03 | C03 |  | DRW | ARC | PTW | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017692 | 2026-06-06 | MLCC-N0003-QHS-QUM-GEN-PRC-00011 | Re: Procedure Submission - NCR- CAR Management Procedure : MLCC-N0003-QHS-QUM-GEN-PRC-00011_Rev.01 | 01 |  | PRC | QHS | QUM | 1 | Alister White
| MLCC-TRANSMIT-017691 | 2026-06-06 | MLCC-C0181-BES-NWW-CDS-RPT-70004 | Re: Report Submission - DCP2 - Station (BG34) - CFD Report for Fire Scenarios (DE.ELS.GE03.MEP.M4.D2) : MLCC-C0181-BES-NWW-CDS-RPT-70004_Rev.C02 | C02 |  | RPT | BES | NWW | 1 | Ismaiel Salama | DCP2
| MLCC-TRANSMIT-017690 | 2026-06-06 | MLCC-S0654-CIV-STN-GAR-DRW-13232 | Shop Drawing Submission - Station BG32 Wing Beam Grid-06 : MLCC-S0654-CIV-STN-GAR-DRW-13232 -13233,MLCC-S0654-CIV-STN-RFC-DRW-13211 - 13217,MLCC-S0654-CIV-STN-SSR-DRW-13006_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017689 | 2026-06-06 | MLCC-S0692-CIV-STN-GAR-DRW-13025 | Shop Drawing Submission - Station BG36 - Wing Beams along Grid-18 : MLCC-S0692-CIV-STN-GAR-DRW-13025, MLCC-S0692-CIV-STN-RFC-DRW-13067 - 13072,MLCC-S0692-CIV-STN-SSR-DRW-13013_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017688 | 2026-06-06 | MLCC-S0654-CIV-STN-GAR-DRW-13230 | Shop Drawing Submission - BG32- Shop drawing Wing Beam Grid-04 : MLCC-S0654-CIV-STN-GAR-DRW-13230,MLCC-S0654-CIV-STN-RFC-DRW-13199 - 13204,MLCC-S0654-CIV-STN-SSR-DRW-13004_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017687 | 2026-06-06 | MLCC-S0654-CIV-STN-GAR-DRW-13231 | Shop Drawing Submission - Station BG32 Wing Beam Grid-05 : MLCC-S0654-CIV-STN-GAR-DRW-13231,MLCC-S0654-CIV-STN-RFC-DRW-13205 - 13210,MLCC-S0654-CIV-STN-SSR-DRW-13005_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017686 | 2026-06-06 | MLCC-C0066-ARC-STN-GAR-DRW-10000 | Shop Drawing Submission - Creek G30 Temporary Scaffolding at Concourse and Platform Level : MLCC-C0066-ARC-STN-GAR-DRW-10000-10001_Rev.C01 | C01 |  | DRW | ARC | STN | 1 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017685 | 2026-06-06 | MLCC-N0003-CIV-VBR-GAR-RPT-00007 | Report Submission - Report For Bearing Access & Replacement Strategy (BG34 & BB03) : MLCC-N0003-CIV-VBR-GAR-RPT-00007_Rev.00 | 00 |  | RPT | CIV | VBR | 1 | Mahmoud Saad
| MLCC-TRANSMIT-017684 | 2026-06-06 | MLCC-N0003-PMC-PRC-SCH-SCH-00036 | Schedule Submission - 5 Weeks Lookahead dated 30-May-2026 : MLCC-N0003-PMC-PRC-SCH-SCH-00036_Rev.00 | 00 |  | OTH | PMC | PRC | 1 | Ahmed Ibrahim
| MLCC-TRANSMIT-017683 | 2026-06-06 | MLCC-S0654-CIV-STN-GAR-DRW-13229 | Shop Drawing Submission - Station BG32 Wing Beam Grid-03 : MLCC-S0654-CIV-STN-GAR-DRW-13229,MLCC-S0654-CIV-STN-RFC-DRW-13194 - 13198,MLCC-S0654-CIV-STN-SSR-DRW-13003_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017682 | 2026-06-06 | MLCC-C0204-BES-TVS-SYW-RPT-70000 | Re: Report Submission - BR09 Station - Tunnel Ventilation System CFD Report ( DE.GEN.GN00.MEP.MF.D2) : MLCC-C0204-BES-TVS-SYW-RPT-70000-DCP2_Rev.C02 | C02 |  | RPT | BES | TVS | 1 | Ismaiel Salama
| MLCC-TRANSMIT-017681 | 2026-06-06 | MLCC-S0709-CIV-STN-GAR-DRW-13012 | Shop Drawing Submission - Station BB06 Retaining Wall Waterproofing Comparment At Elevation (MLCC-S0709-CIV-STN-GAR-DRW-13012 - MLCC-S0709-CIV-STN-GAR-DRW-13022)_Rev.C01 | C01 |  | DRW | CIV | STN | 2 | Suresh Shetty |  |  | PAJV-TRANSMIT-013843 | 2026-06-12
| MLCC-TRANSMIT-017680 | 2026-06-06 | DE.ANX.AX17.ARC.A0 | Package Submission - DCP2 - Annex Structure - BL-EES08 Architecture : DE.ANX.AX17.ARC.A0.D2_Rev.C01 | C01 |  |  |  |  | 1 |  | DCP2
| MLCC-TRANSMIT-017679 | 2026-06-06 | DE.VDT.GN00.STR.01 | Re: Package Submission - DCP3 - Global - Viaduct Structure Superstructure Global 2SP PKG4 : DE.VDT.GN00.STR.01.D3_Rev.C03 | C03 |  |  |  |  | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017678 | 2026-06-06 | MLCC-S0654-CIV-STN-GAR-DRW-13228 | Shop Drawing Submission - Station BG32 Wing Beam Grid-02 : MLCC-S0654-CIV-STN-GAR-DRW-13228, MLCC-S0654-CIV-STN-RFC-DRW-13190 - 13193,MLCC-S0654-CIV-STN-SSR-DRW-13002_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017677 | 2026-06-06 | MLCC-S0654-CIV-STN-GAR-DRW-13227 | Shop Drawing Submission - Station BG32 Wing Beam Grid-01 : MLCC-S0654-CIV-STN-GAR-DRW-13227,MLCC-S0654-CIV-STN-RFC-DRW-13186 - 13189,MLCC-S0654-CIV-STN-SSR-DRW-13001_Rev.C01 | C01 |  | DRW | CIV | STN | 3 | Shahab Ahmad Khan
| MLCC-TRANSMIT-017676 | 2026-06-06 | MLCC-N0003-CIV-NWW-GEO-RPT-82454 | Report Submission - DCP3 - Technical Note-Dynamic Pile Load Test Viaduct Stretch 00 (PE-05-01) (DE.VDT.ST01.GEO.G1.D3) : MLCC-N0003-CIV-NWW-GEO-RPT-82454-DCP3_Rev.C01 | C01 |  | RPT | CIV | NWW | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017675 | 2026-06-06 | DE.VDT.ST07.STR.V2 | Package Submission - DCP3 - Stretch-07 - Viaduct Structure Pierhead 2SP Span : DE.VDT.ST07.STR.V2.D3_Rev.C01 | C01 |  |  |  |  | 1 | Mahmoud Saad | DCP3
| MLCC-TRANSMIT-017500 | 2026-06-03 | MLCC-C0201-CIF-CDS-GEN-IRE-95002 | ICF Submission - DCP2 - Interface Control Form (ICF) for Space proofing analysis DCP2 ARC/MEP - BR10 Stations : MLCC-C0201-CIF-CDS-GEN-IRE-95002_Rev.C01 | C01 | A | OTH | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013850 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017354 | 2026-05-25 | MLCC-S0800-CIV-STN-GAR-DRW-13000-13001,MLCC-S0800-CIV-STN-RFC-DRW-25000-25002 | Shop Drawing Submission - Station BR09 -Top Slab GA,CJ & lifting hook (MLCC-S0800-CIV-STN-GAR-DRW-13000-13001,MLCC-S0800-CIV-STN-RFC-DRW-25000-25002_Rev.C01 | C01 | A | DRW | CIV | STN | 5 | VAK |  |  | PAJV-TRANSMIT-013846 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016573 | 2026-05-12 | MLCC-N0003-ARC-STN-GAR-QUA-00004 | PQ Submission - Prequalification Submittal For Greenhawk : MLCC-N0003-ARC-STN-GAR-QUA-00004_Rev.00 | 00 | A | PQN | ARC | STN | 1 | LS |  |  | PAJV-TRANSMIT-013845 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016926 | 2026-05-18 | DE.TNL.CC02.STR.T2.D3 | Design Drawing Submission - DCP3 - Cut & Cover BB05 Slabs - (DE.TNL.CC02.STR.T2.D3) - Rev.C01 | C01 | A | DRW | CIV | CCV | 34 | MS | DCP 3 |  | PAJV-TRANSMIT-013732 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016815 | 2026-05-15 | MLCC-N0003-BES-DAW-DDS-MTS-00004 | Material Approval Request for Ductile Iron Trench/Channel Drain Grating "Crescent / MNG": MLCC-N0003-BES-DAW-DDS-MTS-00004_Rev.00 | 00 | A | MAT | MEP | DAW | 1 | AKR |  |  | PAJV-TRANSMIT-013839 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017303 | 2026-05-24 | MLCC-S0788-CIV-STN-PIR-DRW-11000 to 11005 | Re: Shop Drawing Submission - Station BR10 - Structure Pier - Type RCC1 to RCC3 & RCP1 to RCP3 Shop Drawing & BBS - MLCC-S0788-CIV-STN-PIR-DRW-11000 to 11006_Rev.C02 (RCS Resubmission) | C02 | C | DRW | CIV | STN | 6 | SAK |  |  | PAJV-TRANSMIT-013838 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017438 | 2026-06-01 | MLCC-S0788-CIV-STN-FND-DRW-11029 to 11043 | Re: Shop Drawing Submission - Station BR10 - Structure Foundation - Pile P5 - P12 Shop Drawing & BBS (Grid 10 to 12) : MLCC-S0788-CIV-STN-FND-DRW-11029 to 11043_Rev.C03 | C03 | C | DRW | CIV | STN | 15 | SAK |  |  | PAJV-TRANSMIT-013837 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017234 | 2026-05-23 | MLCC-N0003-BES-FPS-FFS-MST-00003 | Method Statement For Installation Of Valves And Supervisory Switches For Water-Based Fire Fighting Services : MLCC-N0003-BES-FPS-FFS-MST-00003_Rev.00 | 00 | A | MST | MEP | FPS | 1 | SAK |  |  | PAJV-TRANSMIT-013836 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017437 | 2026-06-01 | MLCC-N0003-PMC-SOH-GEN-PLN-00008 | Re: Plan Submission - HSE Responsibility & Accountability Plan : MLCC-N0003-PMC-SOH-GEN-PLN-00008_Rev.01 | 01 | B | PLN | PMC | SOH | 1 | LL |  |  | PAJV-TRANSMIT-013834 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017289 | 2026-05-23 | DE.ELS.GE10.MEP.M2.D2 | Re: Package Submission - DCP2 - Station BB04 - Water Supply, Drainage and Waste : DE.ELS.GE10.MEP.M2.D2_Rev.C02 | C02 | B | DRW | MEP | DAW | 69 | IS | DCP 2 |  | PAJV-TRANSMIT-013833 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017143 | 2026-05-22 | MLCC-N0003-CYB-NWW-SYW-QUA-00009 | Re: PQ Submission - Prequalification Submittal for Ansen Technology Co. Limited : MLCC-N0003-CYB-NWW-SYW-QUA-00009_Rev.01 | 01 | B | PQN | SYS | CYB | 1 | LS |  |  | PAJV-TRANSMIT-013832 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017262 | 2026-05-23 | DE.ELS.GE01.MEP.M3.D2 | Re: Package Submission - DCP2 - Elevated Station-MEP-BG32-FPS - MEP Fire Protection System FPS: DE.ELS.GE01.MEP.M3.D2_Rev.C01 (RCS Resubmission) | C01 | B | DRW | MEP | FPS | 38 | IS | DCP 2 |  | PAJV-TRANSMIT-013830 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017080 | 2026-05-20 | DE.ANX.AX01.STR.S0.D2 | Package Submission - DCP2 - Annex Structure - BL-EES09 : DE.ANX.AX01.STR.S0.D2_Rev.C01 | C01 | A | DRW | CIV | UTL | 32 | MS | DCP 2 |  | PAJV-TRANSMIT-013828 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017349 | 2026-05-25 | DE.ELS.GE03.GEO.G1.D3 | Re: Report Submission - DCP3 - Geotechnical Design Report for BG34 (DE.ELS.GE03.GEO.G1.D3) - MLCC-C0181-CIV-NWW-GEO-RPT-82203_Rev.C03 (RCS Resubmission) | C02 | E | RPT | CIV | UTL | 1 | MSD | DCP 3 |  | PAJV-TRANSMIT-013827 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017244 | 2026-05-23 | MLCC-N0003-CIV-NWW-GEO-RPT-82248 | Re: Report Submission - DCP3 - Geotechnical Design Report for Viaduct - Stretch 5.2 ( DE.VDT.ST05.GEO.G1.D3) : MLCC-N0003-CIV-NWW-GEO-RPT-82248_Rev.C03 | C03 | C | RPT | CIV | NWW | 1 | MSD | DCP 3 |  | PAJV-TRANSMIT-013826 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017496 | 2026-06-03 | DE.UGS.RE02.STR.S3.D3 | Re: Package Submission - DCP3 - Station BR08 - Structure Concourse Slab Level Submission : DE.UGS.RE02.STR.S3.D3_Rev.C03 | C03 | C | DRW | CIV | STN | 37 | DM | DCP 3 |  | PAJV-TRANSMIT-013825 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016711 | 2026-05-14 | MLCC-C0003-BES-ELE-SYW-QUA-00001 | Re: PQ Submission - Prequalification Submittal For FSIME International Safety & Fire Equipment L.L.C :MLCC-C0003-BES-ELE-SYW-QUA-00001_Rev.01 | 01 | B | PQN | MEP | ELE | 1 | LS |  |  | PAJV-TRANSMIT-013824 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017092 | 2026-05-21 | MLCC-S0054-PDS-MPD-MVN-ITP-00002 | ITP Submission - Inspection and Test Plan (ITP) For Temporary Rerouting and Termination of 33KV Cables: MLCC-S0054-PDS-MPD-MVN-ITP-00002_Rev.00 | 00 | A | ITP | SYS | PDS | 1 | SZ |  |  | PAJV-TRANSMIT-013823 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017199 | 2026-05-22 | MLCC-N0003-ENG-SSA-SAA-PLN-00002 | Re: Plan Submission - Software Development Management Plan : MLCC-N0003-ENG-SSA-SAA-PLN-00002_Rev.C04 | C04 | D | PLN | SAS | SSA | 1 | SAB |  |  | PAJV-TRANSMIT-013822 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017573 | 2026-06-04 | MLCC-N0003-PSD-NWW-SSA-RPT-51603 | Report Submission - DCP2 – Platform Screen Doors (PSD) – RAMS - SSHA Report (RLS.1.1.1.5.5) : MLCC-N0003-PSD-NWW-SSA-RPT-51603_Rev.C03 | C03 | C | RPT | SAS | PSD | 1 | SAB | DCP 2 |  | PAJV-TRANSMIT-013821 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017183 | 2026-05-22 | MLCC-N0003-BES-VAC-SYW-MST-00003 | Method Statement For Installation of Computer Room Air Conditioners (CRAC Units) with Ancillaries : MLCC-N0003-BES-VAC-SYW-MST-00003_Rev.00 | 00 | A | MST | MEP | VAC | 1 | SAK |  |  | PAJV-TRANSMIT-013820 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017188 | 2026-05-22 | DE.TPS.TPS1.MEP.M0.D2 | Package Submission - DCP2 - Al Ruwayyah Depot BDR19 - TPS - MEP : DE.TPS.TPS1.MEP.M0.D2_Rev.C01 | C01 | A | DRW | MEP | GEN | 104 | IS | DCP 2 |  | PAJV-TRANSMIT-013819 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017269 | 2026-05-23 | DE.DPT.OHBD.MEP.M0.D2 | Report Submission - DCP2 - Overhaul Workshop Building CFD Report For Fire Scenarios (DE.DPT.OHBD.MEP.M0.D2) : MLCC-S0765-BES-NWW-CDS-RPT-70000-DCP2_Rev.C01 | C01 | A | RPT | MEP | NWW | 1 | IS | DCP 2 |  | PAJV-TRANSMIT-013818 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017184 | 2026-05-22 | MLCC-C0181-BES-NWW-CDS-RPT-70000 | Re: Report Submission - DCP2 - Station BG34 - MEP Design Report (DE.ELS.GE03.MEP.M4.D2) : MLCC-C0181-BES-NWW-CDS-RPT-70000_Rev.C02 | C02 | B | RPT | MEP | NWW | 1 | IS | DCP 2 |  | PAJV-TRANSMIT-013817 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016219 | 2026-05-06 | MLCC-C0199-CIF-SIF-GEN-ICD-51212 | ICD Submission - DCP2 - Interface Control Documents for Depot Buildings and Facilities - Rail System : MLCC-C0199-CIF-SIF-GEN-ICD-51212_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013816 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016574 | 2026-05-12 | DE.ELS.GE06.ARC.A2.NC | NOC Drawing Submission - Station BG36 Entrance POD : DE.ELS.GE06.ARC.A2.NC_Rev.C01 | C01 | A | DRW | CIV | UTL | 21 | DM |  |  | PAJV-TRANSMIT-013815 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017087 | 2026-05-21 | MLCC-N0003-CIF-SIF-GEN-ICD-51507 | ICD Submission - ICD - Interface Control Document - Enhancement Civil Works / RTA Public Transport Agency: MLCC-N0003-CIF-SIF-GEN-ICD-51507_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT |  |  | PAJV-TRANSMIT-013814 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017041 | 2026-05-20 | MLCC-N0003-SIG-ATC-NWW-RPT-51615 | Report Submission - DCP2 -Signalling (ATC) - ATC System Requirements Specification (SRS) with DOORS Extract Report ( RLS.3.1.39) : MLCC-N0003-SIG-ATC-NWW-RPT-51615_Rev.C01 | C01 | A | RPT | SYS | ATC | 1 | KLI | DCP 2 |  | PAJV-TRANSMIT-013812 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017256 | 2026-05-23 | MLCC-N0003-CIV-NWW-GEO-RPT-82269 | Report Submission - DCP3 - Geotechnical Design Report For Viaduct- Stretch 9.1 (DE.VDT.ST09.GEO.G1.D3) : MLCC-N0003-CIV-NWW-GEO-RPT-82269-DCP3_Rev.C01 | C01 | A | RPT | CIV | NWW | 1 | MSD | DCP 3 |  | PAJV-TRANSMIT-013811 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016622 | 2026-05-13 | MLCC-C0201-BES-VAC-SYW-RPT-70001-DCP2 | Report Submission - DCP2 - Station (BR10) - CFD Report for Fire Scenarios : DE.ELS.RE00.MEP.M4.D2 : MLCC-C0201-BES-VAC-SYW-RPT-70001-DCP2_Rev C01 | C01 | A | RPT | MEP | VAC | 1 | IS | DCP 2 |  | PAJV-TRANSMIT-013809 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016646 | 2026-05-13 | MLCC-N0003-CIV-OCC-GAR-RPT-00001 | Re: Report Submission - Survey Report for Backup Operation Control Centre (BOCC) : MLCC-N0003-CIV-OCC-GAR-RPT-00001_Rev.C02 | C02 | B | RPT | CIV | OCC | 1 | GCP |  |  | PAJV-TRANSMIT-013808 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017468 | 2026-06-01 | MLCC-N0003-CIV-NWW-GEN-RPT-50045 | Report Submission - DCP1_MMUB (Annexes) Lightning Protection Design Report (LPS) (DE.MUUB.MUUB.STR.S0.D1) : MLCC-N0003-CIV-NWW-GEN-RPT-50045_Rev.C01 | C01 | A | RPT | CIV | NWW | 1 | OK | DCP 1 |  | PAJV-TRANSMIT-013807 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017144 | 2026-05-22 | DE.UGS.GE09.ARC.A2.D2 | Re: Package Submission - DCP2 - Station BB05 Underground Station Architecture : DE.UGS.GE09.ARC.A2.D2_Rev.C03 | C03 | C | DRW | ARC | STN | 60 | ML | DCP 2 |  | PAJV-TRANSMIT-013806 | 2026-06-12 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016963 | 2026-05-19 | MLCC-N0003-BES-ELE-LVD-MTS-00038 | Material Approval Request for Earthing Cables "Ducab/MNG": MLCC-N0003-BES-ELE-LVD-MTS-00038_Rev.00 | 00 | A | MAT | MEP | ELE | 1 | AKR |  |  | PAJV-TRANSMIT-013805 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016305 | 2026-05-07 | MLCC-N0003-CIV-TNL-GAR-RPT-00008 | Report Submission - Technical Note on Cutter Head Intervention- TN07 : MLCC-N0003-CIV-TNL-GAR-RPT-00008_Rev.C01 | C01 | A | RPT | CIV | TNL | 9 | EZ |  |  | PAJV-TRANSMIT-013803 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016737 | 2026-05-14 | MLCC-N0003-BES-DAW-SWG-MTS-00005 | Material Approval Request for Gully Trap "Well Fit/ MNG": MLCC-N0003-BES-DAW-SWG-MTS-00005_Rev.00 | 00 | A | MAT | MEP | DAW | 1 | AKR |  |  | PAJV-TRANSMIT-013801 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017267 | 2026-05-23 | MLCC-S0681-CIV-VBR-FND-DRW-13004 to 13015 | Re: Shop Drawing Submission - Stretch 04.2 - Viaduct Structure Foundation Pile Shop Drawing & BBS PM103 to PM113 - MLCC-S0681-CIV-VBR-FND-DRW-13004 to 13015_Rev.C02 | C02 | B | DRW | CIV | VBR | 12 | AKM |  |  | PAJV-TRANSMIT-013800 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016647 | 2026-05-13 | MLCC-S0647-CIV-STN-PIR-DRW-13008-13019, 13021-13025 | Re: Shop Drawing Submission - Station BG31-RCC & Wall : MLCC-S0647-CIV-STN-PIR-DRW-13008-13019, 13021-13025_Rev.C02 | C02 | B | DRW | CIV | STN | 21 | SAK |  |  | PAJV-TRANSMIT-013799 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016598 | 2026-05-12 | MLCC-N0003-ARC-STN-GAR-MST-00002 | Method Statement For Gypsum Board Ceiling Installation : MLCC-N0003-ARC-STN-GAR-MST-00002_Rev.00 | 00 | A | MST | ARC | STN | 1 | SAK |  |  | PAJV-TRANSMIT-013798 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017181 | 2026-05-22 | MLCC-S0300-BES-ESC-SYW-MST-00001 | Method Statement For Dismantling and Installation of Escalators 1 to 4 at Creek station G030 : MLCC-S0300-BES-ESC-SYW-MST-00001_Rev.00 | C01 | A | MST | MEP | ESC | 9 | SAK |  |  | PAJV-TRANSMIT-013797 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017424 | 2026-05-27 | MLCC-S0673-CIV-VBR-2SP-DRW-84301 - 84306, 84308 - 84310, 84316 and 84318 | Shop Drawing Submission - Stretch-03 - Viaduct Structure Twin Span-Superstructure Shop Drawing Span-96 & 97: MLCC-S0673-CIV-VBR-2SP-DRW-84301 - 84306, 84308 - 84310, 84316 and 84318_Rev.C01 | C01 | A | DRW | CIV | VBR | 11 | AK |  |  | PAJV-TRANSMIT-013796 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016793 | 2026-05-15 | DE.VDT.ST02.STR.V2.D3 | Package Submission - DCP3 - Stretch 02 - Viaduct Structure Bearing Schedule BC-3SP-72-02 : DE.VDT.ST02.STR.V2.D3_Rev.C01 | C01 | A | DRW | CIV | VBR | 5 | MS | DCP 3 |  | PAJV-TRANSMIT-013731 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017557 | 2026-06-03 | DE.ZNE.ZN06.ARD.R0.D2 | Re: Package Submission - DCP2 - Zone 06 Roads Z0046 Package : DE.ZNE.ZN06.ARD.R0.D2_Rev.C01 (RCS Resubmission) | C01 | B | DRW | CIV | RAR | 99 | SJ | DCP 2 |  | PAJV-TRANSMIT-013791 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017254 | 2026-05-23 | DE.ELS.GE11.STR.S7.D3 | Package Submission - DCP3 - Station BB03 - Structure Steel - Footbridge : DE.ELS.GE11.STR.S7.D3_Rev.C01 | C01 | A | DRW | CIV | PTW | 31 | DM | DCP 3 |  | PAJV-TRANSMIT-013789 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017128 | 2026-05-21 | MLCC-N0003-CIV-NWW-GAR-MTS-00234 | Re: Material Approval Request for Epoxy Anchors RE-500V4, RE-100HC "HILTI": MLCC-N0003-CIV-NWW-GAR-MTS-00234_Rev.01 | 01 | B | MAT | CIV | NWW | 1 | AKR |  |  | PAJV-TRANSMIT-013788 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016671 | 2026-05-13 | MLCC-Z0015-CIV-NWW-GAR-MTS-00002 | Material Approval Request for 10-Ton Stainless Steel Bollard "Flowline Mechanical Engineering/BVA": MLCC-Z0015-CIV-NWW-GAR-MTS-00002_Rev.00 | 00 | A | MAT | CIV | NWW | 1 | AKR |  |  | PAJV-TRANSMIT-013787 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017096 | 2026-05-21 | MLCC-N0003-CIF-SIF-GEN-ICD-51176 | ICD Submission - DCP2 - Interface Control Document (ICD) - Viaduct Stretches 05.1-09.2 Civil Works / Stakeholders : MLCC-N0003-CIF-SIF-GEN-ICD-51176_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013786 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017036 | 2026-05-20 | MLCC-N0003-CIF-SIF-GEN-ICD-51165 | ICD Submission - DCP2 - Interface Control Document (ICD) BG32 Dubai Creek Harbour 1 Station – Civil Works / Stakeholders : MLCC-N0003-CIF-SIF-GEN-ICD-51165_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013785 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017037 | 2026-05-20 | MLCC-N0003-CIF-SIF-GEN-ICD-51167 | ICD Submission - DCP2 - Interface Control Document (ICD) BG33 Dubai Creek Harbour 2 Provisional Station – Civil Works / Stakeholders : MLCC-N0003-CIF-SIF-GEN-ICD-51167_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013784 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017083 | 2026-05-20 | DE.ELS.GE03.STR.S1.D3 | Re: Package Submission - DCP3 - Station BG34 - (GLE03) Structural : DE.ELS.GE03.STR.S1.D3_Rev.C05 (Partial Submission) | C05 | C | DRW | CIV | STN | 30 | DM | DCP 3 |  | PAJV-TRANSMIT-013783 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017245 | 2026-05-23 | DE.ELS.GE03.STR.S3.D2 | Re: Package Submission - DCP2 - Stations BG34 (GLE03) - Structure : DE.ELS.GE03.STR.S3.D2_Rev.C01 (RCS Resubmission) | C01 | B | DRW | CIV | GEN | 138 | DM | DCP 2 |  | PAJV-TRANSMIT-013782 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016816 | 2026-05-15 | MLCC-N0003-CIV-TNL-SYW-MTS-00048 | Material Approval Request - Technical Submittal for C40/50 - For Tunnel lining,Invert, & Plenum (Mix Code : M5023, M5023R) 45% OPC + 50% GGBS + 5% MS "Emirates Beton": MLCC-N0003-CIV-TNL-SYW-MTS-00048_Rev.00 | 00 | A | MAT | CIV | TNL | 1 | AKR |  |  | PAJV-TRANSMIT-013781 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016736 | 2026-05-14 | MLCC-N0003-BES-TVS-DCT-MTS-00001 | Material Approval Request for OTE & UPE Duct & Accessories "CVS/MNG": MLCC-N0003-BES-TVS-DCT-MTS-00001_Rev.00 | 00 | A | MAT | MEP | TVS | 1 | AKR |  |  | PAJV-TRANSMIT-013780 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016670 | 2026-05-13 | MLCC-Z0015-CIV-NWW-GAR-MTS-00001 | Material Approval Request for Expanded Polystrene "Styrene Insulation/BVA": MLCC-Z0015-CIV-NWW-GAR-MTS-00001_Rev.00 | 00 | A | MAT | CIV | NWW | 1 | AKR |  |  | PAJV-TRANSMIT-013779 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016738 | 2026-05-14 | MLCC-N0003-BES-DAW-DDS-MTS-00006 | Material Approval Request for Rainwater System Outlets "Watts/ MNG": MLCC-N0003-BES-DAW-DDS-MTS-00006_Rev.00 | 00 | A | MAT | MEP | DAW | 1 | AKR |  |  | PAJV-TRANSMIT-013778 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016757 | 2026-05-14 | MLCC-Z0045-BES-ELE-LVD-ITP-00001 | Re: ITP Submission - Inspection and Test Plan For T & C of Electrical Panels (Rashidiya Station – Temporary Pedestrian Passage) : MLCC-Z0045-BES-ELE-LVD-ITP-00001_Rev.01 | 01 | B | ITP | MEP | ELE | 1 | IS |  |  | PAJV-TRANSMIT-013777 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017497 | 2026-06-03 | MLCC-S0810-CIV-STN-RFC-DRW-13838-13856 | Shop Drawing Submission - Station BR08 - Structure Pour-C7 Concourse Slab : MLCC-S0810-CIV-STN-RFC-DRW-13838-13856_Rev.C01 | C01 | A | DRW | CIV | STN | 1 | VAK |  |  | PAJV-TRANSMIT-013774 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017530 | 2026-06-03 | MLCC-S0709-CIV-STN-FND-DRW-13142-13148 | Shop Drawing Submission - Station BB06 Base Slab Pour 22 Reinforcement : MLCC-S0709-CIV-STN-FND-DRW-13142-13148_Rev.C01 | C01 | A | DRW | CIV | STN | 7 | SSY |  |  | PAJV-TRANSMIT-013773 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017091 | 2026-05-21 | MLCC-N0003-BES-VAC-CHW-MST-00003 | Method Statement For Installation of Plate Type Heat Exchanger For Chilled Water System : MLCC-N0003-BES-VAC-CHW-MST-00003_Rev.00 | 00 | A | MST | MEP | VAC | 1 | SAK |  |  | PAJV-TRANSMIT-013770 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017465 | 2026-06-01 | MLCC-N0003-CIV-NWW-GEN-RPT-50020&MLCC-N0003-CIV-NWW-GEN-RPT-50021 | Re: Report Submission - DCP1_EEP1 - Lightning Protection Report (LPS) (DE.EEP.EEP1.STR.S0.D1) : MLCC-N0003-CIV-NWW-GEN-RPT-50020&MLCC-N0003-CIV-NWW-GEN-RPT-50021_Rev.C02 | C02 | B | RPT | CIV | NWW | 2 | OK | DCP 1 |  | PAJV-TRANSMIT-013769 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016777 | 2026-05-15 | MLCC-N0003-BES-FPS-FFS-RPT-70000-DCP2 | Report Submission - DCP2 - Fire Life Safety (FLS) – Technical Note Convergence of Means of Egress in Stations ( DE.GEN.GN00.MEP.M8.D2) : MLCC-N0003-BES-FPS-FFS-RPT-70000-DCP2_Rev.C01 | C01 | A | RPT | MEP | FPS | 1 | IS | DCP 2 |  | PAJV-TRANSMIT-013768 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017469 | 2026-06-01 | MLCC-N0003-CIV-NWW-GEN-RPT-50046 | Report Submission - DCP1_BL-EES06 - Lightning Protection Risk Assessment (LPS) (DE.ANX.AX15.STR.S0.D1) : MLCC-N0003-CIV-NWW-GEN-RPT-50046_Rev.C01 | C01 | A | RPT | CIV | NWW | 1 | OK | DCP 1 |  | PAJV-TRANSMIT-013767 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017016 | 2026-05-20 | DE.DPT.STBD.STR.S0.D3 | Re: Package Submission - DCP3 - Depot BDR01- Stabling Building Structure : DE.DPT.STBD.STR.S0.D3_Rev.C03 | C03 | C | DRW | CIV | DBF | 105 | DM | DCP 3 |  | PAJV-TRANSMIT-013766 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017371 | 2026-05-26 | DE.ELS.GE03.GEO.G1.D3 | Re: Package Submission - DCP3 - Geotechnical - Technical Note-Working Pile Load Test at BG34 (GLE03) (SOP-65 and SOP-154): DE.ELS.GE03.GEO.G1.D3_Rev C04 | C04 | D | DRW | CIV | NWW | 4 | MSD | DCP 3 |  | PAJV-TRANSMIT-013765 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017158 | 2026-05-22 | MLCC-S0810-CIV-STN-RFC-FCR-00005 | FCR Submission - Field Change and Drawing Modification Request (FCR) for BR08-Concourse slab congestion of rebars around concrete King post and cutouts : MLCC-S0810-CIV-STN-RFC-FCR-00005_Rev.C01 | C01 | A | OTH | CIV | STN | 1 | DM |  |  | PAJV-TRANSMIT-013763 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017243 | 2026-05-23 | DE.VDT.ST04.GEO.G1.D3 | Report Submission - DCP3 - Geotechnical Design Report for Viaduct - Stretch 4 Balanced Cantilever Pier PM-95,96,97,98 : DE.VDT.ST04.GEO.G1.D3_Rev.C01 | C01 | A | RPT | CIV | NWW | 1 | MSD | DCP 3 |  | PAJV-TRANSMIT-013762 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-016809 | 2026-05-15 | DE.UGS.RE01.STR.S7.D3 | Re: Package Submission - DCP3 - Station BR09 - Structure D-Wall Ancillary 02 : DE.UGS.RE01.STR.S7.D3_Rev.C02 | C02 | B | DRW | CIV | EPD | 30 | DM | DCP 3 |  | PAJV-TRANSMIT-013761 | 2026-06-11 |  |  | Under Review | Under Review
| MLCC-TRANSMIT-017052 | 2026-05-20 | MLCC-C0003-BES-FPS-SYW-RPT-00001 | Re: Report Submission - Fire Life Safety (FLS) Report for Pedestrian Passage-Rashidiya Station : MLCC-C0003-BES-FPS-SYW-RPT-00001_Rev.C04 | C04 | D | RPT | MEP | FPS | 1 | IS |  |  | PAJV-TRANSMIT-013760 | 2026-06-10 |  |  | SONO | SONO
| MLCC-TRANSMIT-016903 | 2026-05-18 | MLCC-C0199-DEP-LHE-BGH-SPC-51063 | Specification Submission - DCP2 - Depot Equipment (DEP) - AD01, Bogie Lifting Equipment Preliminary Technical Specification (RLS.1.1.6.6.2.2) : MLCC-C0199-DEP-LHE-BGH-SPC-51063_Rev C03 | C03 | C | RPT | SYS | DEP | 1 | DAD | DCP 2 |  | PAJV-TRANSMIT-013759 | 2026-06-10 |  |  | SONO | SONO
| MLCC-TRANSMIT-014874 | 2026-04-10 | MLCC-C0199-DEP-WKE-MEF-SPC-51071 | Re: Specification Submission - DCP2 - Depot Equipment (DEP) - AD09 Frame Turnover Machine Preliminary Technical Specification (RLS.1.1.6.6.2.2) : MLCC-C0199-DEP-WKE-MEF-SPC-51071_Rev.C02 |  |  |  | SYS | DEP | 1 | DAD | DCP 2 |  | PAJV-TRANSMIT-013758 | 2026-06-10 | [9 empty] | withdrawn by MLCC confimed by DAD
| MLCC-TRANSMIT-016673 | 2026-05-13 | MLCC-N0003-CIV-STN-SSR-MTS-00008 | Material Approval Request for Structural Hollow Sections (SHS/RHS/EHS/CHS-Grade S3SSJOH) "Embosal Steel Mill LLC / Assent Steel": MLCC-N0003-CIV-STN-SSR-MTS-00008_Rev.00 | 00 | A | MAT | CIV | STN | 1 | AKR |  |  | PAJV-TRANSMIT-013757 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016459 | 2026-05-11 | DE.VDT.ST02.STR.V3.D3 | Package Submission - DCP3 - Stretch-02 - Viaduct Structure Balanced Cantilever (BC-3SP-72-02) Superstructure : DE.VDT.ST02.STR.V3.D3_Rev.C01 | C01 | A | DRW | CIV | VBR | 20 | MS | DCP 3 |  | PAJV-TRANSMIT-013756 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017280 | 2026-05-23 | MLCC-S0731-CIV-STN-RFC-FCR-00001 | FCR Submission - Field Change and Drawing Modification Request for Misalignment of rebars Wing Beams Station BB04 : MLCC-S0731-CIV-STN-RFC-FCR-00001_Rev.C01 | C01 | A | OTH | CIV | STN | 1 | DM |  |  | PAJV-TRANSMIT-013755 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016983 | 2026-05-19 | DE.VDT.ST51.STR.V2.D3 | Package Submission - DCP3-Stretch 05.1-Viaduct Structure Bearing Schedule ISO & 2SP Span:DE.VDT.ST51.STR.V2.D3_Rev.C01 | C01 | A | DRW | CIV | VBR | 7 | MS | DCP 3 |  | PAJV-TRANSMIT-013754 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017242 | 2026-05-23 | MLCC-S0764-CIV-NWW-GEO-RPT-82227 | Re: Report Submission - DCP3 - Geotechnical Design Report for Inspection Tracks Building (DE.DPT.GN00.GEO.G0.D3) : MLCC-S0764-CIV-NWW-GEO-RPT-82227-DCP3_Rev.C02 | C02 | B | RPT | CIV | NWW | 1 | MSD | DCP 3 |  | PAJV-TRANSMIT-013753 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016735 | 2026-05-14 | MLCC-N0003-CIV-NWW-GAR-MTS-00276 | Material Approval Request for Binding Wire "Hebei Shaoman International Trade Co / Perfect Advanced": MLCC-N0003-CIV-NWW-GAR-MTS-00276_Rev.00 | 00 | A | MAT | CIV | NWW | 1 | AKR |  |  | PAJV-TRANSMIT-013752 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017318 | 2026-05-25 | MLCC-N0003-CIV-NWW-GEO-RPT-82214-DCP3_ | Re: Report Submission - DCP3 - Geotechnical Design Report For Viaduct- Stretch 1 (PS-13 to PM-16) (DE.VDT.ST01.GEO.G1.D3) : MLCC-N0003-CIV-NWW-GEO-RPT-82214-DCP3_Rev.C03 | C03 | C | RPT | CIV | NWW | 1 | MSD | DCP 3 |  | PAJV-TRANSMIT-013751 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017265 | 2026-05-23 | MLCC-Z0039-CIV-NWW-GAR-RPT-00002 | Report Submission - Dubai Metro Blue Line Project Dubai Creek Crossing - Preliminary Provisional Impressed Current Cathodic Protection (ICCP) Design Report For Pile Cap & Pier : MLCC-Z0039-CIV-NWW-GAR-RPT-00002_Rev.C01 | C01 | A | RPT | CIV | NWW | 1 | OK |  |  | PAJV-TRANSMIT-013750 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016460 | 2026-05-11 | DE.VDT.ST02.STR.V3.D3 | Package Submission - DCP3 - Stretch-02 - Viaduct Structure Balanced Cantilever (BC-3SP-72-03) Superstructure -: DE.VDT.ST02.STR.V3.D3_Rev.C01 | C01 | A | DRW | CIV | VBR | 20 | MS | DCP 3 |  | PAJV-TRANSMIT-013749 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017073 | 2026-05-20 | MLCC-S0692-CIV-STN-PIR-FCR-00001 | FCR Submission - Field Change and Drawing Modification Request (FCR) for BG36 Elevated stations - Spine/Wing beam Intersection (Grid-16 to 20) : MLCC-S0692-CIV-STN-PIR-FCR-00001_Rev.C01 | C01 | A | FCR | CIV | STN | 1 | DM |  |  | PAJV-TRANSMIT-013748 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017570 | 2026-06-04 | MLCC-N0003-PSD-NWW-SSA-PLN-51612 | Plan Submission - DCP2 - Platform Screen Doors (PSD) - RAMS - Software Validation Plan (RLS.1.1.1.5.5) : MLCC-N0003-PSD-NWW-SSA-PLN-51612_Rev.C03 | C03 | C | PLN | SAS | PSD | 1 | SAB | DCP 2 |  | PAJV-TRANSMIT-013747 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016993 | 2026-05-19 | RLS.1.1.6.5.2 | Package Submission - DCP2 - Depot Equipment (DEP) - Ground Floor Level Equipment Layout - Yellow Plant workshop : RLS.1.1.6.5.2_Rev.C02 | C02 | B | DRW | SYS | DEP | 5 | DAD | DCP 2 |  | PAJV-TRANSMIT-013746 | 2026-06-10 |  |  | SONO | SONO
| MLCC-TRANSMIT-016516 | 2026-05-11 | DE.VDT.ST42.STR.V3.D3 | Package Submission - DCP3 - Stretch-04.1 - Viaduct Structure Superstructure 2SP Spans Part 2 : DE.VDT.ST42.STR.V3.D3_Rev.C01 | C01 | A | DRW | CIV | VBR | 9 | MS | DCP 3 |  | PAJV-TRANSMIT-013744 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016918 | 2026-05-18 | DE.ELS.GE11.STR.S9.D3 | Package Submission - DCP3 - Station BB03 - Structural (CHILLER YARD): DE.ELS.GE11.STR.S9.D3_Rev.C01 | C01 | A | DRW | CIV | STN | 24 | DM | DCP 3 |  | PAJV-TRANSMIT-013743 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017164 | 2026-05-22 | MLCC-S0675-CIV-STN-GAR-RPT-26001 | Report Submission - Design Calculation for Wall Formwork and Working Platform at BG34 Station : MLCC-S0675-CIV-STN-GAR-RPT-26001_Rev.C01 | C01 | A | RPT | CIV | STN | 1 | DM |  |  | PAJV-TRANSMIT-013742 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016927 | 2026-05-19 | MLCC-N0003-ENG-ASM-GEN-SPC-00002 | Re: Specification Submission - Maintenance Management System (MMS) Location and Asset Data Specification : MLCC-N0003-ENG-ASM-GEN-SPC-00002_Rev.C02 | C02 | B | SPC | SYS | ASM | 1 | NRA |  |  | PAJV-TRANSMIT-013741 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017168 | 2026-05-22 | MLCC-N0003-ENG-ASM-GEN-SPC-00001 | Re: Specification Submission - Maintenance Management System (MMS) Master Data Specification : MLCC-N0003-ENG-ASM-GEN-SPC-00001_Rev.C02 | C02 | B | SPC | SYS | ASM | 1 | NRA |  |  | PAJV-TRANSMIT-013740 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016616 | 2026-05-13 | MLCC-S0820-CIV-STN-RFC-FCR-00008 | Re: FCR Submission - Field Change Request for BR07 Station - Concourse Slab Waler Beam Concrete Grade: MLCC-S0820-CIV-STN-RFC-FCR-00008_Rev.C02 | C02 | B | OTH | CIV | STN | 1 | DM |  |  | PAJV-TRANSMIT-013739 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016795 | 2026-05-15 | MLCC-S0709-CIV-STN-FND-FCR-00002 | FCR Submission - Field Change and Drawing Modification Request (FCR) for BB06 Pile Area Congestion : MLCC-S0709-CIV-STN-FND-FCR-00002_Rev.C01 | C01 | A | OTH | CIV | STN | 1 | DM |  |  | PAJV-TRANSMIT-013738 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-012320 | 2026-02-05 | DE.ELS.GE00.LDS.L2.D1 | Re: Package Submission - DCP1 - BG31 Creek Interchange Station – Landscape Package DE.ELS.GE00.LDS.L2.D1_Rev.C01 (RCS Resubmission) | C02 | B | DRW | ARC | LSC | 23 | ML | DCP 1 |  | PAJV-TRANSMIT-013737 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016879 | 2026-05-18 | MLCC-N0003-PMC-CSV-GEN-PLN-00001 | Re: Plan Submission - Obsolescence Management Plan : MLCC-N0003-PMC-CSV-GEN-PLN-00001_Rev.C03 | C03 | C | PLN | PMC | CSV | 1 | MP |  |  | PAJV-TRANSMIT-013736 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017279 | 2026-05-23 | MLCC-S0692-CIV-STN-FND-FCR-00001 | FCR Submission - Field Change and Drawing Modification Request (FCR) for BG36 Elevated station – Site modifications in PC6 and Pile P10 (SOP 54) : MLCC-S0692-CIV-STN-FND-FCR-00001_Rev.C01 | C01 | A | OTH | CIV | STN | 1 | DM |  |  | PAJV-TRANSMIT-013735 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017064 | 2026-05-20 | MLCC-C0196-CIV-STN-GAR-CAL-00003 | Calculation Submission - Extension Calculation for BB03 Concourse Level Wing Beam (Grid 9) : MLCC-C0196-CIV-STN-GAR-CAL-00003_Rev.C01 | C01 | A | CAL | CIV | STN | 1 | DM |  |  | PAJV-TRANSMIT-013734 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016948 | 2026-05-19 | DE.ANX.AX14.STR.S0.D1 | Package Submission - DCP1 - Annex Structure - BL-EES05 Structure Structure Design : DE.ANX.AX14.STR.S0.D1_Rev.C01 | C01 | A | DRW | CIV | ARO | 34 | MS | DCP 1 |  | PAJV-TRANSMIT-013733 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016633 | 2026-05-13 | DE.ANX.AX15.STR.S1.D3 | Package Submission - DCP3 - Annex Structure - BL-EES06 Structure Slabs : DE.ANX.AX15.STR.S1.D3_Rev.C01 | C01 | A | DRW | CIV | EES | 40 | MS | DCP 3 |  | PAJV-TRANSMIT-013730 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016656 | 2026-05-13 | DE.VDT.ST05.STR.V1.D3 | Re: Package Submission - DCP3 - Viaduct Structure Foundation & Substructure-STRETCH 5.1-BC-3SP-72-07 : DE.VDT.ST05.STR.V1.D3_Rev.C03 | C03 | B | DRW | CIV | VBR | 10 | MS | DCP 3 |  | PAJV-TRANSMIT-013729 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017529 | 2026-06-03 | MLCC-C0204-CIF-CDS-GEN-IRE-95005 | Re: ICF Submission - Interface Control Form for Top Slab STR/MEP - BR09 Station: MLCC-C0204-CIF-CDS-GEN-IRE-95005_Rev.C01 (RCS Resubmission) | C01 | B | OTH | PMC | CIF | 1 | RT |  |  | PAJV-TRANSMIT-013728 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016725 | 2026-05-14 | MLCC-C0174-CIV-STN-SYW-DRW-13000-13001 | Shop Drawing Submission - BG31 Wall, Column, Foundations & Substructure Shop Drawing For Typical Details Of Waterproofing : MLCC-C0174-CIV-STN-SYW-DRW-13000-13001_Rev.C01 | C01 | A | DRW | CIV | STN | 2 | SAK |  |  | PAJV-TRANSMIT-013727 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016019 | 2026-05-01 | MLCC-N0003-CIV-VBR-PIR-FCR-00008 | FCR Submission - Field Change and Drawing Modification Request (FCR) for Viaduct Structure - Pier Head PM 150 : MLCC-N0003-CIV-VBR-PIR-FCR-00008_Rev.C01 | C01 | A | OTH | CIV | VBR | 1 | AK |  |  | PAJV-TRANSMIT-013726 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017266 | 2026-05-23 | MLCC-N0003-CIV-NWW-GEO-RPT-82262 | Re: Report Submission - DCP3 - Geotechnical Design Report for Viaduct - Stretch 4 (PM-100 to PM-113) - ( DE.VDT.ST04.GEO.G1.D3) - MLCC-N0003-CIV-NWW-GEO-RPT-82262-DCP3 - Rev.C02 | C02 | B | RPT | CIV | NWW | 1 | MSD | DCP 3 |  | PAJV-TRANSMIT-013725 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017217 | 2026-05-23 | DE.ELS.GE00.STR.S1.D3 | Package Submission - DCP3 - Station BG31 - Structural - BL Technical Level (Precast M-Girder) - DE.ELS.GE00.STR.S1.D3_Rev C01 | C01 | A | DRW | CIV | STN | 15 | DM | DCP 3 |  | PAJV-TRANSMIT-013724 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016832 | 2026-05-16 | DE.UGS.RE01.STR.S5.D3 | Package Submission - DCP3 - Station BR09 - Structure Base Slab : DE.UGS.RE01.STR.S5.D3_Rev.C01 | C01 | A | DRW | CIV | STN | 29 | DM | DCP 3 |  | PAJV-TRANSMIT-013723 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016971 | 2026-05-19 | DE.VDT.ST03.STR.V2.D3 | Re: Package Submission - DCP3 - Stretch 03 Viaduct Structure Pierhead-Stretch 03-BC-3SP-72-04: DE.VDT.ST03.STR.V2.D3_Rev.C02 | C02 | B | DRW | CIV | VBR | 6 | MS | DCP 3 |  | PAJV-TRANSMIT-013722 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017572 | 2026-06-04 | MLCC-N0003-PSD-NWW-SSA-RPT-51606 | Report Submission - DCP2 - Platform Screen Doors (PSD) – RAMS - Failure Modes, Effects and Criticality Analysis (FMECA) Report (PSD_RLS.1.1.1.5.5) : MLCC-N0003-PSD-NWW-SSA-RPT-51606_Rev.C03 | C03 | C | RPT | SAS | PSD | 1 | SAB | DCP 2 |  | PAJV-TRANSMIT-013720 | 2026-06-10 |  |  | SONO | SONO
| MLCC-TRANSMIT-016677 | 2026-05-13 | MLCC-N0003-CIF-SIF-GEN-ICD-51179 | ICD Submission - DCP2 - Interface Control Document ICD - Annexes 01-17 Civil Works / Stakeholders : MLCC-N0003-CIF-SIF-GEN-ICD-51179_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013719 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016664 | 2026-05-13 | MLCC-N0003-CIF-SIF-GEN-ICD-51178 | ICD Submission - DCP2 - Interface Control Document ICD - Tunnel 1A-3B Civil Works / Stakeholder : MLCC-N0003-CIF-SIF-GEN-ICD-51178_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013718 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016615 | 2026-05-12 | MLCC-N0003-CIF-SIF-GEN-ICD-51172 | ICD Submission - DCP2 - Interface Control Document ICD BR09 Mirdiff City Center Station - Civil/ Stakeholders : MLCC-N0003-CIF-SIF-GEN-ICD-51172_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013717 | 2026-06-10 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017002 | 2026-05-19 | MLCC-N0003-CIF-SIF-GEN-ICD-51221 | Re: ICD Submission - Interface Control Document for PWA-ATC: MLCC-N0003-CIF-SIF-GEN-ICD-51221_Rev.C02 | C02 | B | ICD | PMC | CIF | 1 | RT |  |  | PAJV-TRANSMIT-013716 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016814 | 2026-05-15 | DE.VDT.GN00.STR.01.D3 | Re: Package Submission - DCP3 - Global - Viaduct Structure ISO PKG-2 : DE.VDT.GN00.STR.01.D3_Rev.C03 | C03 | D | DRW | CIV | VBR | 27 | MS | DCP 3 |  | PAJV-TRANSMIT-013715 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017119 | 2026-05-21 | DE.UGS.RE01.MEP.M3.D2 | Re: Package Submission - DCP2 – Underground Station – BR09 Fire Protection System : DE.UGS.RE01.MEP.M3.D2_Rev.C01 (RCS Submission) | C01 | C | DRW | MEP | FPS | 41 | IS | DCP 2 |  | PAJV-TRANSMIT-013714 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017049 | 2026-05-20 | MLCC-N0003-TRW-PWA-TRL-RPT-81004 | Re: Report Submission - DCP2 - Routewide Contact Rail System Component Drawing (DE.TNL.GN00.TWK.P1.D2) : MLCC-N0003-TRW-PWA-TRL-RPT-81004_Rev.C02 | C02 | B | RPT | CIV | TRW | 1 | JP | DCP 2 |  | PAJV-TRANSMIT-013713 | 2026-06-10 |  |  | SONO | SONO
| MLCC-TRANSMIT-017050 | 2026-05-20 | MLCC-N0003-TRW-PWA-TRL-SPC-81000-DCP2 | Re: Specification Submission - Routewide Contact Rail System Technical Specification (DE.TNL.GN00.TWK.P1.D2) : MLCC-N0003-TRW-PWA-TRL-SPC-81000-DCP2_Rev.C02 | C02 | B | SPC | CIV | TRW | 1 | JP | DCP 2 |  | PAJV-TRANSMIT-013712 | 2026-06-10 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016745 | 2026-05-14 | MLCC-C0003-ARC-PTW-GAR-ITP-00004 | ITP Submission - Inspection and Test Plan (ITP) For Signage, Tactile, Fire Escape and Automatic Doors at Rashidiya Temporary Passegeway : MLCC-C0003-ARC-PTW-GAR-ITP-00004_Rev.00 | 00 | A | ITP | ARC | PTW | 1 | SAK |  |  | PAJV-TRANSMIT-013711 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017097 | 2026-05-21 | MLCC-N0003-CIF-SIF-GEN-ICD-51177 | ICD Submission - DCP2 - Interface Control Document (ICD) Viaduct Stretches 06.2-07 Civil Works / Stakeholders : MLCC-N0003-CIF-SIF-GEN-ICD-51177_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013710 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017109 | 2026-05-21 | MLCC-N0003-CIF-SIF-GEN-ICD-51170 | ICD Submission - DCP2 - Interface Control Document (ICD) BB06 Dubai International City Interchange Station – Civil Works / Stakeholders : MLCC-N0003-CIF-SIF-GEN-ICD-51170_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013709 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016761 | 2026-05-14 | MLCC-C0174-CIV-STN-GAR-ITP-00002 | ITP Submission - Inspection and Test Plan (ITP) For Demolition/Removal of Existing Assets/Structures at G30 Creek Metro Station : MLCC-C0174-CIV-STN-GAR-ITP-00002_Rev.00 | 00 | A | ITP | CIV | STN | 1 | SAK |  |  | PAJV-TRANSMIT-013708 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016871 | 2026-05-16 | MLCC-C0174-CIV-STN-GAR-MST-00002 | Method Statement For Removal of Existing Assets and Installation of Temporary Enclosure Works at G30 Station : MLCC-C0174-CIV-STN-GAR-MST-00002_Rev.00 | 00 | A | MST | CIV | STN | 1 | SAK |  |  | PAJV-TRANSMIT-013705 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017547 | 2026-06-03 | MLCC-N0003-ARC-NWW-GAR-MTS-00093 | Material Approval Request for Supply of Metal Doors and Frames, Equipment Access Hatches, Access Doors and Panel & Access Hatches "QMI": MLCC-N0003-ARC-NWW-GAR-MTS-00093_Rev.00 | 00 | A | MAT | ARC | NWW | 1 | AKR |  |  | PAJV-TRANSMIT-013703 | 2026-06-09 |  |  | Rejected | Rejected
| MLCC-TRANSMIT-017435 | 2026-06-01 | MLCC-N0003-CYB-NWW-SYW-QUA-00010 | PQ Submission - Prequalification Submittal For Paramount Computer Systems : MLCC-N0003-CYB-NWW-SYW-QUA-00010_Rev.00 | C01 | A | PQN | SYS | CYB | 1 | LS |  |  | PAJV-TRANSMIT-013702 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017436 | 2026-06-01 | MLCC-N0003-PDS-MPD-NWW-QUA-00004 | Re: PQ Submission - Prequalification Submittal For Tianjin Keyvia Electric Co.,Ltd : MLCC-N0003-PDS-MPD-NWW-QUA-00004_Rev.02 | 02 | D | PQN | SYS | PDS | 1 | LS |  |  | PAJV-TRANSMIT-013701 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016856 | 2026-05-16 | MLCC-Z0015-CIV-NWW-GAR-MTS-00018 | Material Approval Request for Marine Rock for Scour Protection-60-300KG "AL Wissam Stones / Marjan Aman General Transport": MLCC-Z0015-CIV-NWW-GAR-MTS-00018_Rev.00 | 00 | A | MAT | CIV | NWW | 1 | AKR |  |  | PAJV-TRANSMIT-013700 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016776 | 2026-05-15 | MLCC-N0003-BES-FPS-SYW-RPT-70001 | Re: Report Submission - DCP2 - Fire Life Safety (FLS) Strategy Underground Stations (DE.GEN.GN00.MEP.M8.D2) : MLCC-N0003-BES-FPS-SYW-RPT-70001_Rev.C02 | C02 | B | RPT | MEP | FPS | 1 | IS | DCP 2 |  | PAJV-TRANSMIT-013699 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017038 | 2026-05-20 | DE.DPT.OCCA.ARC.A0.D2 | Package Submission - DCP2 - Depot BDR08 OCC and Administration Building - Architecture: DE.DPT.OCCA.ARC.A0.D2_Rev.C01 | C01 | A | DRW | ARC | DBF | 75 | ML | DCP 2 |  | PAJV-TRANSMIT-013698 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016607 | 2026-05-12 | RLS.1.1.1.5.8 | Package Submission - DCP2 - Platform Screen Doors (PSD) - BIM Model - BG32 Station : RLS.1.1.1.5.8_Rev.C01 (RCS Resubmission) | C02 | B | OTH | SYS | PSD | 3 | CH | DCP 2 |  | PAJV-TRANSMIT-013697 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016604 | 2026-05-12 | RLS.1.1.1.5.8 | Package Submission - DCP2 - Platform Screen Doors (PSD) - BIM Model - BR08 station : RLS.1.1.1.5.8_Rev.C01 (RCS Resubmission) | C01 | B | OTH | SYS | NWW | 3 | CH | DCP 2 |  | PAJV-TRANSMIT-013696 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016603 | 2026-05-12 | RLS.1.1.1.5.8 | Package Submission - DCP2 - Platform Screen Door (PSD) - BIM Model - BR07 Station : RLS.1.1.1.5.8_Rev.C01 (RCS Resubmission) | C01 | B | OTH | SYS | PSD | 3 | CH | DCP 2 |  | PAJV-TRANSMIT-013694 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016606 | 2026-05-12 | RLS.1.1.1.5.8 | Package Submission - DCP2 - Platform Screen Doors (PSD) - BIM Model - BB04 Station : RLS.1.1.1.5.8_Rev.C01 (RCS Resubmission) | C01 | B | OTH | SYS | PDS | 3 | CH | DCP 2 |  | PAJV-TRANSMIT-013693 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016605 | 2026-05-12 | RLS.1.1.1.5.8 | Package Submission - DCP2 - Platform Screen Doors (PSD) - BIM Model - BR09 Station : RLS.1.1.1.5.8_Rev.C01 (RCS Resubmission) | C01 | B | OTH | SYS | PSD | 3 | CH | DCP 2 |  | PAJV-TRANSMIT-013692 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016880 | 2026-05-18 | DE.TNL.CC01.STR.T2.D3 | Package Submission - DCP3 - Cut & Cover Slabs, Struts And Waler Beam : DE.TNL.CC01.STR.T2.D3_Rev.C01 | C01 | A | DRW | CIV | CCV | 20 | MS | DCP 3 |  | PAJV-TRANSMIT-013690 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016818 | 2026-05-16 | DE.VDT.ST01.STR.V1.D3 | Package Submission - DCP3 - Stretch 01 - Viaduct Structure - PM19 & PM20 : DE.VDT.ST01.STR.V1.D3_Rev.C01 | C01 | A | DRW | CIV | VBR | 8 | MS | DCP 3 |  | PAJV-TRANSMIT-013689 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017190 | 2026-05-22 | MLCC-S0724-CIV-EPD-RFC-DRW-13060-13095 | Shop Drawing Submission - BB05 Station - Ancillary-03 – D-wall - Type-AS1- Primary & Secondary Panel Reinforcement : MLCC-S0724-CIV-EPD-RFC-DRW-13060-13095_Rev.C01 | C01 | A | DRW | CIV | EPD | 27 | SSY |  |  | PAJV-TRANSMIT-013688 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017197 | 2026-05-22 | MLCC-S0724-CIV-EPD-RFC-DRW-13068 - 13071,MLCC-S0724-CIV-EPD-RFC-DRW-13078 - 13081 | Shop Drawing Submission - Station BB05 Station - Ancillary-03 -D-wall - Type-AS2- Primary & Secondary Panel Reinforcement (MLCC-S0724-CIV-EPD-RFC-DRW-13068 - 13071,MLCC-S0724-CIV-EPD-RFC-DRW-13078 - 13081_Rev.C01 | C01 | A | DRW | CIV | EPD | 8 | SSY |  |  | PAJV-TRANSMIT-013687 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017408 | 2026-05-26 | MLCC-S0709-CIV-STN-FND-DRW-13132 - MLCC-S0709-CIV-STN-FND-DRW-13136) | Shop Drawing Submission - Station BB06 Base Slab Pour 21 (MLCC-S0709-CIV-STN-FND-DRW-13132 - MLCC-S0709-CIV-STN-FND-DRW-13136)_Rev.C01 | C01 | A | DRW | CIV | STN | 5 | SSY |  |  | PAJV-TRANSMIT-013686 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017089 | 2026-05-21 | MLCC-N0003-BES-WTS-SYW-MST-00001 | Re: Method Statement For Installation of GRP Water Storage Tank : MLCC-N0003-BES-WTS-SYW-MST-00001_Rev.01 | 01 | B | MST | MEP | WTS | 1 | SAK |  |  | PAJV-TRANSMIT-013684 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016470 | 2026-05-11 | MLCC-N0003-CIF-SIF-GEN-ICD-51204 | ICD Submission - DCP2 - Interface Control Document for Tunnel - RSY : MLCC-N0003-CIF-SIF-GEN-ICD-51204_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013683 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017448 | 2026-06-01 | MLCC-N0003-PDS-MPD-LVS-SPC-51008 | Specification Submission - DCP2 - RSY LV Cable Technical Specification (RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-LVS-SPC-51008_Rev.C03 | C03 | C | SPC | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013682 | 2026-06-09 |  |  | SONO | SONO
| MLCC-TRANSMIT-017473 | 2026-06-02 | MLCC-N0003-PDS-MPD-NWW-SPC-51005 | Specification Submission - DCP2 - Power Distribution System Control Command Cubicle Technical Specification (RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-NWW-SPC-51005_Rev.C03 | C03 | C | SPC | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013681 | 2026-06-09 |  |  | SONO | SONO
| MLCC-TRANSMIT-016976 | 2026-05-19 | DE.VDT.ST03.STR.V3.D3 | Re: Package Submission - DCP3 - Stretch-03 - Viaduct Structure Superstructure 2SP : DE.VDT.ST03.STR.V3.D3_Rev.C02 | C02 | B | DRW | CIV | VBR | 9 | MS | DCP 3 |  | PAJV-TRANSMIT-013680 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017076 | 2026-05-20 | MLCC-C0184-CIV-NWW-GEO-RPT-82204 | Re: Report Submission - DCP3 - Geotechnical Design Report for BG35 (DE.ELS.GE05.GEO.G1.D3) : MLCC-C0184-CIV-NWW-GEO-RPT-82204_Rev.C01 (RCS Resubmission) | C01 | C | RPT | CIV | NWW | 1 | MSD | DCP 3 |  | PAJV-TRANSMIT-013679 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016732 | 2026-05-14 | DE.VDT.S4PT.STR.V1.D3 | Re: Package Submission - DCP3 - Stretch-04.2 - Viaduct Structure Foundation-Pocket Package 1 : DE.VDT.S4PT.STR.V1.D3_Rev.C02 | C02 | B | DRW | CIV | VBR | 8 | MS | DCP 3 |  | PAJV-TRANSMIT-013575 | 2026-06-06 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017501 | 2026-06-03 | MLCC-N0003-TRW-NWW-SSA-RPT-00005 | Report Submission - DCP2 - Track Permanent Way - RAMS – Track/ Third Rail/ Alignment Preliminary Design Safety Case : MLCC-N0003-TRW-NWW-SSA-RPT-00005_Rev.C01 | C01 | A | RPT | CIV | TRW | 1 | SAB | DCP 2 |  | PAJV-TRANSMIT-013677 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017079 | 2026-05-20 | MLCC-Z0045-UTL-NWW-GEN-DRW-70020 & MLCC-Z0045-UTL-NWW-GEN-DRW-70027 | NOC Drawing Submission - Typical Service Reservation Cross Section (Rashidiya Branch Line : MLCC-Z0045-UTL-NWW-GEN-DRW-70020 & MLCC-Z0045-UTL-NWW-GEN-DRW-70027_Rev.C04 | C04 | D | DRW | CIV | UTL | 2 | MS |  |  | PAJV-TRANSMIT-013676 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit | [5 empty] | need to read together with MLCC-TRANSMIT-015017
| MLCC-TRANSMIT-016941 | 2026-05-19 | DE.ANX.AX17.STR.S0.NC | NOC Drawing Submission - NOC Drawing Submission - ANNEX 08_NOC Drawings : DE.ANX.AX17.STR.S0.NC_Rev.C02 | C02 | B | DRW | CIV | UTL | 29 | MS |  |  | PAJV-TRANSMIT-013674 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016781 | 2026-05-15 | DE.ANX.AX16.STR.S0.NC | NOC Drawing Submission - Annex-BL-EES-07 - Structure NOC : DE.ANX.AX16.STR.S0.NC_Rev.C03 | C03 | C | DRW | CIV | GEN | 32 | MS |  |  | PAJV-TRANSMIT-013673 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017323 | 2026-05-25 | DE.ZNE.ZN2B.ARD.R0.D2 | Re: Package Submission - DCP2 - Zone 2B Roads Z0041 Package : DE.ZNE.ZN2B.ARD.R0.D2_Rev.C01 (RCS Resubmission) | C01 | B | DRW | CIV | RAR | 74 | SJ | DCP 2 |  | PAJV-TRANSMIT-013672 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016881 | 2026-05-18 | DE.ZNE.ZN01.UTI.U2.D2 | Re: Package Submission - DCP2 - Zone 01 Utility Z0039 : DE.ZNE.ZN01.UTI.U2.D2_Rev.C02 | C02 | B | DRW | CIV | UTL | 48 | YS | DCP 2 |  | PAJV-TRANSMIT-013671 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016882 | 2026-05-18 | DE.ZNE.ZN2B.UTI.U2.D2 | Re: Package Submission - DCP2 - Zone 2B Utility Z0041 Package : DE.ZNE.ZN2B.UTI.U2.D2_Rev.C02 | C02 | B | DRW | CIV | UTL | 36 | YS | DCP 2 |  | PAJV-TRANSMIT-013670 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016542 | 2026-05-11 | MLCC-N0003-CIV-NWW-GAR-MTS-00277 | Material Approval Request for Nonwoven Geotextile 120gsm "KANZ": MLCC-N0003-CIV-NWW-GAR-MTS-00277_Rev.00 | 00 | A | MAT | CIV | NWW | 1 | AKR |  |  | PAJV-TRANSMIT-013669 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016961 | 2026-05-19 | MLCC-N0003-BES-VAC-SYW-MTS-00007 | Re: Material Approval Request for Ductwork Hangers and Support "Hira Walrevan/MNG": MLCC-N0003-BES-VAC-SYW-MTS-00007_Rev.01 | 01 | B | MAT | MEP | VAC | 1 | AKR |  |  | PAJV-TRANSMIT-013668 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017139 | 2026-05-22 | MLCC-N0003-SIG-ATC-NWW-RPT-51604 | Re: Report Submission - DCP2 - Signalling (ATC) - RAMS - Hazard Log (RLS.1.1.1.4.5) : MLCC-N0003-SIG-ATC-NWW-RPT-51604_Rev.C02 | C02 | B | RPT | SYS | ATC | 1 | SAB | DCP 2 |  | PAJV-TRANSMIT-013667 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016660 | 2026-05-13 | DE.VDT.ST07.STR.V2.D3 | Package Submission - DCP3 - Stretch 07 - Viaduct Structure Bearing Schedule -BC-3SP-72-10A : DE.VDT.ST07.STR.V2.D3_Rev.C01 | C01 | A | DRW | CIV | VBR | 6 | MS | DCP 3 |  | PAJV-TRANSMIT-013666 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016727 | 2026-05-14 | MLCC-N0003-CIV-NWW-GAR-RPT-26008 | Report Submission - Mould System Design Reports (U Shape Segment Mould C16) : MLCC-N0003-CIV-NWW-GAR-RPT-26008_Rev.C01 | C01 | A | RPT | CIV | NWW | 3 | MS |  |  | PAJV-TRANSMIT-013664 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016893 | 2026-05-18 | MLCC-N0003-BES-FPS-FFS-MST-00002 | Method Statement For Installation Of Water Based Fire Fighting System (Standpipes, Sprinklers, FHC, Fire Department Connection, Extinguishers And Other Ancillary Components) : MLCC-N0003-BES-FPS-FFS-MST-00002_Rev.00 | C01 | A | MST | MEP | FPS | 1 | SAK |  |  | PAJV-TRANSMIT-013663 | 2026-06-09 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016319 | 2026-05-07 | DE.ELS.GE11.STR.S0.D2 | Re: Package Submission - DCP2 - Station BB03 Structural Package : DE.ELS.GE11.STR.S0.D2_Rev.00 (RCS Resubmission) | 00 | B | DRW | CIV | STN | 100 | DM | DCP 2 |  | PAJV-TRANSMIT-013662 | 2026-06-09 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017428 | 2026-05-27 | DE.VDT.ST03.STR.V3.D5 | Shop Drawing Submission - Stretch-03 - Viaduct Structure ISOSpan - Superstructure Shop Dwg Transition Span - 87 - (DE.VDT.ST03.STR.V3.D5) : MLCC-S0673-CIV-VBR-ISS-DRW-84061, 84062, 84064, 84066, 84067, 84069_Rev.C01 | C01 | A | DRW | CIV | VBR | 7 | AK |  |  | PAJV-TRANSMIT-013656 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016999 | 2026-05-19 | MLCC-N0003-CIV-VBR-GAR-MST-00052 | Method Statement For Segment Erection of Drop-In Span on Falsework : MLCC-N0003-CIV-VBR-GAR-MST-00052_Rev.00 | 00 | A | MST | CIV | VBR | 1 | AKM |  |  | PAJV-TRANSMIT-013655 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016022 | 2026-05-01 | DE.VDT.ST04.GEO.G1.D3 | Package Submission - DCP3 -Technical Note-Working Pile load Test Viaduct Stretch 4 (PM-101-04): DE.VDT.ST04.GEO.G1.D3_Rev.C01 | C01 | A | DRW | CIV | NWW | 1 | MS | DCP 3 |  | PAJV-TRANSMIT-013654 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017000 | 2026-05-19 | MLCC-N0003-CIV-VBR-GAR-MST-00051 | Method Statement For Segment Erection on Falsework For ISO /Twin/Station Span : MLCC-N0003-CIV-VBR-GAR-MST-00051_Rev.00 | 00 | A | MST | CIV | VBR | 1 | AK |  |  | PAJV-TRANSMIT-013653 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016870 | 2026-05-16 | MLCC-N0003-CIV-VBR-GAR-CAL-00001 | Calculation Submission - Extension Calculation for ISO-32 PT-CU2 : MLCC-N0003-CIV-VBR-GAR-CAL-00001_Rev C01 | C01 | A | CAL | CIV | VBR | 1 | MS |  |  | PAJV-TRANSMIT-013652 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016928 | 2026-05-19 | DE.DPT.TBG2.ARC.A0.D2 | Re: Package Submission - DCP2 - Depot BDR11 - Architecture Chiller Compound-2 : DE.DPT.TBG2.ARC.A0.D2_Rev.C02 | C02 | B | DRW | ARC | DBF | 26 | ML | DCP 2 |  | PAJV-TRANSMIT-013651 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017048 | 2026-05-20 | MLCC-N0003-TRW-PWA-TRL-RPT-81005-DCP2 | Re: Report Submission - DCP2 - Routewide Contact Rail System Support Position Arrangement Drawing (DE.TNL.GN00.TWK.P1.D2) : MLCC-N0003-TRW-PWA-TRL-RPT-81005-DCP2_Rev.C02 | C01 | B | RPT | CIV | TRW | 1 | JP | DCP 2 |  | PAJV-TRANSMIT-013650 | 2026-06-08 |  |  | SONO | SONO
| MLCC-TRANSMIT-016890 | 2026-05-18 | MLCC-N0003-CIF-SIF-GEN-ICD-51175 | ICD Submission - DCP2 - Interface Control Document (ICD)- Viaduct Stretch 6.1 Civil Works / Stakeholders : MLCC-N0003-CIF-SIF-GEN-ICD-51175_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013649 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016889 | 2026-05-18 | MLCC-N0003-CIF-SIF-GEN-ICD-51171 | ICD Submission - DCP2 - Interface Control Document (ICD) BB04 Dubai Silicon Oasis Station - CIVIL/ Stakeholders : MLCC-N0003-CIF-SIF-GEN-ICD-51171_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013648 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016859 | 2026-05-16 | MLCC-N0003-CIF-SIF-GEN-ICD-51174 | ICD Submission - DCP2 - Interface Control Document (ICD) - Viaduct Stretches 00-04.2 Civil Works / Stakeholders : MLCC-N0003-CIF-SIF-GEN-ICD-51174_Rev.C01 | C01 | A | ICD | PMC | CIF | 1 | RT | DCP 2 |  | PAJV-TRANSMIT-013647 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-015492 | 2026-04-22 | MLCC-N0003-CIV-STN-GAR-MST-00006 | Re: Method Statement For Diaphragm Wall Repair Works : MLCC-N0003-CIV-STN-GAR-MST-00006_Rev.01 | 01 | B | MST | CIV | STN | 1 | SSY |  |  | PAJV-TRANSMIT-013646 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017208 | 2026-05-22 | MLCC-S0709-CIV-STN-RFC-DRW-13001 to 13004 | Re: Shop Drawing Submission - Station BB06 - Structure External Wall (EW1) Reinforcement along Grid H Shop Drawing & BBS : MLCC-S0709-CIV-STN-RFC-DRW-13001 to 13004_Rev.C02 | C02 | B | DRW | CIV | STN | 1 | SSY |  |  | PAJV-TRANSMIT-013645 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017124 | 2026-05-21 | MLCC-S0724-CIV-EPD-RFC-DRW-13048-13049, 13105-13110 | Shop Drawing Submission - BB05 Station - Ancillary-02 – D-wall - Type-AS1 - Primary Panel D14 & D16 Reinforcement : MLCC-S0724-CIV-EPD-RFC-DRW-13048-13049, 13105-13110_Rev.C01 | C01 | A | DRW | CIV | EPD | 8 | SSY |  |  | PAJV-TRANSMIT-013644 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017368 | 2026-05-26 | MLCC-S0709-CIV-STN-RFC-DRW-13028 to 13039 | Shop Drawing Submission - Station BB06 - Structure External Wall (EW8, WE9 & EW10) Reinforcement Along Grid-A (BS to CL) Shop Drawing & BBS : MLCC-S0709-CIV-STN-RFC-DRW-13028 to 13039_Rev.C01 | C01 | A | DRW | CIV | STN | 12 | SSY |  |  | PAJV-TRANSMIT-013643 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017495 | 2026-06-03 | MLCC-S0651-CIV-VBR-FND-MST-00004 | Method Statement For Installation of Precast Shell for Foundation Pile Cap – Dubai Creek Crossing : MLCC-S0651-CIV-VBR-FND-MST-00004_Rev.00 | 00 | A | MST | CIV | VBR | 1 | AKM |  |  | PAJV-TRANSMIT-013639 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017447 | 2026-06-01 | MLCC-C0199-PDS-MPD-NWW-SPC-51001 | Specification Submission - DCP2 - Power Supply (PDS) - BOCC Enhancement Works Specification (RLS.1.1.2.2.2) : MLCC-C0199-PDS-MPD-NWW-SPC-51001_Rev.C02 | C02 | B | SPC | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013637 | 2026-06-08 |  |  | SONO | SONO
| MLCC-TRANSMIT-016621 | 2026-05-13 | DE.ELS.RE00.MEP.M2.D2 | Package Submission - DCP2 - BR10 Stations MEP - DAW &WTS : DE.ELS.RE00.MEP.M2.D2_Rev.C01 | C01 | A | DRW | MEP | DAW | 64 | IS | DCP 2 |  | PAJV-TRANSMIT-013634 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017605 | 2026-06-04 | MLCC-N0003-CIV-VBR-GAR-PLN-00001 | Plan Submission - Quality Plan for Spherical Bearing : MLCC-N0003-CIV-VBR-GAR-PLN-00001_Rev.C01 | C01 | A | PLN | CIV | VBR | 1 | AW |  |  | PAJV-TRANSMIT-013633 | 2026-06-08 |  |  | Rejected | Rejected
| MLCC-TRANSMIT-016895 | 2026-05-18 | MLCC-N0003-TRW-NWW-GEN-PLN-00004 | Plan Submission - Qualification Test for Flash butt welding machine : MLCC-N0003-TRW-NWW-GEN-PLN-00004_Rev.00 | 00 | A | PLN | CIV | TRW | 1 | JP |  |  | PAJV-TRANSMIT-013632 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017426 | 2026-05-27 | MLCC-S0727-CIV-VBR-FND-DRW-84000, 84002 & 84005 | Re: Shop Drawing Submission - Stretch-06.2 - Viaduct Structure Foundation - Pile Drawing - PM-158 & PM-161 - (DE.VDT.ST06.STR.V1.D5) MLCC-S0727-CIV-VBR-FND-DRW-84000, 84002 & 84005_Rev.C02 | C02 | C | DRW | CIV | VBR | 4 | AK |  |  | PAJV-TRANSMIT-013631 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016463 | 2026-05-11 | MLCC-Z0045-BES-ELE-LVD-MST-00002 | Re: Method Statement For FAT of Electrical Panels (Rashidiya Station – Temporary Pedestrian Passage) : MLCC-Z0045-BES-ELE-LVD-MST-00002_Rev.01 | 01 | B | MST | MEP | ELE | 1 | SAK |  |  | PAJV-TRANSMIT-013630 | 2026-06-08 |  |  | SONO | SONO
| MLCC-TRANSMIT-016826 | 2026-05-16 | MLCC-S0675-CIV-STN-PIR-DRW-13001-13006 | Re: Shop Drawings Submission - Station BG34 - Structure Pier - Type RCC1 to RCC6 Shop Drawing & BBS : MLCC-S0675-CIV-STN-PIR-DRW-13001-13006_Rev.C04 | C04 | E | DRW | CIV | STN | 6 | SAK |  |  | PAJV-TRANSMIT-013629 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016522 | 2026-05-11 | MLCC-S0701-CIV-CCV-RFC-DRW-13070 to 13072, 13085 to 13090 | Re: Shop Drawing Submission - CC01-Cut & Cover Structure D-Wall Reinforcement Shop Drawings Type-C Primary Panel (P47, P48 & P49) : MLCC-S0701-CIV-CCV-RFC-DRW-13070 to 13072, 13085 to 13090_Rev.C02 | C02 | B | DRW | CIV | CCV | 9 | SAK |  |  | PAJV-TRANSMIT-013628 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017582 | 2026-06-04 | MLCC-S0820-CIV-STN-RFC-DRW-14021 to MLCC-S0820-CIV-STN-RFC-DRW-14079 | Re: Shop Drawing Submission - Station BR07-Structure Pour-C9 Concourse Slab Shop Drawings : MLCC-S0820-CIV-STN-RFC-DRW-14021 to MLCC-S0820-CIV-STN-RFC-DRW-14079_Rev.C02 | C02 | B | DRW | CIV | STN | 31 | SSY |  |  | PAJV-TRANSMIT-013627 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016712 | 2026-05-14 | MLCC-N0003-BES-WTS-SYW-MST-00002 | Method Statement for Installation of Domestic Water Supply Pumps and Treatement System : MLCC-N0003-BES-WTS-SYW-MST-00002_Rev.00 | 00 | A | MST | MEP | WTS | 1 | SAK |  |  | PAJV-TRANSMIT-013626 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016850 | 2026-05-16 | MLCC-S0692-CIV-STN-RFC-DRW-13080-13086, MLCC-S0692-CIV-STN-GAR-DRW-13028-13029, MLCC-S0692-CIV-STN-SSR-DRW-13015 | Shop Drawing Submission - Station BG36 - Concourse Level Wing Beam Reinf. At Grid 20 : MLCC-S0692-CIV-STN-RFC-DRW-13080-13086, MLCC-S0692-CIV-STN-GAR-DRW-13028-13029, MLCC-S0692-CIV-STN-SSR-DRW-13015_Rev.C01 | C01 | A | DRW | CIV | STN | 10 | SAK |  |  | PAJV-TRANSMIT-013625 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017193 | 2026-05-22 | MLCC-S0654-CIV-STN-RFC-DRW-13103-13106,13129_ | Re: Shop Drawing Submission - Station BG32 - Concourse Level RC Elements Wing Beam Reinf. At Grid 10 : MLCC-S0654-CIV-STN-GAR-DRW-13201, MLCC-S0654-CIV-STN-RFC-DRW-13103-13106,13129_Rev.C02 | C02 | B | DRW | CIV | STN | 5 | SAK |  |  | PAJV-TRANSMIT-013624 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016667 | 2026-05-13 | MLCC-S0749-CIV-VBR-PAP-DRW-13002-13017 | Re: Shop Drawing Submission - Stretch-08.1 Viaduct Structure Foundation - Pile Cap Shop Drawing - Pile caps - 247, 248, 249, 250, 251, 252, 253, 254, 255, 256, 257, 258, 259 & 260 : MLCC-S0749-CIV-VBR-PAP-DRW-13002-13017_Rev.C02 | C02 | B | DRW | CIV | VBR | 16 | AK |  |  | PAJV-TRANSMIT-013623 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017575 | 2026-06-04 | MLCC-S0727-CIV-VBR-FND-DRW-13050 | Re: Shop Drawing Submission - Stretch-06.2 Viaduct Structure Pile Coordinates & Foundation - Pile Shop Drawing PM159 & PM160 : MLCC-S0727-CIV-VBR-FND-DRW-13000-13003 & 13050_Rev.C01 | C01 | B | DRW | CIV | VBR | 3 | AKM |  |  | PAJV-TRANSMIT-013622 | 2026-06-08 |  |  | SONO | SONO
| MLCC-TRANSMIT-016580 | 2026-05-12 | MLCC-N0003-ARC-PTW-GAR-ITP-01000_Rev.00 | Re: ITP Submission - Inspection and Test Plan (ITP) For Gypsum Wall Lining & Ceiling Works For Elevated Station : MLCC-N0003-ARC-PTW-GAR-ITP-01000_Rev.00 | 00 | B | ITP | ARC | PTW | 1 | SAK |  |  | PAJV-TRANSMIT-013621 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017427 | 2026-05-27 | DE.VDT.ST06.STR.V1.D5 | Shop Drawing Submission - Stretch-06.2 - Viaduct Structure Pier Shop Drawing PM158 and PM161 - ( DE.VDT.ST06.STR.V1.D5) MLCC-S0727-CIV-VBR-PIR-DRW-84000, 84001, 84025 and 84026_Rev.C01 | C01 | A | DRW | CIV | VBR | 5 | AK |  |  | PAJV-TRANSMIT-013620 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017331 | 2026-05-25 | DE.VDT.ST06.STR.V1.D5 | Shop Drawing Submission - Stretch-06.2 - Viaduct Structure Pier Shop Drawing - PM159 & PM160 : DE.VDT.ST06.STR.V1.D5_Rev.C01 | C01 | A | DRW | CIV | VBR | 8 | AK |  |  | PAJV-TRANSMIT-013619 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-014824 | 2026-04-10 | MLCC-N0003-BES-NWW-EQG-MST-00001 | Re: Method Statement For Pull Out Test of Mechanical Works : MLCC-N0003-BES-NWW-EQG-MST-00001_Rev.01 | 01 | B | MST | MEP | NWW | 1 | AK |  |  | PAJV-TRANSMIT-013618 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017574 | 2026-06-04 | MLCC-N0003-CIV-VBR-SYW-DRW-13023 | Shop Drawing Submission - Global - Viaduct Structure Foundation PM160-01 Pile Head And Shop Drawing BBS-Dynamic Test : MLCC-N0003-CIV-VBR-SYW-DRW-13023_Rev.C01 | C01 | A | DRW | CIV | TNL | 17 | AK |  |  | PAJV-TRANSMIT-013617 | 2026-06-08 |  |  | SONO | SONO
| MLCC-TRANSMIT-017233 | 2026-05-23 | MLCC-S0654-CIV-STN-GAR-DRW-13238 | Re: Shop Drawing Submission - Station BG32 - Concourse Level RC Elements Wing Beam Reinf. at Grid 09 : MLCC-S0654-CIV-STN-GAR-DRW-13238_Rev.C02 | C02 | B | DRW | CIV | STN | 10 | SAK |  |  | PAJV-TRANSMIT-013616 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017507 | 2026-06-03 | MLCC-N0003-PDS-MPD-NWW-PLN-51700 | Plan Submission - DCP2 – Power Supply (PDS) – EMC Control Plan (RLS.1.1.2.2.2) : MLCC-N0003-PDS-MPD-NWW-PLN-51700_Rev.C02 | C02 | B | PLN | SYS | PDS | 1 | OK | DCP 2 |  | PAJV-TRANSMIT-013615 | 2026-06-08 |  |  | SONO | SONO
| MLCC-TRANSMIT-016655 | 2026-05-13 | DE.VDT.ST04.STR.V2.D3 | Package Submission - DCP3 - Stretch-04.1 - Viaduct Structure Bearing Schedule (Part 1) : DE.VDT.ST04.STR.V2.D3_Rev.C01 | C01 | A | DRW | CIV | VBR | 6 | MS | DCP 3 |  | PAJV-TRANSMIT-013614 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016950 | 2026-05-19 | DE.ELS.GE06.GEO.G1.D3 | Re: Report Submission - DCP3 - Technical Note-Dynamic Pile load Test at BG36 (GLE06) (DE.ELS.GE06.GEO.G1.D3) : MLCC-C0186-CIV-NWW-GEO-RPT-82432-DCP3_Rev.C03 (RCS Resubmission) | C03 | D | RPT | CIV | NWW | 1 | MS | DCP 3 |  | PAJV-TRANSMIT-013613 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016601 | 2026-05-12 | MLCC-S0719-CIV-STN-RFC-FCR-00003 | Re: FCR Submission - Field Change and Drawing Modification Request (FCR) for Concrete Grade Modification for Concourse Level Waler Beam WB4 – BB05 Station : MLCC-S0719-CIV-STN-RFC-FCR-00003_Rev.C01 (RCS Resubmission) | C01 | B | OTH | CIV | STN | 1 | DM |  |  | PAJV-TRANSMIT-013612 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016812 | 2026-05-15 | MLCC-S0820-CIV-STN-RFC-FCR-00011 | FCR Submission - Field Change and Drawing Modification Request (FCR) for BR07 Station Concourse Slab - Pour 4 & 5 Waler Beam Compression Zone Coupler Extension : MLCC-S0820-CIV-STN-RFC-FCR-00011_Rev.C01 | C01 | A | OTH | CIV | STN | 1 | DM |  |  | PAJV-TRANSMIT-013611 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016784 | 2026-05-15 | DE.UGS.GE08.STR.S4.D3 | Re: Package Submission - DCP3 - Station BB06 Base slab (TBM SHAFT AREA) : DE.UGS.GE08.STR.S4.D3_Rev.C03 (Partial Submission) | C03 | D | DRW | CIV | STN | 16 | DM | DCP 3 |  | PAJV-TRANSMIT-013610 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016750 | 2026-05-14 | DE.DPT.TBG1.STR.S0.D3 | Package Submission - DCP3 - Depot BDR10 Chiller Compound 1 - Structural (DM Submission): DE.DPT.TBG1.STR.S0.D3_Rev.C01 | C01 | A | DRW | CIV | DBF | 40 | DM | DCP 3 |  | PAJV-TRANSMIT-013609 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017508 | 2026-06-03 | MLCC-N0003-PDS-MPD-MVN-SPC-51002 | Specification Submission - DCP2 - MV Auxiliary Transformer Technical Specification (RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-MVN-SPC-51002_Rev.C03 | C03 | C | SPC | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013608 | 2026-06-08 |  |  | SONO | SONO
| MLCC-TRANSMIT-017110 | 2026-05-21 | DE.UGS.GE09.STR.S1.D3 | Re: Package Submission - DCP3 - Station BB05 - Earthing and Bonding Below Base Slab Design: DE.UGS.GE09.STR.S1.D3_Rev C02 | C02 | B | DRW | MEP | ELE | 7 | OK | DCP 3 |  | PAJV-TRANSMIT-013606 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016949 | 2026-05-19 | MLCC-Z0039-CIV-NWW-GAR-SPC-00001 | Specification Submission - Dubai Creek Crossing Cathodic Protection Design Specification for Reinforced Pile, Pile Cap & Pier Lower Level : MLCC-Z0039-CIV-NWW-GAR-SPC-00001_Rev.C01 | C01 | A | SPC | CIV | NWW | 1 | OK |  |  | PAJV-TRANSMIT-013605 | 2026-06-08 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016541 | 2026-05-11 | MLCC-N0003-CIV-NWW-GAR-MTS-10017 | Material Approval Request for Cut & Bend Factory - Steel Structure - Temporary Works "Core Metal": MLCC-N0003-CIV-NWW-GAR-MTS-10017_Rev.00 | 00 | A | MAT | CIV | NWW | 1 | AKR |  |  | PAJV-TRANSMIT-013604 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016322 | 2026-05-07 | MLCC-N0003-BES-VAC-CHW-MTS-00007 | Material Approval Request for Air and Dirt Separator "Reflex / MNG": MLCC-N0003-BES-VAC-CHW-MTS-00007_Rev.00 | 00 | A | MAT | MEP | VAC | 1 | AKR |  |  | PAJV-TRANSMIT-013603 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016867 | 2026-05-16 | DE.ELS.GE00.ARC.A2.D2 | Re: Package Submission - DCP2 - BG31 Creek Interchange Station Architectural : DE.ELS.GE00.ARC.A2.D2_Rev.C02 | C02 | B | DRW | ARC | STN | 123 | ML | DCP 2 |  | PAJV-TRANSMIT-013602 | 2026-06-08 |  |  | Revise & Resubmit | Revise & Resubmit | [5 empty] | Part 2 Submitted on 05-06-2026 via PAJV-TRANSMIT-017658
| MLCC-TRANSMIT-016908 | 2026-05-18 | MLCC-N0003-ENG-SSA-HUF-RPT-00002 | Report Submission - BOCC Preliminary Ergonomics Study : MLCC-N0003-ENG-SSA-HUF-RPT-00002_Rev.C01 | C01 | A | RPT | PMC | SSA | 1 | SAB |  |  | PAJV-TRANSMIT-013599 | 2026-06-06 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017475 | 2026-06-02 | MLCC-N0003-PDS-MPD-MVN-SPC-51003 | Specification Submission - DCP2 - Medium Voltage Cables Technical Specification (RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-MVN-SPC-51003_Rev.C03 | C03 | C | SPC | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013597 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-017474 | 2026-06-02 | MLCC-N0003-PDS-MPD-NWW-SPC-51006 | Specification Submission - DCP2 - Power Distribution System Control and Command Cables Technical Specification (RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-NWW-SPC-51006_Rev.C03 | C03 | C | SPC | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013595 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-017449 | 2026-06-01 | MLCC-Z0001-COM-NWW-GEN-MST-51001 | Re: Method Statement for the Rerouting of FON, NBR and TVM Cables : MLCC-Z0001-COM-NWW-GEN-MST-51001_Rev.02 | 02 | C | MST | SYS | COM | 1 | VHL |  |  | PAJV-TRANSMIT-013594 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-017456 | 2026-06-01 | MLCC-N0003-PDS-MPD-NWW-SPC-51002 | Specification Submission - DCP2 - Blue Light Station/ECO Bypass Panel Technical Specification (RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-NWW-SPC-51002_Rev.C03 | C03 | C | SPC | SYS | PSD | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013593 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-017452 | 2026-06-01 | MLCC-N0003-PDS-MPD-NWW-SPC-51003 | Specification Submission - DCP2 - Blue Light Station Control Panel Technical Specification (RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-NWW-SPC-51003_Rev.C03 | C03 | C | SPC | SYS | PSD | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013592 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-017445 | 2026-06-01 | MLCC-N0003-PDS-MPD-MVN-SPC-51001 | Specification Submission - DCP2 - MV System Design Specification and System Architecture (RLS.1.1.2.2.2) : MLCC-N0003-PDS-MPD-MVN-SPC-51001_Rev C03 | C03 | C | SPC | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013591 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-017526 | 2026-06-03 | MLCC-N0003-PDS-MPD-TRP-SPC-51005 | Specification Submission - DCP2 – Traction Rectifier Transformer Technical Specification (PDS_RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-TRP-SPC-51005_Rev.C03 | C03 | C | SPC | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013590 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-017484 | 2026-06-02 | MLCC-N0003-PDS-MPD-TRP-SPC-51007 | Specification Submission - DCP2 – Traction Rectifier Technical Specification (PDS_RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-TRP-SPC-51007_Rev.C03 | C03 | C | SPC | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013589 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-017584 | 2026-06-04 | MLCC-N0003-PDS-MPD-MVN-NTS-51006 | Re: Notes Submission - DCP2 - Medium Voltage Cable Sizing Calculation Note (RLS.1.1.2.2.3): MLCC-N0003-PDS-MPD-MVN-NTS-51006_Rev.C02 | C02 | B | OTH | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013588 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-017483 | 2026-06-02 | MLCC-N0003-PDS-MPD-TRP-SPC-5100 | Specification Submission - DCP2 – Traction Protection Switchboard Technical Specification (RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-TRP-SPC-51001_Rev.C03 | C03 | C | SPC | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013586 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-017147 | 2026-05-22 | MLCC-N0003-PMC-THA-EMC-RPT-00001 | Report Submission - EMC Environment Characterization Report : MLCC-N0003-PMC-THA-EMC-RPT-00001_Rev.C01 | C01 | A | RPT | PMC | THA | 1 | OK |  |  | PAJV-TRANSMIT-013585 | 2026-06-06 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-017146 | 2026-05-22 | DE.ELS.GE11.ARC.A2.D2 | Re: Package Submission - DCP2 - BB03 - Academic City Station (GLE-11) Architecture Design Package: DE.ELS.GE11.ARC.A2.D2_Rev C04 | C04 | D | DRW | ARC | STN | 109 | ML | DCP 2 |  | PAJV-TRANSMIT-013584 | 2026-06-06 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017523 | 2026-06-03 | MLCC-N0003-PDS-MPD-TRP-SPC-51006 | Specification Submission - DCP2 – Traction Inverter Transformer Technical Specification (PDS_RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-TRP-SPC-51006_Rev.C03 | C03 | C | SPC | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013583 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-017511 | 2026-06-03 | MLCC-N0003-PDS-MPD-TRP-SPC-51008 | Specification Submission - DCP2 - Traction Inverter Technical Specification (RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-TRP-SPC-51008_Rev.C03 | C03 | C | SPC | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013582 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-017140 | 2026-05-22 | MLCC-N0003-SIG-ATC-NWW-RPT-51607 | Report Submission - DCP2 - Signalling (ATC) - RAMS – Preliminary Design Safety Case (RLS.1.1.13.2.9) : MLCC-N0003-SIG-ATC-NWW-RPT-51607_Rev.C01 | C01 | A | RPT | SAS | ATC | 1 | SAB | DCP 2 |  | PAJV-TRANSMIT-013581 | 2026-06-06 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017515 | 2026-06-03 | MLCC-N0003-PDS-MPD-TRP-SPC-51004 | Specification Submission - DCP2 - Traction Negative Panel Specification (PDS_RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-TRP-SPC-51004_Rev.C03 | C03 | C | SPC | SYS | PDS | 1 | SZ | DCP 2 |  | PAJV-TRANSMIT-013580 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-016753 | 2026-05-14 | DE.VDT.ST06.GEO.G1.D3 | Re: Package Submission - DCP3 - Technical Note - Working Pile Load Test Viaduct Stretch 6 (PM-172-01) : DE.VDT.ST06.GEO.G1.D3_Rev.C02 | C02 | B | DRW | CIV | STN | 6 | MSD | DCP 3 |  | PAJV-TRANSMIT-013579 | 2026-06-06 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016528 | 2026-05-11 | DE.UGS.GE09.STR.S5.D3 | Re: Package Submission - DCP3 - Station BB05 - Structure Base Slab : DE.UGS.GE09.STR.S5.D3_Rev.C02 | C02 | B | DRW | CIV | STN | 1 | DM | DCP 3 |  | PAJV-TRANSMIT-013578 | 2026-06-06 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016726 | 2026-05-14 | DE.UGS.SB01.STR.S6.D3 | Package Submission - DCP3 - Switchbox-Structure Top Slab Design : DE.UGS.SB01.STR.S6.D3_Rev.C01 | C01 | A | DRW | CIV | STN | 16 | DM | DCP 3 |  | PAJV-TRANSMIT-013577 | 2026-06-06 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016789 | 2026-05-15 | DE.ELS.RE00.GEO.G1.D3 | Package Submission - DCP3 - Technical Note-Working Pile Load test at BR10 (SOP42) : DE.ELS.RE00.GEO.G1.D3_Rev.C01 | C01 | A | DRW | CIV | NWW | 1 | MSD | DCP 3 |  | PAJV-TRANSMIT-013576 | 2026-06-06 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-017078 | 2026-05-20 | MLCC-S0647-CIV-STN-GAR-DRW-26005-26006 | Report - Spreader Beam (S.W.L 240 Ton Capacity) - MLCC-S0647-CIV-STN-GAR-RPT-26003, MLCC-S0647-CIV-STN-GAR-DRW-26005-26006_Rev.C01 | C01 | A | DRW | CIV | STN | 4 | DM |  |  | PAJV-TRANSMIT-013574 | 2026-06-06 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-015440 | 2026-04-22 | DE.UGS.GE09.STR.S1.D3 | Re: Package Submission - Station BB05 Instrumentation and Monitoring Drawings : DE.UGS.GE09.STR.S1.D3_Rev.C02 | C02 | C | DRW | CIV | STN | 9 | DM |  |  | PAJV-TRANSMIT-013573 | 2026-06-06 |  |  | SONO | SONO
| MLCC-TRANSMIT-016472 | 2026-05-11 | MLCC-S0647-CIV-STN-GAR-RPT-26002 | Report Submission - Design Report of Core Wall Formwork at BG31 Station : MLCC-S0647-CIV-STN-GAR-RPT-26002_Rev.C01 | C01 | A | RPT | CIV | STN | 1 | DM |  |  | PAJV-TRANSMIT-013572 | 2026-06-06 |  |  | Revise & Resubmit | Revise & Resubmit
| MLCC-TRANSMIT-016416 | 2026-05-09 | DE.VDT.ST02.STR.V1.D3 | Re: Package Submission - DCP3 - Viaduct Foundation & Substructure - Stretch 02-Balance Cantilever 3SP-72-01 : DE.VDT.ST02.STR.V1.D3_Rev.C03 | C04 | D | DRW | CIV | VBR | 12 | MS | DCP 3 |  | PAJV-TRANSMIT-013571 | 2026-06-06 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-015688 | 2026-04-25 | MLCC-N0003-CIV-NWW-GAR-DRW-00315 - 00323 | NOC Drawing Submission - BR07 Station Proposed 400Ø Sewer Line Diversion NDRC Layout : MLCC-N0003-CIV-NWW-GAR-DRW-00315 - 00323_Rev.C01 | C01 | A | DRW | CIV | NWW | 9 | YS |  |  | PAJV-TRANSMIT-013570 | 2026-06-06 |  |  | Revise & Resubmit |  |  | 2026-05-23
| MLCC-TRANSMIT-015930 | 2026-04-30 | DE.TNL.GN00.MEP.T1.D2 | Package Submission - DCP2 - Tunnel 01 Drainage Package (S0702 & S0704): DE.TNL.GN00.MEP.T1.D2_Rev.C01 | C01 | A | DRW | CIV | TNL | 1 | YS | DCP 2 |  | PAJV-TRANSMIT-013569 | 2026-06-06 |  |  | NOWC | NOWC | [5 empty] | Time extended via PAJV-LETTER-001734
| MLCC-TRANSMIT-016956 | 2026-05-19 | MLCC-C0174-CIV-NWW-GEO-RPT-82200-DCP3 | Re: Report Submission - DCP3 - Geotechnical Design Report for BG31 (DE.ELS.GE00.GEO.G1.D3) : MLCC-C0174-CIV-NWW-GEO-RPT-82200_Rev.C03 | C03 | D | RPT | CIV | NWW | 1 | MSD | DCP 3 |  | PAJV-TRANSMIT-013568 | 2026-06-06 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016687 | 2026-05-13 | MLCC-S0701-CIV-CCV-GAR-RPT-10000 | Re: Drawing and Report Submission - Geotechnical/Structural Design of Temporary Structures for the Retrieval Shaft at Cut and Cover CC01 CH. 107+631,665 ÷ CH.107+661065 : MLCC-S0701-CIV-CCV-GAR-RPT-10000_Rev.C02 | C02 | B | RPT | CIV | CCV | 1 | MS |  |  | PAJV-TRANSMIT-013566 | 2026-06-06 |  |  | NOWC | NOWC
| MLCC-TRANSMIT-016318 | 2026-05-07 | MLCC-N0003-BES-FPS-FFS-MTS-00010 | Material Approval Request for Fire Hydrant System "Naffco / MNG": MLCC-N0003-BES-FPS-FFS-MTS-00010_Rev.00 | 00 | A | MAT | MEP | FPS | 1 | AKR |  |  | PAJV-TRANSMIT-013565 | 2026-06-06 |  |  | Revise & Resubmit | Revise & Resubmit
|  |  | MLCC-C0174-CIF-CDS-GEN-IRE-95002 | Re: ICF Submission - Interface Control Form (CIF) for Space Proofing and Loading Analysis DCP2 - BG31 Station Technical Level Beams and Piers: MLCC-C0174-CIF-CDS-GEN-IRE-95002_Rev.C01 | [9 empty] | PAJV-TRANSMIT-013851 | 2026-06-12 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-N0003-OSM-ROM-GEN-RPT-51090 | Re: Report Submission - DCP2 - Baseline for DCP2 Operation Simulation (PRE.3.1.14) : MLCC-N0003-OSM-ROM-GEN-RPT-51090_Rev.C03 (RCS Resubmission) | [9 empty] | PAJV-TRANSMIT-013848 | 2026-06-12 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | DE.ELS.GE01.MEP.M4 | Re: Package Submission - DCP2 - Elevated Station-MEP-BG32-VAC : DE.ELS.GE01.MEP.M4.D2_Rev.C02 (RCS Resubmission) | [9 empty] | PAJV-TRANSMIT-013831 | 2026-06-12 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-S0673-CIF-CDS-GEN-IRE-95002 | Re: ICF Submission - Interface Control Form (ICF) for L3 and L2 ICF - Foundations - Stabling Building structure loads STR/ARC/MEP & STR/RSY : MLCC-S0673-CIF-CDS-GEN-IRE-95002_Rev.C02 | [9 empty] | PAJV-TRANSMIT-013793 | 2026-06-11 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | DE.ZNE.ZN01.ARD.R0 | Re: Package Submission - DCP2 - Roads Z0039 Package: DE.ZNE.ZN01.ARD.R0.D2_Rev.C01 (RCS Resubmission) | [9 empty] | PAJV-TRANSMIT-013790 | 2026-06-11 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-S0709-CIV-STN-RFC-DRW-13286 | Re: Shop Drawing Submission - Switchbox BB06 External Wall EW-12&EW-14 : MLCC-S0709-CIV-STN-RFC-DRW-13286-13291_Rev.C01 | [9 empty] | PAJV-TRANSMIT-013776 | 2026-06-11 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-S0709-CIV-STN-FND-DRW-13122 to 13126 | Re: Shop Drawing Submission - Station BB06 Base Slab Pour 20 Bottom Reinforcement Details : MLCC-S0709-CIV-STN-FND-DRW-13122 to 13126_Rev.C02 | [9 empty] | PAJV-TRANSMIT-013775 | 2026-06-11 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-N0003-COM-VSS-GEN-PLN-53700 | Re: Plan Submission - DCP3 - Communications (COM) VSS Proof of Concept (POC) (RLS.1.1.9.8.17.1.6) : MLCC-N0003-COM-VSS-GEN-PLN-53700_Rev.C01 | [9 empty] | PAJV-TRANSMIT-013745 | 2026-06-10 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-S0762-UTL-WTS-SYW-DRW-15000 | Re: Shop Drawing Submission - Al Ruwayyah Depot Utilities Potable Water (MLCC-S0762-UTL-WTS-SYW-DRW-15000,MLCC-S0762-UTL-WTS-SYW-DRW-15030 - 15032,MLCC-S0762-UTL-WTS-SYW-DRW-15070,MLCC-S0762-UTL-WTS-SYW-DRW-15200-15204_Rev.C01 | [9 empty] | PAJV-TRANSMIT-013707 | 2026-06-09 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-N0003-AFC-NWW-GEN-SPC-53036 | Re: Specification Submission - DCP3 - Automatic Fare Collection (AFC) – System CyberSecurity Design Specification (RLS.1.1.9.8.17.16.5) : MLCC-N0003-AFC-NWW-GEN-SPC-53036_Rev. C01 | [9 empty] | PAJV-TRANSMIT-013695 | 2026-06-09 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-N0003-PMC-PRC-SCH-PGM-00003 | Re: Programme Submission : Project Master Baseline Schedule - Rev D02 Programme Report - Narrative - MLCC-N0003-PMC-PRC-SCH-PGM-00003-03 | [9 empty] | PAJV-TRANSMIT-013661 | 2026-06-08 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-C0191-CIV-EPD-RFC-DRW-13056 to 13058 | Re: Shop Drawing Submission - Station BB05 - Entrance-B D-Wall Reinforcement Shop Drawings Type-EB1 Primary Panel (B56) : MLCC-C0191-CIV-EPD-RFC-DRW-13056 to 13058_Rev.C02 (RCS Resubmission) | [9 empty] | PAJV-TRANSMIT-013659 | 2026-06-08 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-S0692-CIV-STN-GAR-DRW-13026 to 13027 | Re: Shop Drawing Submission - Structure Concourse Level Wing Beam PTB8 Details for PT, Reinforcement and Anchor Bolt At Grid 19_MLCC-S0692-CIV-STN-GAR-DRW-13026 to 13027, MLCC-S0692-CIV-STN-RFC-DRW-13073 to 13079, MLCC-S0692-CIV-STN-SSR-DRW-13014_Rev | [9 empty] | PAJV-TRANSMIT-013658 | 2026-06-08 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-S0724-CIV-EPD-RFC-DRW-13038 | Re: Shop Drawing Submission - Station BB05-Ancillary-02 D-Wall Reinforcement Shop Drawings Type-AS2 Primary Panel (D10) : MLCC-S0724-CIV-EPD-RFC-DRW-13038-13039_Rev.C02 | [9 empty] | PAJV-TRANSMIT-013642 | 2026-06-08 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-S0724-CIV-EPD-RFC-DRW-13100 | Re: Shop Drawing Submission - Station BB05-Ancillary-02 D-Wall Reinforcement Shop Drawings Type -AS1 Primary Panel (D12) : MLCC-S0724-CIV-EPD-RFC-DRW-13100-13104_Rev.C02 | [9 empty] | PAJV-TRANSMIT-013641 | 2026-06-08 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-S0724-CIV-EPD-RFC-DRW-13040 | Re: Shop Drawing Submission - BB05 Station - Ancillary-02 – D-wall - Type-AS2 - Secondary Panel D11 Reinforcement : MLCC-S0724-CIV-EPD-RFC-DRW-13040-13041_Rev.C02 | [9 empty] | PAJV-TRANSMIT-013640 | 2026-06-08 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-C0003-ARC-PTW-SGN-RPT-00001 | Re: Report Submission - Temporary Passageway Signage Artworks - 03 June 2026 : MLCC-C0003-ARC-PTW-SGN-RPT-00001_Rev.C01 | [9 empty] | PAJV-TRANSMIT-013638 | 2026-06-08 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-N0003-PDS-MPD-MVN-SPC-51000 | Re: Specification Submission - DCP2 – Medium Voltage Switchboard Technical Specification (RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-MVN-SPC-51000_Rev.C03 | [9 empty] | PAJV-TRANSMIT-013607 | 2026-06-08 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-N0003-OCS-SYW-OPM-RFI-10002 | Re: RFI Submission - Request for Information - Required Information for Legacy Interface Control Document : MLCC-N0003-OCS-SYW-OPM-RFI-10002_Rev.C01 | [9 empty] | PAJV-TRANSMIT-013601 | 2026-06-06 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-N0003-DEP-VBR-GNW-RFI-10010 | Re: RFI Submission - Request for Information - Al Jaddaf Pontoon Station – As Built Civil Works : MLCC-N0003-DEP-VBR-GNW-RFI-10010_Rev.C01 | [9 empty] | PAJV-TRANSMIT-013600 | 2026-06-06 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-N0003-PDS-MPD-TRP-SPC-51002 | Re: Specification Submission - DCP2 – Traction Distribution Switchboard Technical Specification (PDS_RLS.1.1.2.2.3) : MLCC-N0003-PDS-MPD-TRP-SPC-51002_Rev.C03 | [9 empty] | PAJV-TRANSMIT-013598 | 2026-06-06 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-N0003-PDS-MPD-MVN-RPT-51002 | Re: Report Submission DCP2 - MV Power Calculations Report : MLCC-N0003-PDS-MPD-MVN-RPT-51002_Rev.C02 | [9 empty] | PAJV-TRANSMIT-013596 | 2026-06-06 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-S0828-UTL-NWW-GEN-RFI-00001 | Re: MEP RFI Submission - Request for Information - Al Jaddaf Pontoon Station - As Built Utilities : MLCC-S0828-UTL-NWW-GEN-RFI-00001_Rev.C01 | [9 empty] | PAJV-TRANSMIT-013587 | 2026-06-06 | [9 empty] | No matching MLCC/GUNAL submittal found for this response
|  |  | MLCC-N0003-CIV-NWW-GAR-DRW-00352 | Re: NOC Drawing Submission - Zone-5 Proposed Removal Of Green Area Trees At Al Rashidiya Area : MLCC-N0003-CIV-NWW-GAR-DRW-00352 - 00357_Rev.C01 | [9 empty] | PAJV-TRANSMIT-013567 | 2026-06-06 | [9 empty] | No matching MLCC/GUNAL submittal found for this response

## Summary
Processing Summary
Total rows produced | 591
New outgoing submittals | 334
Already in master log | 1
Existing rows updated with PAJV response | 232
Unmatched PAJV responses (no submittal found) | 24
Generated | 17/06/2026 08:08